## Slide 1: Planning, & Managing Change In The NHS
“In this world nothing can be said to be certain
except change, death and taxes.”
BENJAMIN FRANKLIN
e-learning
version
If you require additional information there are
Notes
sections
below each slide
use
left-mouse
or
right arrow
to
move-forward
Auto Slide : Please Wait
a module specially designed and developed by Martyn Laycock for HealthKnowledge
Notes: WELCOME ! to this our second Module on Managing Change. This one focuses particularly on planning change – and also key aspects of managing it – managing the people in your team(s), but also, very importantly, managing yourself through change.
If you need a detailed introduction to this subject then we suggest that you firstly look at the sister Module “Introduction to Managing Change in the NHS” which is also available on this HealthKnowledge platform. If you simply need a “refresher” on some of the fundamentals of change plus a quick review of the Models and Tools that can be used, then we recommend that you visit Slide 6 in this Module which provides a comprehensive listing of all the tools and techniques and indicates where precisely you can locate them in this Module.
In this Module we look in detail at the planning and management of the change processes and at changes in Clinical Practice and how they are impacting on generally very high levels of change that are now underway in the National Health Service, driven by the NHS Plan. We also take in-depth looks at teams and team-working and at a key aspect – effective communication during change initiatives.
Benjamin Franklin, famous US politician, made the above statement about change death and taxes over 200 years ago but it still has real relevance today. It suggests that change - like death and taxes - is something to be avoided. Neither death nor taxes are avoidable of course, although people do work hard to postpone their impacts for as long as they possibly can! In the 21st Century, change is all around us; in fact a number of “gurus” reckon that the only constant in life these days is change. The pace of life in most Western communities is fast and change seems to occur with increasing regularity. So, although the changes now underway in the NHS are fundamental and long-term, we feel we can safely say that “we are not alone”.
Experience, however, shows that many people view change with suspicion, see it as a threat. But change can also bring opportunity. To realise these opportunities though, Change needs to be very carefully planned and managed. Managers need to be trained in how to plan, implement and manage change. And their people need to be supported through the change processes, supported by the organisation, supported by their managers.
So planning and managing change, managing people are key themes in this Module. We hope you find it useful.

## Slide 2: Objectives for this Module
On completion of this Module you should :
* understand the role of individuals, teams and
organisations in changing clinical practice in the NHS
* have developed a check-list of tools, techniques, actions, possible problems, solutions and key measurements (Indexed at Slide 6)
* have a sound knowledge about the whole subject of change,
its impacts and how to manage it in today’s work environments
* understand how staff and colleagues can be supported through
transition and the role that team-working can play in this
* have completed a number of practical tasks
and exercises relevant to your own work area
* understand the importance of planning and managing change
* have a summary of the evidence-base to support various change management tools & techniques
use
left-mouse
or
right arrow
to
progress
* Understand the key importance of Communication and be
able to develop your own Communication Plan
Please refer to the Notes
Pages for additional
Information on all slides
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
BACKGROUND & OBJECTIVES :
In 2001 the NHS embarked upon major structural change - part of a government-led “reform” intended to put primary focus on patients/consumers and to invest in, to ‘empower’, the workforce, placing particular importance on involving and supporting “front-line” staff. This major - “step” - change, part of a long-term programme of strategic structural and organisational change would bring many challenges over the five years to 2006 and beyond. This Module has been designed to support managers and key staff whose role it will be guide, steer, influence, manage change. To do this we make particular use of a Model (Slide 14) developed by William Bridges in “Managing Transitions”; we use Bridges’ Model to underpin our approach to managing change.
After completing the “Introduction to Managing Change” and the “Planning and Managing Change” modules users should be able to :
Understand the overall impacts and dynamics of change - its drivers, its dynamics, and the underpinning evidence
Understand the importance of both planning and managing change in the NHS
Recognise the vital importance of involving people in change processes
Apply and use a variety of models and tools designed to help with the management of change
Understand the role of individuals, teams and organisations in change processes
Understand and be able to start using a range of theories, models, tools and techniques of actively managing change
Develop a personal change programme with a check-list of tools, techniques, actions, potential problems, possible solutions and key measurements

## Slide 3: The Change Perspective
Change is inevitable - history shows this
Change = Threat
Change = Opportunity
The ability to adopt and manage change is now a key skill
Change is complex - often messy
Change requires planning and leadership
CHANGE
People generally resist change
“In a changing world the only constant now is change”
COLIN CARNALL, HENLEY MANAGEMENT COLLEGE.
“People resist not only change that is bad for them, but also change
that will benefit them in the long-run.” BOYETT/BOYETT “The Guru Guide”
REPEATED SLIDE FROM
MODULE 1
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
PUTTING CHANGE IN PERSPECTIVE There are huge amounts of change in life generally. Even a cursory survey of recent history - lets say the 20th century – will show the very high levels of technological change, conflict, warfare, political, economic and social change that have occurred. From the development of the automobile and the aeroplane to the concept of nuclear power and nuclear weapons, from the origins of space travel to sophisticated computers and tele-communications, to the Internet. In the Western world, all these things have led to very very high levels of sophistication of people’s needs. But everywhere it seems things change with an increasingly rapid pace. In this Module we will show how change can present both Threats and Opportunities and will stress that good Planning and sound Leadership can help to make successful ‘transitions’ from one state, one scenario, to another. That said we will be emphasising that Change is rarely clean and orderly – most of it is complex, complicated, often confusing – frequently “messy”. We will differentiate between change and transition. There is little, if any, doubt that the rate and pace of change in the 1990s and into the 21st Century has become more intensive, more frenetic – such that the ability to adopt and manage change has now become a key management skill. Gurus such as Charles Handy and change experts such as Colin Carnall of Henley Management College comment regularly on the rate, pace, frequency and impacts of change and tell us that in today’s fast moving environments perhaps the only “constant” is change! A book we have used in the compilation of this Modules is the “Guru Guide” developed by Joseph and Jimmie Boyett - a digest of the views and ideas of 79 of the “world’s most influential management experts”. The Boyetts focus on people’s general fear of change and explain how in resisting changes that are perceived to be bad for them people often also resist changes that could well be good for them in the medium or longer term. Which is why throughout this Module we refer to the organisation’s people over and over again, stress the essential need to understand, support and manage them through organisational change.

## Slide 4: 7 Factors for Success in the Management of Change
planning the change

communicating
and
reinforcing
changes
consolidating and
integrating improvements
FINISH
START

Effective
Implementation
Monitor : Review
“Flex” : Consolidate





commitment
from the top
Create and
Share
the Vision
Effective
Communication
Understand
the
Culture
THERE
IS NO
FINISH!
change process is
typically continuous
Address
Attitudes &
Change
Types
involving
people
- ------->-------------->-------
establishing
change culture
patient driven
Understand
the
Environment
This is a Review slide from Module 1. Please refer to the Notes Pages for additional
Information on all slides
REPEATED SLIDE FROM
MODULE 1
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
REVIEW : 7 FACTORS FOR SUCCESSFUL MANAGEMENT OF CHANGE :
This Model shows the 7 key factors that together can lead to the successful management of change: Classically, significant change (Factor 1) begins with a Vision - a vision for the future and changes that flow from that Vision, that can help it to be realised. In the centre of the Slide we have shown how change in the NHS is, in accordance with the NHS Plan, to be “patient driven”. If the Vision can be articulated to the people who work in the organisation in a committed and convincing way then management will have a much better chance of carrying their people with them through the change process.
The next three factors (2-4) embrace the well-known practice of PLANNING - an essential ingredient in successful change initiatives :
Any change programme needs to take into account (Factor 2) the existing culture of the organisation. The people driving and managing the change need to recognise the culture and think about how people will view/respond to the changes. They need also to look (Factor 3) at the proposed change in the context of the environment – i.e political, economic, social, technological; the changes inside the organisation need to “fit” with what is going on outside. Next, (Factor 4) management will benefit from a detailed understanding of the impacts of change on people - understand how people re-act and respond to change, how attitudes to change can vary from person to person.
There also needs to be a thorough, well-thought-through (Factor 5) implementation plan - systematic, rigorous but sufficiently flexible to build in solutions to problems that might arise.
Factor 6 relates to the whole subject of Communication and how important this can be throughout the entire change process.
Finally Factor 7 affirms the importance of ongoing Monitoring and Review against the Implementation Plan to ensure changes get integrated, mainstreamed, consolidated into the organisation.

## Slide 5: Planning, Implementing & Managing Change: Key Factors for Success
good leadership : good management
clear customer (i.e. patient/consumer) focus
planned, structured approach
good use of the change models to assess/understand:
    cultural aspects
    external environment
    peoples attitudes and responses to change
constant monitoring and review
employee focus :
    involvement
    ongoing two-way communication
    training and support
    benefits of team-working
Auto Slide : Please Wait
Notes: SUMMARY OF KEY LEARNING POINTS
In this Module we emphasise the importance of good leadership, of visible, ongoing commitment from the top of the organisation. People appreciate being presented with a Vision for change – they typically want to know what it is intended to achieve, what the benefits of attaining the required changes are expected to be. People like to make their own assessments, their own judgements. We also stress the very strong need for managers to be trained and supported as they battle, with their teams, to implement often difficult changes, implement not-previously-known processes and systems which may be as unfamiliar to them as to their staff. Training, for mangers and for employees is very important in times of change (see below). If the customer (consumer or patient) does not feature highly in the reasoning for change then we would find this worrying. Most changes should have the interests of the Consumer, the “end-user” at heart - also these groups need to be ‘protected’ as the organisation and its staff move through the change, through the transitional processes that are the hallmarks of change. Organisations take their collective “eyes” off vital Customer Service aspects during change initiatives at their Peril! We will repeatedly stress the need for planning, for a structured, phased approach to change – one that recognises some of the challenges of cultural change and the different ways in which different people respond and adapt to change. Take these into account and often the change processes become less difficult. Ongoing Monitoring and Review, key parts of the overall planning process, are also advocated here – this to ensure that the organisation and its people respond to problems, rise to meet the challenges of change. Last but certainly not least, there needs to be a strong focus on involving and supporting employees through the transitional processes - encouraging them to get involved, help identify and solve problems, to shape and fashion change to the needs of the local environment, the local “market-place”. This is where effective ongoing communication is so very important; effective communication needs to be “two-way” - “bottom-up” as well as “top-down”, so that it “taps” into the rich resource of the people who work, implement change within the organisation.
All the above are key components in the successful planning and implementation of Change.

## Slide 6: Directory Of Tools/Techniques
Force-Field Analysis (used in Module 1, repeated here, Slide 7)
  well-known planning/analysis tool
SWOT and PEST analyses
  generic strategy/assessment tools
7 Factors of Successful Change (Model used in Module1, repeated here, Slide 4)
Endings < Beginnings via the “Turbulent Zone” Schematic: Adapted from William Bridges “Transitions” (used in Module 1, repeated here, Slide 9)
FIVE KEY STAGES IN SUCCESSFUL TRANSITION
  NEW and covered in detail in this Module, Slides 11 -25
PLAN : ACTION : REVIEW (used in Module 1, repeated here, Slide 10)
  Model : Briner et al
THE CLASSIC FOUR STEP APPROACH TO PLANNING CHANGE :
  NEW and covered in detail in this Module, Slides 14-18
Types of Change : Chart (used in Module 1, included as Appendix here)
Change Adopters Graph (used in Module 1, included as Appendix here)
  Everett Rogers
Change “Types” : Chart (used in Module 1, included as Appendix here)
  Binnie & Williams
Impacts of Change: Diagram (used in Module 1, included as Appendix here)
  Colin Carnall : “The Coping Cycl”e
Organisational Culture Matrix – (used in Module 1, repeated here Slide 8)
  Charles Handy
THE CHANGE TOOL-KIT
Auto Slide :
Please Wait
Notes: THE CHANGE TOOL-KIT
Here we summarise a whole range of Models and Tools/Techniques that can help to plan, implement and manage change.
In the next few Slides we will consider several of the key Models and, given its importance to this particular Module. we have covered the “Four Step Approach to Planning Change” in detail in Slides 19-23
We have also collated these Models and Tools into a separate Document that you can explore on this Knowledge platform; it can be downloaded for future use.
There is also an excellent booklet published by the NHS which describes a number of these Models, and many others, in considerable detail. (See “Research Sources” + Final Slide)

## Slide 7: Force-field Analysis
DRIVERS
RESISTORS
Information Management
and Technology
Political/ Environmental Pressures
Multi-Disciplinary
Care teams
Consumer
Demands
Change
fatigue
Lack of time
Cost
pressures
Organisational Culture
Lack of motivation
Government
Interventions
Demographics :
e.g Ageing Population
New Research
& Practices
Poor Communication
Forces Driving and Opposing Change
Combined Clinical
& Social Care
Fear of Change
Internal Politics
Poor Leadership
SEE NOTES
BELOW
REPEATED SLIDE FROM
MODULE 1
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
DRIVERS FOR CHANGE : RESISTORS OF CHANGE
In our chart above – a Force-Field Analysis - we have recorded some of the key Drivers and Resistors of Change in the UK. Many of these are “generic” but there are some which impact specifically on Change and managing it in the National Health Service. Here we comment briefly on the overall key Drivers and Resistors and then in the next Slide look at some of those affecting the NHS in greater detail. DRIVERS for change include ongoing cost pressures, probably reflected in the constant pursuit of new productivity and efficiency gains and there are environmental (e.g removal/treatment of “waste”) considerations. Working against these Drivers are a number of RESISTORS : we have already mentioned organisational culture, perhaps reflected in the lack of motivation of people to change or the impacts of “internal politics”, the latter often driven by an inherent fear of change, of its possible consequences. In some cases people suffer from what is called “change fatigue” – too many change initiatives. Poor leadership can certainly inhibit attempts at change as can defence of “status quo” (“we’re O.K.as we are”) and perception of lack of time in which to handle the changes.

## Slide 8: Organizational Culture
Power
wielded by individuals in the centre
Influence: Central Authority
Role
Communication flows up but not across, stability is the key
Influence:
work up each “leg”
Task
power flows up and
down and across.
Influence: key individuals and ‘buy in’ from most members
* *
****
*******
* *
Person
individuals are important
Influence: everyone
Handy C. Understanding Organizations. Aylesbury: Penguin Books, 1985
4 Main Cultures
“Failure to take culture into
account will result in just
that – failure!”
Neil Russell-Jones
“The Managing Change
Pocketbook.” 1995
use
left-mouse
or
right arrow
to
progress
See Module 1 for
More on Culture
CHANGE
MODELS
REPEATED MATERIAL FROM
MODULE 1
Notes: ASSESSING ORGANISATIONAL CULTURE
Here we give a brief overview of the importance of organisational culture when planning and implementing change. Detailed coverage is provided in the “Introduction to Managing Change” Module. Above we show the four key types of organisational culture as identified by Charles Handy (“Understanding Organisations”) : POWER cultures are controlled by a powerful central person or group and activities radiate out from the central “hub”. Handy characterises the Power culture by a “spider’s web”. Power cultures are relatively easy to change if the change is driven by the central authority. ROLE cultures have a similar ‘control group’ but Handy represents this culture by a Temple; powerful Senior Management groups are the ‘pediment’ of the Temple which is supported by various functional “pillars” e.g finance, marketing, operations, personnel. Communications typically travel up and down the pillars but there is relatively little communication across the organisation, making such organisations notably hard to change. They are classically bureaucratic, being dominated by procedures and rules. TASK organisations, in contrast, are job and/or project orientated; the emphasis is on getting the work (‘jobs-in-hand’) done, rather than having complex rules and procedures about how it should be done. In Task cultures the power and communication processes are more widely distributed; typically these are project-driven organisations; to change them requires the ‘buy in’ of a majority of people in the organisation.
PERSON cultures have a clear focus on a number of key individuals who work in minimalistic structures for their own benefit; often they are seen in professional practices (e.g Solicitors and Accountants) but they can also be seen in the NHS - typically in Group Practices of General Practitioners (GPs) and often amongst Consultants. IMPORTANT NOTE : Some organisations display the characteristics of one or other cultural types. Others - and we reckon the NHS is one of these - exhibit hybrid characteristics and are a blend of cultural types, making them potentially even more difficult and challenging to manage and change. We strongly recommend you visit the detailed coverage in Module 1.

## Slide 9: Bridges’ Model of Transition
change
The “turbulent zone” is the ‘neutral zone’ between the ‘old reality’ and the ‘new way of doing things’ i.e where change activity is at its most intense ; where change management is most challenging
adapted from :
Old
Way
Beginning
of the New way
New
Way
“Turbulent Zone”
Transition
Process
Use Left Mouse or Right Arrow to progress
Ending
(of the Old way)
CHANGE
MODELS
REPEATED SLIDE FROM
MODULE 1
Notes: CHANGE and TRANSITION
Change Consultant and Author William Bridges wrote, back in 1991, a successful book called “Managing Transitions”. We have adapted Bridges work slightly to show how “turbulent” change can often be and we will use the Model to steer us through this Module.
The first principle Bridges introduces us to is that in all change there is an “ending” and a “beginning”. The “ending” is the end of an “old” way of doing things. The “beginning” is the start of some “new” way of doing things. Bridges refers to the process of getting from the End of the “old way” to the Beginning of the new way as a transition. He refers to transition as a “neutral zone” between the “old reality” and the “new vision”, an area where many, often most, of the problems of implementing and managing change are most evident, an area where managing the change is at its most challenging.
The “neutral zone” writes Bridges is a “nowhere” between “two somewheres” – he likens life in the neutral zone to letting go of one trapeze with the faith that the new trapeze is on its way. In the meantime, he writes, “there’s nothing to hold on to.” !
We have re-named the Neutral Zone the “Turbulent Zone” because we feel it more adequately describes the “atmospherics” when organisations and their people go through major, fundamental (“step”) change (see Slide 9). With “step” change the transitional period can be longer, the management challenges more intense - to be truthful, it also means the chances of failure (of the change initiative) can be that much higher.
That is why we strongly advocate planning change initiatives, using a disciplined, planned approach to managing change.
NOTE : we have shown a series of “steps” in the graphic in order to represent the various stages that a ‘transition’ normally moves through; we will explain these stages or steps in Slide 16 and show how in reality they often merge into each other.

## Slide 10: Plan : Action : Review
a simple Model that defines a proven
approach to planning and implementing change
Developed from Briner W, Geddes M, Hastings C. Project Leadership. 1987
plan
action
review
plan
action
review
plan
action
review
CHANGE
MODELS
Incorporate regular Reviews into your Planning Cycle
Auto Slide :
Please Wait
REPEATED SLIDE FROM
MODULE 1
Notes: PLANNING CHANGE We have said that one of the hallmarks of successful change is that it is well planned. Good planning for change takes into account the culture of the organisation, the attitudes of individuals and is conceived against a thorough knowledge of what is happening in the external environment. There is little doubt that good planning helps Change leaders, and the managers who have to implement the changes, get through problems - by anticipating them wherever possible but also by being ready with contingencies should problems arise. Also by providing the flexibility within the organisation for those involved in the changes to help find solutions themselves.
There is a well-known and well-used PLAN-ACTION-REVIEW approach shown in the schematic above. Using this approach realistic plans are firstly drafted (in this case to get the organisation – and its people – through the change, through the “turbulent zone” and out to the “new beginning” – see Transition Model, previous Slide). Then various actions and activities are carried out in accordance with the Plan. A good, practical, pragmatic Plan helps to provide a form of structure, a form of discipline through which the Change can be implemented. In this case managing change, managing transition, relies on many of the components of Project Management - see separate Module.
Of key importance is the Review part of this process – change leaders and line managers need to continually review how things are going – they look at progress – and at problems; they “flex” their plans – and their actions – accordingly. In this way the whole process is constantly being monitored and reviewed, management retain control and can act accordingly. In this way it is considerably less likely that the change initiative will “stall” of “fizzle out” – and more likely that the organisation and its people will get through the “turbulent zone” and on to the “new beginning”.
In the NEXT slide we have augmented William Bridges’ “Transition” Model, adding our own 5-Step Process - “The Five key Stages of Transition” - to guide us through the various stages and phases of change……..

## Slide 11: Five Key Stages in Successful Transition
NEW
SCENARIO
KEY SLIDE
for this Module
Planning &
Preparing
1
Kicking
It Off
2
Achieving
Lift-Off
3
Keeping
It Going
4
Managing
It Through
5
use
left-mouse
or
right arrow
to
progress
TURBULENT
ZONE
TURBULENT
ZONE
FIVE
key
stages
OLD
SCENARIO
COVERED IN DETAIL
SLIDES 12-24 + 25
Notes: FIVE KEY STAGES OF SUCCESSFUL TRANSITION In Module 1 we used a model “Seven Factors for Success in the Management of Change (Slide 4) In this Module we are using Bridges’ Transition Model (Slide 14)) which we have adapted and augmented by defining five key stages that will help us make the transition from the “old” way of doing things, to the “new” way of doing things : Firstly, Key Stage 1 is the Planning & Preparing stage; in this stage the organisational (internal) and external environments are taken into consideration - together they give us the “backdrop” against which the change is to be carried out. For this we use SWOT and PEST analyses; we also need to take a very close look at our organisational culture - the “way we do things around here”. Charles Handy’s work on organisational culture is particularly useful here (Slide 13). We also should use the various Models that we have covered in Slides 6-12, described in more detail in our Change Tool-Kit. There should be a PLAN for Change that takes all relevant factors into account, considers the main challenges and potential problems and how they can be managed. Next, (Key Stage 2) is the LAUNCH of the change initiative; the reasons for the change are explained to those who are to be involved in implementing it and the communication processes should ensure people know their roles in implementing the change, also how staff are to be supported and trained through the change processes and how communications will be handled. The Change Plan should also detail how the early stages (Key Stage 3) of the change initiative are to be managed – we call this “achieving lift-off”. In this stage it is important that those who manage the change process ensure that some early successes are achieved; the Change Plan should show where and how such successes can be achieved. Key Stage 4 (we call this Keeping it Going) is important because even where Stages 1-3 have been well handled, this is the stage where the organisation can “lose its way”, where the change initiative can become “sand-banked” or “fizzle-out”. Stage 4 is at the core of the “turbulent zone” where the key challenges of securing the change need to be managed. Key Stage 5 (“Managing it Through”) is the final Stage designed to build on the achievements in Stages 1-4, to ensure that the overall transition leads smoothly into the “new beginning”, the new ways of doing things.

## Slide 12: STAGE 1 : Planning for Change
Change is about achieving a future desired state of affairs
in part it is an act of ‘crystal ball gazing’……
but we can use a variety of models to make informed decisions
the first part of the change process is planning the change
Adapted from “Managing Organizations”
WILSON & ROSENFELD, 1990
  - goals are agreed
  targets are set
  timetables and “milestones” are established
  processes are determined
  people are organised
  monitoring systems are put in place
NOTE:
Project Management
is very useful in
Change Management
PLANNING CHANGE
Auto Slide :
Please Wait
Notes: THE PLAN FOR CHANGE
Throughout our whole approach to Managing Change we have been stressing the importance of planning change; doing so helps managers consider the background to the change, helps them plot a route through the change processes - through the “transition” which, dependent upon the degree and levels of change, may last from a few months to several years. Implementation of the major NHS changes, for instance, will take a number of years and will be undertaken in Phases - firstly some fundamental “step” change (see Slide 9), to establish a completely new structure, a new focus - often a focus on customers (NHS – patients/consumers) and/or a clear commitment to empowering staff Typically this is followed by a period of consolidation, then some further substantial “incremental” changes that will take the initial initiative forward. In larger change initiatives those at the top who design and initiate the change will normally issue overall ‘Change Plans’ with the “Human Resource” aspects often covered in separate document. Then divisions and departments will typically be asked to develop their own change plans to take into account “local” (i.e divisional and departmental) conditions. In well planned Change initiatives individual managers and key groups of employees should be invited to become involved in the planning process so that they can firstly understand the reasons for the change, know the objectives and required outcomes, then consider how best to implement the changes in their own work areas. In the case of major changes, such as those in the NHS, a period of Consultation with main ‘stakeholders’ will often be included Typically Goals and Objectives are agreed, targets and timetables set, key “milestones” established. This is where the use of “Project Management” techniques can be particularly useful (see Project Management module). Actions, activities, processes are determined and, importantly key monitoring processes are put in place; management need to measure performance against Plan and to “flex” and “tailor” the Plan in light of the progress made, severity of problems encountered, solutions found. This is where the PLAN : ACTION : REVIEW approach (Slide 15) is so important.

## Slide 13: The NHS Plan : KEY FEATURES “A Plan for Investment. A Plan for Reform.”
a long-term programme for reform & performance improvement
to create a health service fit for the 21st century
a health service designed around the patient
national standards and frameworks in key areas e.g CHD, Diabetes
key emphasis on reducing inequalities in delivery of health and social care across the UK
additional funding will see the NHS grow by a third in real terms over five years
significant increases in numbers of doctors, consultants, nurses
key focus on people : empowerment of staff
radically changed structures :
  Social Services integrated with NHS
  Strategic Health Authorities
  Primary Care Trusts
  Integration of Public Health
  Greater involvement of Private Sector
PLANNING CHANGE
Auto Slide :
Please Wait
NHS Plan
July 2001
Notes: THE NHS PLAN : KEY AIMS AND FEATURES
We show in the Slide the key features of the NHS Plan, launched in July 2000 and now to be implemented via “Shifting the Balance of Power”- the major change document issued in July 2001 detailing the structural changes that are to take place as part of a “long-term programme of reform and performance improvement in the NHS”.
The programme of change is “designed to change the culture and introduce new and improved ways of working”; a number of underpinning principles are stated including the support of staff through the transition process and a commitment to “keep as far as possible the skills, experience and commitment of existing staff.”
This is by far the biggest change programme introduced in the NHS since it was created back in 1948 and will present a series of major challenges to managers and staff throughout the Service. It will involve, overall, a transition period of several years. Major structural (“step” - see Slide 9) changes will be implemented by April 2002. Then a period of consolidation will see further change initiatives underway - recruitment of more doctors and nurses, up-grading of premises, the introduction of new work-practices that will put the patients and the front-line staff who serve them at the very heart of the reformed Service.
NOTE : there are key commitments in the Structure Plan - and the accompanying Human resource document - to putting the patients first and to “keeping staff informed during the change process”. It is also stated that every effort will be made to avoid redundancies and that a “Clearing House” system will be set up in each region to enable displaced staff to find employment wherever possible.

## Slide 14: Planning Change : The Classic FOUR-STEP Approach
1. WHERE ARE WE AT NOW? (= Present Position)
2. WHERE DO WE NEED TO GET TO? (= ‘Destination’)
3. HOW WILL WE GET THERE? (Our Map and Milestones)
4. HOW WILL WE KNOW WHEN WE GET THERE? (Measurements & Milestones)
PLANNING CHANGE
Auto Slide :
Please Wait
KEY SLIDE
for this Module
COVERED IN
NEXT 4 SLIDES
Notes: PLANNING CHANGE : THE FOUR-STEP APPROACH
Here we introduce a very useful structured approach to Planning which has been developed from work done by Price Waterhouse in connection originally with marketing planning and more recently applied in Change Management planning. (We have included a Template for this 4-Step approach to Change Planning in the Change Tool-Kit.)
The 4-Step approach is a simple enough structure that helps us to think firstly (STEP 1) about “where we are at now”, to establish our present position – what we sometimes refer to as our “current reality” – an honest and realistic assessment of our position across key factors in the organisation generally and in our part of the organisation specifically; this really needs to be honest and realistic as it is a key part of the process; any ducking of issues or avoidance of existing problems here will have detrimental impacts later. We then consider (STEP 2) our Vision (referred to in Module 1) – which we refer to here as “where we want to get to”. In a large organisation, such as the NHS, there will almost certainly be an overall Vision, often enunciated in a Plan for Change ( e.g The NHS Plan) and supporting documents. But it is also necessary to consider the local situation – within the overall Plan what do we have to achieve in our area? Where do we need to get to? STEP 3 is an important one. “How will we get there?”. This will be our own journey plan, our own map or Plan for Change and will include a series of detailed actions and steps that we will take to help us to get to “where we want to go”. STEP 4 has to do with key measuring and monitoring aspects. Once we have our journey plan, our map our Plan for Change we need to set monitoring points to check how things are going. Thus we schedule key review points as part of our PLAN : ACTION : REVIEW approach (see Model, Slide 15). To do this effectively we need to determine some key performance indicators (KPIs), things that we will measure and assess to help our monitoring and evaluation processes.
We look at each Step of the 4-Step process in the next four Slides………………..

## Slide 15: Planning Change : STEPS I & 2
1. Where are we at now?
  the framework under which we operate
  our ‘domain’
  our ‘current reality’
2. Where do we want to get to?
WHAT WE WILL DO = The “Mission”
and BY WHEN? Draft Timetable with “Milestones”
PLANNING CHANGE
Auto Slide :
Please Wait
Notes: WHERE ARE WE AT NOW ? The better we understand where we are at now the better we should be able to plan our change initiative; so a SWOT analysis (see Tool-Kit) and perhaps, where relevant, a PEST analysis should be carried out. This should be done honestly and realistically - problem areas and current issues need to be clearly identified. Strengths and Weaknesses should re realistically assessed. We should through these processes establish any obstacles or barriers that exist in the present situation; we will need to plan to try and resolve/eradicate these within our Plan for Change. There is an old Chinese Proverb that says “ if you don’t know where you are going, any road will get you there” but if you don’t know fully where you are starting out from then this will cause you real problems also. So, we emphasise that the “where we are at now” assessment is a crucial, critical “first step”. The better, more accurately and honestly this is done, the better the overall change and transition processes are likely to be.
WHERE DO WE WANT TO GET TO ? This lies at the very heart of the Chinese proverb mentioned above. What are we trying to achieve by this Change initiative? What is it that we are required to do? What are our Goals, our Objectives, within the change Plan? Clearly state these and then look at them against the outputs from Step 1 (“where are we at now”) and then Steps 3 & 4 become much more meaningful. In essence we are working here towards defining our “destination” so that in Step 3 we can develop our “map”, our Plan for Change
In this connection it often helps to try and develop a brief ‘Vision’ or ‘Mission’ statement - to encapsulate in a sentence or two where it is, in organisational terms, you need to get to. This done you should then seek to determine some “milestones” (you can find help on these in the Project Management module), some key points along the way. And, as we say in Project Management, make sure your milestones are realistic and attainable. Don’t let your milestones become “millstones”!

## Slide 16: Planning Change : STEP 3
How will we get there?
this is our ‘map, our Plan for Change :
OUR OBJECTIVES:
we’ll measure our progress and performance against these
OUR KEY THRUSTS:
(i.e areas around which actions will be grouped)
OUR PEOPLE:
the people who will help us get there
- types, abilities, commitment levels, likely contributions
KEY ACTIONS:
list of actions & activities that will “make it happen”
PLANNING CHANGE
Auto Slide :
Please Wait
Notes: HOW WILL WE GET THERE ? Our Plan for Change : Only when we have established our “Starting Point” and looked carefully at our Vision (see previous Slide) can we start to develop the structure and detail of our Change Plan. Steps 1 and 2 are essential steps to help us do this as thoroughly and as meaningfully as possible. Done well, Steps 1 and 2 will help inform and shape your Change Plan around the realities of “where we are at now” and “where we need to get to”. Skimp on either Step 1 or Step 2 and you could end up in serious difficulties however. It is very important to adopt the overall discipline of the 4-step Approach.
So, with Steps 1 and 2 fully completed we can start to actually draft our Plan for Change!
The Plan should clearly state the key Goals and Objectives - what is to be achieved and by when. It is useful here to apply the discipline of summarising what is to be achieved within a brief, succinct “mission” or “vision” statement. The Plan should indicate the overall structure and scheduling of the change, detailing the key actions and how, and by whom, they are to be carried out. Many of the advantages of using a “Project Management” approach can be realised when tackling the generally difficult subject of managing and implementing change (see Introduction to Project Management module). Following the overall Project Management approach, “milestones” should be set - these are “checkpoints” where reviews are carried out, assessments made as to whether achievements and progress are in accordance with Plan. Importantly, the Plan should indicate how the organisation’s people are to be motivated, trained and supported through the proposed change. The contributions that people can make towards successful change and transition should not be underestimated. Here the use of the various Models for change (Slides 6-16) can be of considerable benefit. Evidence from research on change indicates that efforts to get a sizeable proportion of an organisation’s people to support and contribute towards the change processes are frequently well rewarded in terms of better, more effective progress through the transition process, through the Turbulent Zone.

## Slide 17: Planning Change : STEP 3 (continued)
HOW WILL WE GET THERE? (continued)
OUR KEY CHALLENGES (i.e. for the team)
How strong is Commitment from the Top - and further down ?
What shape are the “troops” in? (morale ,change fatigue)
What’ll make the most difference : short-term, long-term
Key People - “On-Board”? OR “To be Won Over” ?
Focus on ‘Size of task’ : “Complexity of Task”
MY KEY CHALLENGES
what do I need to know to make this happen ?
what do I need to DO to make this happen ?
what Training - and Development - do I need ?
PLANNING CHANGE
Auto Slide : Please Wait
Notes: HOW WILL WE GET THERE? Key Challenges :
As part of our planning for change there are opportunities to address some of the fundamentals that contribute to successful transition:
Firstly, we should consider the strength of the commitment from top management to lead and support the change processes (see ‘Seven Steps to Successful Change’ which underpinned our Introduction to Change module); also to consider the key challenges presented by the change initiative locally. How strong is our own commitment to the change. How well are we prepared? What do we need to do to prepare ourselves for the challenges that change presents?
In particular we need to consider the shape our people are in - their morale and motivation; how ready are they for the change? What training and support will they need? This all needs to be built in to the Plan. We also need to consider how our people will re-act to the changes - see Adopting Change, Change Types and the Psychology of Change (Slides 10-12)
All of this will influence our communication plan - how we handle the whole communication process. As we will stress later the communication Plan is a very important part of the overall Plan for Change. How will we announce (launch) the change initiative? How will we communicate with our people throughout the transition processes? (see Slides 41-46)
As managers and supervisors we obviously need to consider how we can manage and support our staff through change. But it would be foolish to ignore ourselves, to overlook our own needs. So it’s equally important to ask ourselves “what do I need?”. What do I need in terms of training and support if I am to make a good job of managing this change? What learning and new experiences do I need in order to get both myself and my team through the transition process, to get through to the “new beginning”?

## Slide 18: Planning Change : STEP 4 : measuring, monitoring, reviewing
4. HOW WILL WE KNOW WHEN WE GET THERE?
Measure and Monitor Against Plan:
  are we on schedule (time)?
  milestones (= “check” or “review” points) are very useful
  is the team, are the team members, performing?
  there will be Quantitative and Qualitative objectives
Regular Reviews :
  team reviews : executive reviews
Set “Key Performance Indicators” :
  targets/objectives
  if you’re getting these, you’re getting there
  if you aren’t then find out why!
PLAN
ACTION
REVIEW
PLANNING CHANGE
Auto Slide :
Please Wait
Notes: HOW WILL WE KNOW WHEN WE GET THERE ?
Step 4 in our 4-Step approach to Planning is to do with the key aspects of measuring and monitoring our performance against the Change Plan, not just as we approach our destination but during our journey through the transition processes.
Are we achieving our Milestones? Are things running to schedule? If we are falling behind - why?
Thus we advocate regular performance reviews, as part of our overall PLAN : ACTION : REVIEW approach. as we move through the Change Plan. To make these Reviews as meaningful as possible it is important to determine at the outset some “key performance indicators” - some ‘measures’ against which progress and performance can be assessed. It’s here that good goal and objective setting can prove very useful. For instance the Plan may state an objective that “the new customer service arrangements be completed and underway by 31st May” or “the move to new offices takes place on 30th September”. But clearly for either of these things to be achieved, work will need to be carried out ahead of the target dates. So good scheduling is very important. If critical pieces of work do go wrong to an extent that they cause other actions to be delayed, then it will be important to take some kind of remedial action as soon as possible. Good planning will try to anticipate where such delays or performance failures might occur – and to have potential solutions identified should the “worst happen”.
An important thing is : when things do go wrong, think about why. This may just help you to avoid similar problems in the future!

## Slide 19
Planning for Change – The People Factor
ORGANISATIONS initiate change (normally)
only People can “make change happen”
PEOPLE
But the key to successful change is :
managing
– and motivating - PEOPLE
PLANNING CHANGE
Auto Slide : Please Wait
Notes: KEY FOCUS ON PEOPLE It is vitally important at the Planning stage to understand how crucial an organisation’s people are to in the whole process of change. Without doubt, people, and the way they are managed and motivated can make a significant difference to the degrees of success achieved. Through our Change Models (Slides 6-12) we have shown some of the key impacts of change on individuals; we have also stressed how people need to be supported through change, through the whole transition process from the ‘old’ way of doings things to the ‘new’. This key focus on people needs to happen at several levels : firstly in the overall planning and structure for change, which is typically developed by senior management; then at divisional levels where divisional managers will need to work to shape and tailor the changes to suit the characteristics of their own operations, their own people. From there the change process is typically “cascaded” down to area and departmental levels - where normally the inter-face with the vast majority of an organisation’s work-force exists. It is at this lower, operational, level where much of the critical change implementation takes place - and where most of the operational management challenges occur. As a manager you may have been involved in designing and developing the overall change initiative; more likely you will be involved at divisional or operational level - as part of the cascade process. But whatever level you are involved at, a deep understanding of how people re-act, and often resist, change can help you manage, motivate and support your people through the transition process. The NHS Plan, issued in June 2000, set the overall Vision for the “new NHS”. In July 2001 the “Shifting the Balance of Power” (StBoP) document addressed the detailed structures and timetables for change; it detailed the key emphasis that would be placed on “putting the patient first” and also how front-line staff would be empowered, given more freedom and responsibility to carry out their work. A “Human Resources Framework” which supplemented the “StBoP”document addressed many of the critical human resource aspects of the NHS Change Plan. It re-iterated that the transformational cultural change in the NHS would put the individual “at the heart of everything we do” and “support front-line staff in delivery”.

## Slide 20: Develop Your “Inner Circle”
a small group of key and committed people you can trust, who can work with you as you ‘transition’
some may not be in your close domain - but will have the vision, skills, ideas that you need, they can contribute
this may well not be a formal group
PLANNING &
MANAGING CHANGE
Auto Slide : Please Wait
Notes: INTRODUCING THE “INNER CIRCLE”
The concept of “Inner Circles” has useful applications during change initiatives. You may well find this approach useful:
The idea is that you as a manager of change develop your own Inner Circle – your own “support group” of people. This will not necessarily be a formal group, much more likely an informal network, a distributed support mechanism - one you can call upon at key times during the change programme.
The concept is that managers develop their own “circle” of people who can help and support them, as necessary, as they move through the processes of transition. Often the people in Inner Circles are managers - but not always; often they are people located quite close to you in work terms - but again not always, they may for example be managers undergoing the same or similar change programmes in other locations, other areas/departments or they may be people with specialist knowledge or experience who can be particularly helpful in key areas. Generally your Inner Circle will include people who can help you, people - often in the midst of the change themselves - who you can talk to, discuss problems and possible solutions.
Inner Circles are typically informal networks of people who support each other through change. So informal that they may not even be referred to as “Inner Circles”, they may just be there in the background as a people-based support mechanism helping you to manage the transitions upon which your success will depend.

## Slide 21: STAGE 2 : Kicking It Off
Typically once the Planning & Preparation
have been done there is a LAUNCH of the
change programme – frequently a formal
launch that is, where necessary, then
cascaded down the organisation
Smaller change programmes – or departmental versions of
larger programmes – may have an informal launch
The KEY thing is to have a point where people are :
made aware that the change initiative is getting underway
aware as to the reasons for it, its objectives/outcomes
aware of their role in it, how they can “play their part”
:either as individuals and or members of teams
- aware of how it is likely to affect them
Auto Slide :
Please Wait
PLANNING &
MANAGING CHANGE
Notes: LAUNCHING THE CHANGE INITIATIVE Large-scale and organisation-wide Change initiatives are often launched first to senior the middle/junior managers, then “cascaded” down the organisation to divisions, departments, sections etc. Smaller change programmes, say for a department or one area only, may have a formal launch, often a more informal announcement that the initiative is to get underway. The KEY thing is to make every effort to get the people who are going to be involved in the change “on-side”, to let them know what’s to happen and when, to explain the reasons for the change (people typically appreciate knowing this, even where they may not necessarily agree with the reasons) and to explain their role(s) in it. We stressed in Module 1 - and stress again now - that if you can win-over the majority of your people early in the change process then you are much more likely to get a successful outcome. It helps to make the effort to “get people involved”.
Evidence generally shows that where employees can be encouraged to get involved, contribute to the change processes, they are more likely to take “ownership”, help steer through the transition processes towards success in achieving the planned changes. In the past there have been instances across many industries and sectors where managements have not fully communicated the background and reasons for change - leaving middle and more junior managers with a more difficult task of trying to convince people that the changes are “for the best”, that things will work out “all right”. It is fear, often fear of the unknown, that makes people anxious or worried about change. Best Practice indicates that the more accurate information management provide, typically the better the chances of successful transition..
We will explain later in this Module the importance of good communication as part of the transition processes - it is not enough simply to tell people at the outset what’s going to happen; the communication processes need to carry on throughout the entire change initiative. Where managements successfully encourage two-way communication (“top-down” and “bottom-up”), where they encourage employee involvement during transition, Best Practice shows that the transitions are frequently smoother, the outcomes (achievements) often better.

## Slide 22: STAGE 3 : Achieving Lift-off
at or following the ‘launch’ of your transition initiative:
  involve your Team, get people involved
  target the ‘Early Adopters’ (13.5%), the ‘Innovators’ (2.5%) will typically come to you!
  be looking towards the “Early Majority” (34%)
don’t be too ambitious
keep in touch via your ‘Inner Circle’
aim for an early success or two but NO “quick-fixes”!
communicate - and celebrate! - Success
Auto Slide : Please Wait
PLANNING &
MANAGING CHANGE
Notes: AFTER THE LAUNCH OF THE CHANGE INITIATIVE…….. Let’s assume the change programme has been well planned and introduced; there’s been a generally helpful “launch”, management have explained the changes, explained the reasons for them, explained what people’s roles in the transition are likely to be. The initiation of the Change programme has been ‘cascaded’ down the organisation. Now its time to “knuckle down”, get on with things, try and make things work. Teams and team-working can be very important, very useful here. Often the “we’re all in this together” approach (the inclusive approach) helps people support each other, helps them search for ideas, seek solutions to problems. It’s often a good way of getting people “involved” although (see Change Types - Slide 11) they won’t all rush towards the change programme pledging their full support; many will remain apprehensive, some could be downright hostile! The challenge for managers is to win over the ‘early majority’; typically the innovators (the ‘pioneers’) will have identified themselves and will be busy asking you to give them key roles in the changes. And, if the changes have been well explained and appear well “thought through” then the “early adopters” will soon come onboard too. The “early majority” are somewhat more reticent, they wait and they watch, they assess. But many of them are ready to be convinced. Good communication and an early success or two should convince them that they should be involved. If you can win over the ‘early majority’ (typically 34% of the total) then you should be at or near the half-way stage - and heading hopefully towards success. But - don’t be too ambitious, don’t try to push people too hard; most people prefer space, and to make their minds up in their “own good time”. In the quest for “early successes”. Resist the temptation to go for a “quick fix” or two; these rarely work, people see through them and this heightens their concerns about the validity of the change generally. Good positive two-way communication is very useful through this stage, keep people informed : informed of progress, informed about problems - where possible invite them to help you find solutions. And where you do achieve successes, then celebrate that success. People appreciate a “pat on the back”, a little “thank-you”, a celebration - perhaps with encouragement to move onto the next big challenge(s). Celebrating success can be good for morale.

## Slide 23: STAGE 4 : Keeping It Going
the challenge is to maintain the Momentum
keep up the PLAN : ACTION : REVIEW
  monitor against:
    KEY PERFORMANCE INDICATORS
    MILESTONES
  be flexible, “learn as you go”
  deal with problems as they arise
  make good use of your Inner Circle
maintain activities : keep people involved
flex and continue the COMMUNICATION
continue to celebrate Success
steer thru’ the ‘Turbulent Zone’:
  encourage discarding
  encourage ‘adoptation’
Auto Slide :
Please Wait
PLANNING &
MANAGING CHANGE
Notes: MAINTAINING THE MOMENTUM Even when a Change programme has been well planned and launched there is still a key challenge in keeping it going; this is Stage 4 in the transitional process. Sometimes change initiatives flounder, they can become bogged down; there can be set-backs and delays - which might impact adversely on morale. So it is important to be firstly aware of this; also to be alert to the problems a slow-down might cause. The challenge is to keep things moving, to stick to the Change Plan, to be on the look-out for problems before they arise……. Regular reviews will help here; they enable you to stand-back from all the activity and to take a hard look at what has happened, what is happening - and how things are shaping up for the remainder of the change programme. Reviews help you spot potential problems before they become real problems, allow you time to find solutions, take evasive or remedial action. Elements of Project Management can be very useful here - notably the incorporation of “milestones” into your Change Plan and the measurement of progress against agreed ‘Key Performance Indicators’ (KPIs). In this phase of Change you’ll need to be particularly flexible, “fleet-of-foot” - you’ll need to respond as quickly as possible where you spot things might be going wrong. It is in this phase that you may well need to rely more heavily on your “Inner Circle” (see Slide 24), to discuss problems, possible solutions, get the experience of people who may have experienced similar problems, found ways of solving them. We have said that Change is frequently ‘messy’ and it is in this phase - right in the middle of the ‘turbulent zone’ - where it can become most challenging. You will need to have regular dialogues with your team, encourage them to work together, work with you to find ways through some of the difficulties that will almost undoubtedly arise in this phase. It is very important to keep the communication processes going during this Phase as you steer through the Turbulent Zone. As a manager you’ll be working hard in this phase to help people ‘discard’ the past and to adopt the new ways of working (see Coping Cycle, Slide 12). But don’t forget, where challenges are met, to look for ways to celebrate success - it helps keep the momentum going.

## Slide 24: STAGE 5 : Managing It Through
the Innovators and the Early Adopters are on board – and busy
50% of the Early Majority are “on board”; more are “thinking of getting involved”
a few key Opponents have been won over
one or two people have Emigrated, a ‘Terrorists’ or two may have “surrendered” - or moved on to pastures new
NO – not YET! DON’T Stop Now !
Keep the Processes Going : Build on SUCCESS !
PLAN : ACTION : REVIEW
Don’t forget your ‘Inner Circle’
Ensure ‘new recruits’ are involved
Keep Communicating :
Work on the Late majority
Auto Slide :
Please Wait
MADE IT ?
see the
job through !
PLANNING &
MANAGING CHANGE
Notes: TOWARDS THE ‘NEW BEGINNING’ – Managing it Through This is Stage 5 in the Transition process. By now we will be well through the Turbulent Zone and hopefully looking towards coming out the other side - to attaining the ‘new beginning’. The Innovators and Early Adopters will be on-board and, hopefully, working enthusiastically with you through the actions and activities required in the Change Plan. By now you should have many of the ‘Early Majority’ (see Slide 10) with you, discarding the old ways and becoming more enthusiastic, hopefully about the new ways, new structures that represent the ‘new beginning’. You will probably have had a few battles with some of the ‘honest opponents’ (see Slide 11), and hopefully been able to win some of these over (it can make a big difference to others, and to overall morale, when you do!). You might have had some people – ‘Emigrants’ - who decide to leave - some people are so anti-change that they decide to make changes themselves - to move elsewhere!. And the ‘terrorists’ - or ‘members of the underground resistance’ as Binnie and Williams call them - will probably be quietly ignoring much of what you say/do, some of them actively working in the background to prevent some of the changes happening. ‘Terrorists’ are often a ‘fact of transitional life’! All of this can of course create extra challenges as you work hard with your team to cover the work done by leavers, to fill gaps etc.
But you haven’t made it yet! You haven’t reached the ‘new beginning’ quite yet and typically there is still much to do. You need to keep up the momentum of the Change Plan, to build on successes that have been attained. You can probably still get considerable value from your Inner Circle (Slide 25) and you’ll probably be working hard now to ensure the ‘late majority’ come on-board, perhaps also to settle in new people recruited to replace any who might have decided to leave. Resist any temptation to relax the communication processes at this stage; keep people involved, keep them informed - about problems as well as progress. A challenge now is to encourage your people to take “ownership” of the new ways of doing things - help consolidate them into how things get done in the future.

## Slide 25: Determination to Succeed
There WILL be times…when:
  you need to go ‘one step back’
  you are let down by a friend or supporter
  you need to re-group, re-new
  you need to come up with a new Solution to a new Problem
  you get a wee bit o’ Luck
Good Leadership, Training/Support and Communication are the Keys
Your ‘Inner Circle’ can prove very useful here
All within a robust PLAN
IMPORTANT
NOTE
Auto Slide : Please Wait
PLANNING &
MANAGING CHANGE
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
GRIT AND DETERMINATION
In this Module we are trying to show you a smoother, more effective way through the transition processes. But there will be times during many change initiatives when you hit problems, perhaps need to invoke remedial action - maybe even go back a step or two, to work hard to hold your team together when and if the going gets tough. If problems occur then its best to face up to them - to look for solutions. Involving your people will normally help, get them to help address the problems, help you find solutions that will work. If you are encountering conflict, serious conflict then we recommend you visit Slide 36 There will almost inevitably be times during change initiatives when your management/ leadership abilities are stretched towards, sometimes beyond, normal limits. These can be tough, challenging, often de-moralising at times. Your ‘Inner Circle’ (Slide 25) if you have formed one, can be very useful in times like this - for sympathy and understanding as well as support, for potential solutions as well as suggestions on what remedial actions you might take.
A REMINDER HERE : A good, robust Change Plan can help you through problem areas - one benefit of a structured, disciplined planned approach is that it will encourage you to review, to think ahead, to focus on results, to see through some of the problems - out to the other side.
Forewarned is fore-armed !

## Slide 26: Adding Value Through Team-working
INTEGRATING TASKS AND
INDIVIDUALS THROUGH TEAMS
TASK
TEAM
INDIVIDUAL
critical
areas
Team-working
can add real
value during
the transition
process
Auto Slide :
Please Wait
REPEATED SLIDE FROM
MODULE 1
TEAMS &
TEAM WORKING
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
INDIVIDUALS AND TEAMS
We have stressed that much in major change programmes depends on the responses of individuals. But even more can depend on the way individuals can be encouraged to work as teams. Team-working has been shown over the years to be of real benefit through change and transitional processes.
The Slide, based on original work by the Tavistock Institute, shows how the individual is encouraged to think about his/her own work, about the various tasks which are to be performed; also how people are encouraged through participation in teams to ‘share the load’, to support each other as they go through the transition.
Joseph and Jimmie Boyett in “The Guru Guide” say that teams are the foundation of “high-performing” organisations and, well organised, can make considerable contributions in the ‘improvement’ areas that can be so critical to successful change.
In well-formed, well-led teams ideas can be developed, discussed, developed, acted-upon. Often teams make good use of “brainstorming” principles - together they identify issues, define problems, seek solutions, solutions of which, when implemented, they can take collective ownership. Where staff/team-members take ownership of changes during transition process the changes will typically be more durable, have greater overall effect.
It can be well worthwhile managers encouraging the “team” approach, the inclusive approach, as they and their people move through the various stages of transition.

## Slide 27: Team Dynamics
PERFORMING !
‘norming’
‘storming’
‘forming’
The CLASSIC
four-stage
way in which teams
are formed and
develop……
1. team members
come together,
the team is formed
2.team “storms”
(addresses, tackles)
what it is they
have to do
brainstorming is
often used to seek solutions
3. typically a
Balance is
achieved and the team begins
to ‘normalise’,
to work
to its
strengths
4. eventually the
team begins to
perform,
achieve
its goals
and
objectives
AIM is to achieve
High-Performing Teams
Auto Slide :
Please Wait
TEAMS &
TEAM WORKING
Notes: KEY ASPECTS OF TEAMS AND TEAM-WORKING In this and the following Slide we capture key features of teams and team-working: FORMING TEAMS : In this Slide we show the classic model frequently used for forming and developing high-performing teams. Firstly the team is brought together having regard to the responsibilities and functions required of the team - this is known as “forming”. Efforts should be made to combine a good and appropriate range of skills and experience that will ensure harmony, efficiency, effectiveness - success! Often, but not always, a team has a Leader (who may be elected by the team members themselves, or appointed by others). It often also has a Mission Statement - a short but clear, concise written statement that says what the purpose of the team is, what its goals are - what the team must achieve and to what standards.When teams are first formed there is typically a brief, often intense period of “storming” – in this stage the team members discuss and debate (“brain-storm”) how best to carry out the work - who should do what etc. There then follows typically a period of “norming” - the team begin to establish procedures and working rules, they sort out systems and communicational matters - they start to get on with the work for which the team has been formed. Finally, well constituted, well motivated teams can move through to a final - longer - period where they begin performing - achieving that which they were formed to do, to good standards and timely delivery. Here are some of the key features of high performing teams :
* they develop a certain group belief, group approach, that sees team- members working for - rather than against - each other
* they typically achieve, frequently exceed, their Objectives.
* they develop high credibility, high levels of performance
* their achievements (“outputs”) often exceed the “sum of the parts”of the individuals

## Slide 28: Team Dynamics II
most of us seek harmony
but conflict is almost everywhere!
but not all conflict is unhealthy
some groups/organisations thrive on it
but it does need to be managed
conflict resolution is not the same as conflict management
remember Forming:Storming:Norming:Performing
Auto Slide :
Please Wait
TEAMS &
TEAM WORKING
Notes: SOME DYNAMICS OF TEAMS :
Individuals can often feel “lost” in the midst of change and transition processes. Teams help people to draw support for one-another, to develop “common purpose”. A majority of individuals are believed to seek harmony in team and work environments but that is NOT to say that there won’t be conflict within teams. In fact many reckon that a degree of conflict can be beneficial; some particularly high-performing teams are known to thrive on conflict - but we don’t recommend that you encourage this. Teams and team-working need to be managed – teams need to work within stipulated “frameworks”. Sometimes where real conflicts break out and cannot readily be resolved, the manager responsible for the team (not always the team leader) will need to intervene; to try and find a resolution for the conflict outside the full, formal team environment.
If you bear in mind the “Forming - Storming” model described in the previous Slide you may well find this useful when considering how to deal with conflict within your team(s). E.g expect - and encourage! - lively debate and discussion in the “storming” phases, this can be healthy. But if conflict carries into the “norming” and “performing” stages then you will need to manage it, manage it carefully.
We cover the whole aspect of managing conflict in Slide 36 but in the next Slide let us consider what management ‘guru’ Peter Senge has to say on the subject……

## Slide 29: Team Learning
“Avoiding the pitfalls of defensive communications, they “learn by practice” and achieve energy, power and insight.”
PETER SENGE
“The Fifth Discipline”
Auto Slide :
Please Wait
“The best teams are ones which
are able to use conflict
productively”
TEAMS &
TEAM WORKING
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
TEAM DEVELOPMENT & TEAM LEARNING
It is generally reckoned that the best performing teams use conflict productively - they use it to debate and challenge assumptions, they often use it to develop potential solutions to problems. Via these routes they can often reach consensus. But for this to be achieved, those responsible for teams need to encourage debate and discussion, to strive to create open and honest communication, to work towards a strong coalition of individuals, skills and attitudes.
Peter Senge’s seminal work “The Fifth Discipline” focuses on the issue of performing versus non-performing teams.
Senge explores the concept of ‘defensive routines’ which he says are strategies designed by individuals to avoid threat and embarrassment. These routines are “so diverse and commonplace” that they often go unnoticed, Senge says. However their effects can, he says, severely limit the potential of teams and their members. The remedy, Senge says is to face up to and talk through defensive tendencies within the team and, committing the team to learning, to practice positively the skills which will transform the mediocre team into a great one.
Senge places a lot of emphasis on “learning” in “The Fifth Discipline” and shows how through teams people can share learning experiences; good team-working can help people throw-off negativity; they can support each other, work to their strengths. Together the members of effective teams can frequently attain more than working as individuals. But as we have said teams do need to be managed, supported, motivated; effective teams rarely develop on their own!
In the next Slide we summarise the key characteristics of effective teams
[

## Slide 30: Characteristics of Effective Teams
well led
good skills/experience sets
clearly defined goals
clearly defined roles
shared values
mutually supportive
sound operating framework
high performing
recognised by others
effective leader
clear sense of direction and purpose
stretching objectives
participative, people are involved
often over-achieve
good at problem-solving
celebrate success
Auto Slide : Please Wait
TEAMS &
TEAM WORKING
Notes: CREATING EFFECTIVE TEAMS
To emphasise the potential contributions of teams working within change processes we have summarised some of the key features of effective teams. They need, generally, a leader- a good team-leader, someone who can uphold the need to achieve consensus, promote reasonable harmony, encourage the team members to work towards common goals and objectives. The very best teams not only share common goals but they often develop ‘shared values’, they are mutually supportive; typically they adopt positive approaches to problem-solving, they work together to develop solutions
Effective teams need a sound ‘operating framework’, they need some procedures and processes that ensure that they don’t “stray” from the purpose and activities for which they were created. If members of a team can be encouraged to adopt a clear sense of direction and purpose in an environment where people feel genuinely ‘involved’ then the likelihood is that teams will perform well. The best of them will probably “over-achieve” - they will achieve more than their bosses, their peers, even they themselves, expected.
One final thing - we’ve mentioned this before – teams should be encouraged to celebrate success; celebrating success helps cement relationships, maintain/improve morale; it can help the team move forward to their next challenges with increasing confidence.

## Slide 31: Managing Conflict
Types of conflict :
  “fights”
  “games”
  “debates”
  beware the ‘underground resistance’!
Levels of Conflict :
  high : medium : low
Other Factors :
  do those involved:
    share same goals?
    have equal or unequal status?
Three main methods of handling :
  negotiation
  mediation
  group arbitration
Auto Slide :
Please Wait
TEAMS &
TEAM WORKING
Notes: MANAGING CONFLICT
Whilst we advocate real efforts to achieve harmony and co-operation we also recognise that during change initiatives there is often an even higher potential for conflict to arise. Firstly at a basic human level, some people may violently disagree with the changes and express themselves to be so (Binnie and Williams refer to them as “honest opponents”); others (members of what Binnie and Williams refer to as the “underground resistance) may not express their disagreement but may actively be working against the change initiative. (Slide 11, “Change Types”). Each of these types can cause or create “conflict” and we have shown above some of the types of conflict you may encounter.
One attribute you can usefully develop is to be able to “stand back” from conflict - to first of all consider its impacts, whether they are likely to be high, medium or low in the context of the change initiative that is underway? If high then you will need to deal firmly and positively with the conflict. If it is between individuals or within teams you should first of all consider whether those involved actually share the same goals. If not you need to deal separately with the the people or groups involved, dealing particularly firmly with those who seem to be preventing or ‘blocking’ change. If the conflict is a team dispute then you may need to resort to some kind of arbitration process - to either win-over the dissenters, or if necessary, isolate them from the main group, manage them accordingly. With less deep-seated conflict then the art of negotiation can help; but if that fails then you may need to ‘escalate’ the problem to your line manager or specialist department for mediation. Conflict management is never easy and you may need to prepare yourself for this through additional reading, perhaps specialist training as part of your own preparation for managing change.

## Slide 32: Motivation
WHAT MOTIVATES PEOPLE ?:
  As Individuals ? As “Players in Teams” ?
    Money ? Status ?
    Interest/curiosity ?
    Belief ?
    Being involved ?
FIND THE GOLDEN KEYS :
  work hard to motivate the team
    shared objectives and goals
    shared resources
    shared achievement
    celebrate success
    get – and keep!- the team members involved
DEAL WITH CONFLICT AS AND HOW NECESSARY !
Auto Slide :
Please Wait
Managing & Motivating
People
Notes: MOTIVATING PEOPLE TO WORK THROUGH THE TRANSITION PROCESSES: Here we consider one of the major challenges in change management, of getting through the Turbulent Zone - how to motivate people - as individuals and as members of teams - to contribute, to get involved in the transition processes. We know that (Slide 10) people move towards (“adopt”) change at different speeds (‘innovators’ - approx 2.5% - move quickly and readily towards new things, new ways of doing things but the majority are far more reticent - many “sit on the fence”, take some convincing that change is necessary). So a key challenge for managers is how to motivate and encourage the “fence-sitters” to get involved, to make positive contributions to the transition processes. Generally, the sooner a majority can be “won-over” the better the chances of a successful transition. But what is it that motivates people towards adopting change ? Money is not usually a motivational option in times of change; but the re-assurance that people will still have jobs certainly can be! Even then the ‘fear’ factor can still loom quite large - will people have the same jobs, the same status? Will they work in the same location? Managers need to be cognisant of the fear, the anxiety which change invokes in many people; they will need to work hard to communicate and explain the reasons for change, to encourage people to become involved. This is where, as we have said, some of the benefits of team-working can come in. If people can be encouraged to work together towards the change objectives, to play to strengths, to share achievements as well as problems then often the route through the Turbulent Zone can be less arduous, more likely to succeed. Whilst many people see change as a threat there are, of course, people who see it as an opportunity. The ‘opportunists’ will welcome the changes and typically look within them for routes for personal advancement; they will be pro-active in seeking out opportunities; these people typically motivate themselves. Some of them can be useful supporters of change, become “change-agents”; they can help you to convert some of their more reticent colleagues, help get you and your team successfully through the transition process.

## Slide 33: Motivating Yourself and your People through Transition
people ask “WHY?” Change
- which often means “WIFM”
    “what’s in it for ME?”
they need to understand the reasons for change
there needs to be a route mapped out to get from “current reality” to “new vision”
managers/leaders need to get “buy-in”
“goals” and “shared values” help
“missionaries” and “disciples” are very important
keep focusing on the “early majority”
clear commitment & communication from the “top” help!
Auto Slide :
Please Wait
Managing & Motivating
People
Notes: MOTIVATIONAL MATTERS: In our change Models (Slides 10-12) we show how people frequently resist change - often preferring the ‘status quo’, however much they may have criticised it in the past, to the perceived fear, trauma, sometimes pain of going through major organisational change. Indeed as a manager or key employee you may well find yourself going through the same process - these groups are certainly not immune from the fear of change! It’s worth looking at what is called the “WIFM” (“What’s in it for Me ?”) factor. People can be motivated towards change. If you can show people, convince them, that change will be for the better - better for the organisation, better for its customers and consumers, better for them, then your job of getting them involved in the transition processes will be less difficult. The same applies to yourself of course - your boss may need to work quite hard in the early stage to convince you! In the midst of change and lack of certainty it is often difficult to show people how and why things will be better. So you need to manage yourself as well as your people through change; it is important to realise this, to make sure you get the necessary training, the necessary support from your boss. We have said that it helps to have a clear Plan, a clear programme for change so that, hopefully, you can see and understand your own role in the transition - and be able to explain to those people you are responsible for how it also impacts on and involves them. Managers need to encourage employees to ‘buy-in’ to the change and it helps if they can be committed and positive themselves, if they can encourage a “shared” approach to the changes. In the end the achievement of a workable ‘concordance’ or ‘coalition’ can be the thing that works for you. Elsewhere we have mentioned that typically the ‘innovators’ and the ‘early adopters’ (Slide 10) move quickly towards change and new opportunities; a key task for managers is to tap into their energy and enthusiasm, get them to help convince the ‘early majority’ - get the ‘early majority’ on board and as we’ve said you should be at least “half-way there”.

## Slide 34: PEOPLE : Parts to Play
gives people insight into the real problems
aligns people together against problems
provides a resource for solving problems
encourages personal opinion, interest - and inputs
people are implicated in the outcomes…….
= “Ownership”
Getting people involved and
keeping them motivated
are keys to success
A part to play in processes :
and in Outcomes !
Auto Slide :
Please Wait
Managing & Motivating
People
Notes: THE IMPORTANCE OF PEOPLE We emphasised in Module 1 - and make no apology for stressing it again here that people – and how they are managed - are vitally important if you are to get through the change programme, through the transition process, successfully. As people have such a key role to play in the whole process of change, managements increasingly recognise that getting people involved, keeping people involved, can prove very valuable throughout the whole change implementation process. Why ?
Typically the organisation’s people are closest to its customers (patients, consumers in the NHS) and can provide valuable inputs and insights; they can spot problems and, if well motivated, can often work together to find solutions. Compare that to the position if the work-force is not involved - people then typically watch in bewilderment as management try to push-through changes, changes which often are not geared and fashioned to the needs of the divisional and more local “market-places”. Organisations today find it is highly important to win-over their people if change is to be successfully achieved.
Encouraging employee involvement certainly needs firm and positive management but can often produce much better results.
If people are involved, if their fears and concerns about the impacts of change can be allayed, then they will typically take greater interest and involvement in the processes of change, eventually they take “ownership” of their parts in the transition processes.

## Slide 35: Three Challenges for Managers - the Opportunities in Change :
Binnie & Williams “Leaning into The Future”
The challenge for managers is to create the climate, the circumstances, the situations in which people can explore ‘current reality’.
People can discover a new reality in their organisation as a result of sharing their thoughts and feelings.
This discovery creates choices and energy which can be transformed into action.
Auto Slide :
Please Wait
Managing & Motivating
People
Notes: THE CHALLENGES – AND THE OPPORTUNITIES – OF CHANGE
Here we summarise earlier slides and, using snippets from “Leaning into the Future” by Binnie and Williams, we detail the key challenges and opportunities for managers involved in major change.
Firstly the challenge is, within the overall change initiative, to find ways to create the climate, the circumstances in which people can “explore current reality”. In other words they need to be encouraged to consider “where they are at now” and to think about where it is that the changes are required to “take them to”. An ‘inclusive’ approach, one that encourages people to get involved, to share and debate their thoughts and feelings can lead to a cohesive, team approach to implementing change - an environment where people support each other, where they achieve reasonable consensus, work together through the transition process.
Binnie and Williams say, based on their work and their research that where such ‘coalitions’ can be achieved then typically there is a drive and an energy that can be “transformed into action”. It is this energy, this drive, this momentum that managers need to work to generate within their people if progress through the Turbulent Zone is to be successful.

## Slide 36: Communication
Good two-way communication is one of the most important aspects of transition programmes.
Not too little, not too much !
The right amount of information to the right people at the right time.
KEY MESSAGE :
keep people :
- informed
- involved
“The neutral zone is a lonely place…….
People feel isolated, particularly if they don’t understand what is happening to them….
……it is important to re-build a sense of identification with the group and of connectedness with one another.”
WILLIAM BRIDGES, Managing Transitions
Auto Slide : Please Wait
GOOD COMMUNICATION
IS VITALLY IMPORTANT
DURING TRANSITION :
Communication
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
THE VITAL IMPORTANCE OF EFFECTIVE COMMUNICATION There is a wealth of research and mounting evidence that shows that organisations that master the art of effective communication as part of a package of measures during change programmes, enjoy a considerably higher chance of overall success. This said, good, effective communication is probably one of the hardest things to achieve! Bear in mind that people undergoing change, going through transition, typically experience reduced morale (Coping Cycle, Slide 12); often there is an increased work-load as people battle to ‘keep things going’ whilst grappling with the challenges of change at the same time. The Turbulent Zone tells us that transition is a place where old grievances and unresolved issues can surface, and frequently do.
Conscious of the need to communicate, many managers these days tend to over-communicate – they often swamp staff with too much information, tending to tell them what is going on rather than involving them - discussing it, using a variety of communicational methods.
One secret of success is to ensure communication is two-way, not just “top-down” (as it is, sadly, still is in many organisations). It has been shown that where people are encouraged to feed-back as part of overall communication there are better chances of success; people generally feel more involved. This approach signifies greater levels of trust and so a strong ongoing commitment to change form the top of the organisations remains important here. Another key to success is to get just the right information to the right people at the right time - not too little, not too much. Not all people need the same amounts or types of information. The “news” from the change front is that, even where sometimes the news is not particularly good, people do appreciate being kept informed about what is going on. The worst thing, many of them say, is NOT being told what is going on. Good news or bad they prefer to know. Where successes are achieved, milestones met, then the organisation’s communications system should ensure that people know about it, so that they can share in that success - even perhaps help celebrate it - which is an excellent way to help get employee “buy-in”, to encourage “concordance”, to get their “ownership” of - and involvement in - the “new ways of working” .

## Slide 37: Communicate the right things to the right people at the right time
Minimal Effort
Keep Satisfied
Keep Informed
Low POWER High
Low LEVEL OF INTEREST High
from Johnson & Scholes, Exploring Corporate Strategy ‘93
Auto Slide :
Please Wait
KEY MESSAGE :
Get the right information to the right people at the right time
Key Players
Keep involved
REPEATED SLIDE FROM
MODULE 1
Communication
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
“DIFFERENTIAL COMMUNICATION”
Clearly some information in and around change programmes needs to go to everybody who, in some way, is a “stakeholder” (i.e. ‘interested party’) in the change initiative. But, based around the main central themes of the change initiative, different groups of people require differing amounts/types of information. Sadly, as we have said, there is a tendency these days in some organisations to over communicate, to try and tell everybody everything - all this achieves generally is a dilution of impact, or that often people feel over-whelmed by the volumes of communication, give-up on it.
The above Four-Box Matrix is an approach that “segments” (groups) those who need to be communicated with, this particular version segmenting people with regard to their “power” (importance) in the organisation (vertical axis) and with their likely “level of interest” in what is going on (horizontal axis). Separate communicational programmes can then be developed and “rolled-out” to each “segment”. But overall, generic, communications (which need to reach all those involved) need to continue and the key messages within all communications need to synthesise, need to be driven by the core reasons for change. Adhering to this fundamental tenet, the secret is to get the right information to the right people at the right time.
Don’t overlook though what we have said about the communications process being two-way, allowing people the opportunity to “feed-back” - that way management should be better able to gauge (rather than guess) how things are going, how people feel. Frequently feed-back and contributions from the “front-line” can often help shape and tailor change programmes to take into account local conditions - help ensure that the change actually achieves its aims and objectives at the Consumer end!

## Slide 38: Methods & Types of Communication
TYPES AND STYLES :
formal
informal
one subject
many subjects
one-way, “closed”
two-way, “open”
to individuals
to teams/groups
long +detailed
short ‘n’ sweet
serious
warm ‘n’ friendly
COMMUNICATIONAL METHODS :
letters/memos
e-mails
bulletins, newsletters
team briefings
meetings
presentations
gee-up/motivational events
“funerals”
celebrations
it is important to plan the right frequency & mix of Communications…..
Auto Slide : Please Wait
Communication
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
USE THE COMMUNICATIONS “MIX”
Here is quite a long list of types of communication (left column) and methods of communication (right column). As we have said the key is to use the right “mix” of communications for particular groups or “segments” of employees (see the Matrix on the previous Slide).
Note that as well as formal communication - the overall approach and processes for this should be delineated in your Communication Plan - quite a lot of communications during transitional periods are informal e.g ‘quiet words’ with key people, brief informal gatherings to address particular issues or problems, and so on.
Colin Carnall in “Managing Change in Orgnisations” says that “most work cannot be done without informal communication” and explains that many studies show that managers of all kinds and levels prefer informal and verbal communication to documents; “they spend around 45% of their time communicating outside the formal authority structure”, he says. Minzberg, as far back as 1973, was writing that managers often build their “own networks of informal contacts” - our mention of “Inner Circles” is in fact one somewhat more formal approach to this networking concept.
We can only stress again that good, effective two-way communication can help bring about successful change. Communication is a very important component of the overall management of change.
In the next Slides we look at different approaches to effective communication, consider what might work best and where. Then we look at how to put together an effective Communication plan for your work area.

## Slide 39: A Good Communications Plan..
WHY?
WHAT?
WHO?
WHEN?
HOW?
WHERE?
A Plan
for
CONTENT
and
PROCESS
Auto Slide :
Please Wait
Construct a robust communications
Plan and remember :
PLAN : ACTION : REVIEW
COMMS
PLAN
Communication
Notes: THE IMPORTANCE OF PLANNING EFFECTIVE COMMUNICATION
If you’ve read the previous few Slides then you’ll know the importance that we attach to having a sound Communication Plan. And that whilst communication is vitally important you need to think carefully about what you communicate, to whom, how - and when. You also need to consider what “communications mix” is going to best for your change initiative - for your area, your people. Slide 44 gives you a comprehensive list of the methods and types of communication you can use. You won’t need all of them, just to choose those that will work best in your work environment, your particular organisational culture.
The main requirements are to be consistent and progressive, consistent in style, progressive in the sense that each communicational “piece” - be it an up-date in a meeting, a memo or e-mail - should add something to that which has gone before.
Hence our recommendation that you develop a Communications Plan for your change initiative - a plan that addresses the communication processes, a Plan that considers the style and type of content of the communications that you intend to use.
Let us also at this stage remind you that good communications processes are two-way - they are not simply “top-down” (from management), they should also provide for “bottom-up” communication - i.e feed-back from the people who are being ‘communicated with’ - the people who are implementing the change. The aim is to achieve a cohesive approach where people work together towards clear goals and objectives.

## Slide 40: Communication Check-List
PLAN your Communications
Get the right “mix” of methods, styles
Different rationale for different “groups”
….but keep key messages consistent
Not too Little : Not too Much
Formal v Informal communication
Two-Way communication
“Inner Circles”
Seek Inclusion, Acceptance, Adopting
Encourage :
  Innovation, Involvement, Internalisation
  Ownership
try to take the FEAR out of change
Auto Slide :
Please Wait
Communication
Notes: CHECK-LIST FOR EFFECTIVE COMMUNICATION
Firstly we recommend that you develop a communications Plan that determines how you will communicate, what you will communicate, who (which groups) you will communicate with. Its important to get the communications “mix” right. As we explained in Slide 43 you may wish to consider a different “mix” of communications for different groups of people - ensuring of course that even using this approach there is a consistency of messages. And of course your own communications need to “fit” with those that are being disseminated from those above e.g there may be organisation-wide Up-Dates and Newsletters; there may also be agreed “cascade” systems e.g Team Briefings that you will be asked to deliver, and manage the responses thereto.
We recommend that the communications processes are two-way i.e people “down-the-line” are encouraged to respond and feed-back, so that they are involved in the change processes. By doing this you promote a more “inclusive” approach – encourage your people to be involved, show that you feel that they too have roles to play. Using this approach you may well help to take some of the fear out of change. Thus you can encourage your people to discard things from the past – the ‘old’ way of doing things – and to start adopting the ‘new’ ways of doing things. Using this approach change management evidence suggests that you will generally improve your chances of successful implementation of change..

## Slide 41: Practical
1. Develop a Communication Plan
for your work area
What will be the main “themes” of your communication ?
What will be the main communicational
processes and methods you will use ?
Are there different groups that will require different
Communicational processes and styles /content ?
Don’t forget to build in regular Reviews of your plan !
Do you feel you need an ‘Inner Circle’ ?
if so – who might you ask to be in it ?
use
left-mouse
or
right arrow
to
progress
Communication
Notes: NOTES FOR YOUR COMMUNICATION PLAN

## Slide 42: Handling Problems : Finding Solutions
Keep your Team involved
Use your ‘Inner Circle’ whenever you need
Deal with problems as they crop up
  openly where possible to seek “buy-in”
Encourage SOLUTIONS , not Problems
Deal with real Conflicts (and Terrorists!) “off-line” (one-to-one/more communication)
Use Delegation, Teamwork and Negotiation wherever appropriate
Brainstorming can often Help!
Auto Slide : Please Wait
Problem-Solving
Notes: PROBLEMS & SOLUTIONS
Before we close this Module with a Summary Slide let us take a more detailed look at Problem-solving; there’s normally plenty of scope in most change initiatives for this!
Let’s start by re-iterating the potential real value of team-working in Change situations; well constructed teams that have consensus and are encouraged to have open and honest communication can often identify and discuss issues, often come up with local solutions – local solutions that could well ensure acceptance in the local context. In other words involving people, either individually or as members of teams can help tailor change implementation so that it works locally.
A key factor is to recognise that, however well you plan things, there will almost inevitably be problems – remember a feature of change initiatives is that they are invariably ‘messy’ - and that what you want from you dialogues with your people are solutions to problems – not more problems! The development of a “brainstorming” approach can help here – this can often help you grind out solutions in a team environment that will work. Also look to deploying responsible delegation – assign key tasks to competent people, ensure they know what is required of them.
For you the manager of change we have said that it can be useful - some say very useful - to establish your own “Inner Circle” - a network of people outside your own immediate domain with whom you can comfortably communicate, especially useful for “someone to talk to” when things get tough (as they often do in major change initiatives). This may well help you to consider solutions to particular problems, help you to deal with issues and problems as quickly and efficiently as possible. If you encounter real conflict or “terrorists” or “members of the underground resistance” the best advice we can give is to try and deal with these “off-line” i.e outside the team environment. You may well need to hone your negotiating skills to help you handle some of the trickier situations you may encounter.

## Slide 43: SUMMARY SLIDE : Module 2
PLANNING change
  the NHS Plan
  the Four-Step Planning Framework
  Customer (Patient/Consumer) Focus
MODELS & TOOLS for change
CHANGE and TRANSITION
  the Five-Stage Transition Process
  Changes in Clinical Practice
The importance of PEOPLE
  The Psychology of Change; Change Types
  Motivation & Involvement
IMPLEMENTING and MANAGING Change
  Motivation
  Team-work
  Inner Circle
COMMUNICATION during Change/Transition
PLAN : ACTION : REVIEW
“Turbulent Zone”
PLAN for
CHANGE
inner
circle
PLAN
Auto Slide :
Please Wait
SUMMARY
Notes: SUMMARY OF MODULE 2 In this Module we have used Bridges’ concept of “transition” to consider the challenges of getting through what we call the “turbulent zone” – the period of time that spans the end of the ‘old’ way of doing things and the beginning of the ‘new’ way. We have emphasised particularly the importance of planning change initiatives because time invested in quality planning can pay handsome dividends during the transition process itself. We have described a number of Models and Techniques that can assist the planning process; these, and others, are contained in the Change Tool-Kit that can be accessed from this Knowledge Platform. In terms of implementing change programmes we have used our Five-Step Transition model to take us through from essential planning activity to the “launch” of the programme and then shown how to use the Change Plan to ensure that momentum is maintained as we work our way through the ‘turbulent zone’, to help us maintain morale through the most difficult parts of the transition process. To this end we have shown how involvement of an organisation’s people can help drive changes through, also to help ensure that the changes are tailored to suit differing local conditions. To emphasise the overall value of good change planning we have showed how - using the 4-Step Planning Process - a robust, practical Plan for Change can be developed. Alongside this we have re-inforced our strong belief that it is an organisations’ people – and the way they are managed – who can help make the difference between successful and unsuccessful change.
We have recommended also that managers consider developing their own ‘Inner Circle’ - a fairly informal support network that can be used for help and support as they work to manage their teams through the transition period and processes. We explained how it is particularly important to consider how people re-act to change and to structure the Change plan to take these factors into account. We have also stressed the vital importance of effective communication to support the change/transition processes. Overall we have considered how managers can motivate their staff towards positive implementation of change and have stressed the real benefits that team-work can bring to assist the transitional processes.

## Slide 44: Research Sources
AN INTRODUCTION TO MANAGING CHANGE
The following books and Publications have been used in the collation of this Learning Module:
MANGING CHANGE IN ORGANIZATIONS, Colin Carnall, Prentice Hall International, 1995 ISBN: 0-13-150954-3 ; THE MANAGING CHANGE POCKET BOOK, Neil Russell Jones, Management PocketBooks, ISBN: 1 870471 31 8; MANAGING TRANSITIONS, William Bridges, Nicholas Brealey Publishing. ISBN : 1-85788-112-5; TURBULENT CHANGE, Every Working Person’s Survival Guide, Peter R Garber, Davies-Black Publishing ISBN : 0-89106-135-5; THE GURU GUIDE, Boyett & Boyett, 1998, Wiley ISBN 0 471 18242 7 “Managing Organizations” WILSON & ROSENFELD, 1990 MANAGING CHANGE IN THE NHS :
1. ORGANISATIONAL CHANGE A Review for Health Care Managers, Professionals and Researchers, Valerie Iles and Kim Sutherland; 2. MAKING INFORMED DECISIONS ON CHANGE, NCCSDO, London School of Hygiene and Tropical Health, TEL: +44 (0) 20 7612 7980; :
KEY WORDS: Change, Transition, Psychology of Change, Attitudes to Change, Step Change, Incremental Change, Organisational Culture, Planning Change, Implementing Change, Managing Change, Change in the NHS, Managing People, Involving People
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/

## Slide 45: “Managing Change in the NHS”
“Making Informed Decisions on Change”
a VERY useful, practical little booklet that summarises the volume mentioned above and gives LOTS of examples
“Organisational Change”
a very detailed assessment of practically all tools and models
that can be used in Change Management – very comprehensive
NATIONAL CO-ORDINATING CENTRE FOR NHS SERVICE DELIVERY AND ORGANISATION
available free to NHS staff via :
www.sdo.lshtm.ac.uk
There are TWO excellent books about Managing Change in the NHS :
Notes: MANAGING CHANGE IN THE NHS : Support Booklets
These booklets are excellent, covering the management of change and its implications in the National Health Service. They were published only in June 2001 and together provide an excellent resource. The first book carries detailed assessments of virtually all models for change that are currently being applied in the NHS, and it attempts to assess their application and usefulness. The second is an altogether smaller, lighter booklet which contains the essence of what its “big brother” has to say but also provides lots of practical examples. Both the book and booklet are available free of charge to NHS employees and can be ordered via the web-site shown
www.sdo.lshtm.ac.uk

## Slide 46: APPENDICES
Here we have included material about
Tools and Techniques
used in Module 1

## Slide 47: Types/levels of Change
STEP
INCREMENTAL
STEP
INCREMENTAL
CONTINUOUS CHANGE
time
Rate
of
Change
Fund
Holding
PCGs
PCTs
?
Use Left Mouse
or Right Arrow
to progress
lets plot
some
NHS “landmarks”
TWO main types of change……
Most organisations undergo continuous
change (i.e mixed step/incremental) these days
CHANGE
MODELS
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
THE TYPES AND LEVELS OF CHANGE
These days almost all organisations undergo almost continuous processes of change but it is important to recognise the different kinds and levels of change that take place within an organisational context: STEP CHANGE is a major change, or programme of change, that occurs within a relatively short period of time – from 2/3 months to perhaps 5 years. It requires major efforts and organisation to effect and accommodate this kind of change. It is often done to combat increased competition or to mitigate spiralling costs or to change to accommodate huge new systems or technology. Examples of Step change would be major premises rationalisation, major stakeholder (e.g. government) intervention. INCREMENTAL change is an altogether steadier rate of change, although it can still prove difficult and challenging to manage. Many organisations these days undergo almost unending incremental change – many of these incremental changes interspersed by periods of “Step” change. Examples of Incremental changes would be programmes to introduce performance-related pay or to gradually reduce work-force numbers via voluntary redundancy and/or early retirement initiatives. It is important to recognise that Step and Incremental change are not mutually exclusive. Programmes of Incremental change will typically not stop just because a period of Step change is planned or anticipated. In fact more and more organisations these days are committed to programmes of what is called “Continuous Improvement” – ongoing programmes of phased change that help organisations keep up-to-date, remain efficient, productive – in commercial firms – competitive. In all these types and variations of Change there will be impacts on the organisation’s people – its executives, its managers, its supervisory staff, its “shop-floor” or “front-line” staff. Organisations ignore the fears and needs of their work-forces at their peril.
The illustrative example above shows the change processes that have occurred - and are continuing to occur - in the National Health Service since the early 1990s.

## Slide 48: Adopting Change
Everett Rogers : Diffusion of Take-Up of Innovations
Uptake of
Innovation
2.5%
(actively seek/embrace change)
Innovators
13.5%
(keen to take up ‘good ideas’
– become “disciples”)
Early adopters
16%
(“dinosaurs”)
Laggards
34%
(“sit on the fence”)
Early
Majority
CHANGE
MODELS
34%
Late
Majority
(generally
disinterested)
Time
Use Left Mouse
or Right Arrow
to progress
Rogers carried out research into how quickly people take
up “innovations” – new ways of doing things. (see notes)
Understand the impacts
of this research and you’ll
see how people adopt change
at very different rates/paces.
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
HOW PEOPLE RESPOND TO AND TAKE-UP CHANGE
Everett Rogers developed his “Diffusion” model out of research he conducted into the rate at which people adopt or take-up new “innovations”. The categories and proportions of normal populations he identified from his research are, we feel, very enlightening when considering how people generally move towards, take up, change.
Only 2.5 % typically rush towards new innovations, new ways of working - most prefer to sit on the fence, watch what happens - whilst some are openly critical, can’t, perhaps won’t, see the need etc. Typically there is a larger number (about 13.5%) who take-up innovations some time after the “Innovators” have adopted them. This category Rogers calls “early adopters” - part of the first sizeable “wave” of people who take up change, innovation - many of them becoming committed disciples of the change or innovation in question in due course. Next come what Rogers calls the “early majority” - typically they have ‘watched and waited’ before either seeing the benefits and/or getting the confidence to take-up the changes themselves. The ‘early majority’ are significant because they represent typically 34% of the particular population. (Significantly, add the 2.5% Innovators, 13.5% Early Adopters and the 34% Early Majority and you’ll note that they together represent 50% of the total number of people – get this far and you should be “well on the way” to attaining the changes you are implementing.)
According to Rogers’ research a further 34%, known as the “late majority” follow in due course - they are less change-orientated, slower to respond, need more convincing. But if the change initiative can be kept going then typically the late majority do eventually come “on board”.
Which still leaves about 13% so-called “laggards” who really don’t show an interest, don’t really want to “get involved”. Some of them never do - they leave, or they become “terrorists” (see Next Slide). Others succumb in due course, either through peer pressure or because they finally “see the light”.

## Slide 49: Attitudes to Change
CHANGE “TYPES” Binney G & Williams C, “Leaning into The Future”
MISSIONARIES : BELIEVERS : “LIP SERVERS”
HIDERS/REFUGEES : THE UNDERGOUND RESISTANCE
HONEST OPPONENTS : EMIGRANTS
CHANGE
MODELS
Missionaries
Believers
People who
pay lip service
Hiders and
refugees
Members of
the underground
resistance
Honest
Opponents
Emigrants
Binnie and Williams conducted research in the 1990s
and defined various “Types” in relation to Change
see Notes below
Use Left Mouse
or Right Arrow
to progress
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
CLASSIC “CHANGE TYPES”
The types identified in this useful Model were developed by Binnie and Williams back in the early 1990s. The categories were determined from research the authors did into change and the management of it within organisations. (There are some linkages here to Rogers’ “diffusion” model, explained in the previous Slide) Missionaries are proud and pleased to embrace change – they adopt it, adapt to it quite quickly and actively encourage others to do so too. Believers are just that - they see the merits of the changes, believe in them - but are a little more cautious, less extrovert perhaps than Missionaries - and are frequently convinced by a mixture of repetition of the reasons for and benefits of the changes and through the influence of the Missionaries. Next come a much larger group “people who pay lip service” - they nod and acknowledge that change is probably necessary but are typically not active in supporting or adopting it. They might well be called “fence sitters”! The next category, and there are typically plenty of these too, are “Hiders and Refugees” - they ignore or try to hide from the change - often through fear (fear of the unknown) or because they are genuinely disinterested in it - perhaps typically preferring the “status quo” (old or existing order) to the “new ways of working”. Whilst “hiders and refugees” are rarely troublesome, the remaining categories can be - especially to those trying to drive/steer through change. The first group Binnie and Williams call “Members of the Underground Resistance” - they are actively and probably fairly quietly (perhaps subversively) trying to “block the changes” and can be dangerous. Whereas “Honest Opponents” declare their resistance - they openly challenge the need for change, question the benefits. “Honest opponents” typically identify themselves - by words and actions - as being against the changes. (If change leaders/managers can convince an “honest opponent” that the changes are acceptable then many others, often many of the “hiders and refugees” will sit up and take notice, perhaps be convinced themselves about the need to change.) The last category - “Emigrants” simply leave, wanting nothing to do with the changes, preferring to seek their employment elsewhere!

## Slide 50: The Psychology of Change
These are the
five Stages work-forces
typically go through
During Change initiatives
adapted from “The Coping Cycle” **
Stage 2
Defence
(**Managing Change
in Organizations, Carnall C,
T J Press (Padstow) Ltd, ISBN 0 13 150954 3 p 144)
Performance
Self-Esteem
change
Turbulent
Zone
CHANGE
MODELS
See Notes
below for Details
Use Left Mouse
or Right Arrow
to progress
Stage 1
Denial
Stage 5
“Internalisation”
Discarding
Stage 3
Adaptation
Stage 4
Time
Notes: Copyright Martyn Laycock - the knowledge college - ALL RIGHTS RESERVED
http://www.phel.nice.org.uk/healthknowledge/
THE PSYCHOLOGY OF CHANGE : the “Coping Cycle” This Model developed by Colin Carnall looks at the underlying psychology of change, its impact on people; it identifies a number of key stages that people go through when organisational changes is “in the air”. Stage 1 typically brings “denial” - apart from a few ‘Missionaries’ most people don’t see the reason for or benefits of change, preferring at this stage to cling to the ‘old order’. Why? Largely because they fear change - they fear the unknown, perhaps fearing that they might lose their jobs or lose status, or have to change locations, learn new skills etc. “Self esteem” (blue line) holds up well in the First Stage and, perversely, performance (red line) often improves for a while - people work hard to show management that the “old” ways are OK - that they do actually “work”. In Stage 2 - “defence” - many people spend time and energy defending the old way - some of the early adopters have “adopted” - moved towards the change - but the majority typically remain unconvinced. During this Stage both self-esteem and performance go down. Typically we are now headed into the “turbulent zone”. In the next stage, Stage 3, more people begin “discarding”- starting, with encouragement from the change leaders, the ‘Missionaries’ and some of the ‘Early Adopters’, to “let go” of the past. But self-esteem and performance continue typically to go down during this Stage. This may well not be a “happy time”. For by now we are well into the “turbulent zone” where it has to be said many badly planned and/or poorly implemented change initiatives flounder. Stage 4 (adaptation) is also in the “turbulent zone” but in this stage people are not only letting go of the past, the old order, but are increasingly starting to move towards, take-up the new ways. The ‘Underground Resistance’ won’t be, nor will many of the ‘Honest Opponents’ (see previous Slide) - yet! But during this Stage morale and self-esteem do generally start to pick up, as does overall organisational performance. By this stage the changes are starting to work - to take hold. Stage 5, (Carnall calls it “Internalisation”) is where the changes really start to take effect; typically more and more people, probably many of the ‘late majority’, are now supporting, or starting to support, it. In well planned, well managed change initiatives the organisation and its people come out of the “turbulent zone” into the New Beginning - where typically morale and performance continue to improve.