## Slide 1: Programme & Project Management INTERMEDIATE MODULE
a module specially designed for
HealthKnowledge
WRITTEN & DEVELOPED BY
MARTYN LAYCOCK MBA MCIM ACIB
e-learning
version
Additional information
is provided in the ‘Notes’
sections
below each slide
NOTE
Many Slides in this
Presentation
load automatically.
Each such
Slide is marked, as this one,
“Auto Slide
Please Wait”
use
left-mouse
or
right arrow
to
move-forward
AUTO SLIDE
Please Wait
You can download and then print-off this PowerPoint presentation
(Use ‘Notes’ version to print full presentation with notes or
‘Handout’ version to print Slides only)
Notes: Welcome To The Intermediate Level Module On Programme & Project Management
This intermediate module is designed to build upon and develop our introductory module. It has been specially designed to help you explore the practicalities of the ‘programme and project management approach’ and to show how useful programme and project management can be in the work environment. If you are new to project management we suggest you first visit the introductory module. If you are reasonably experienced in working jn projects then you may well choose to use just this Intermediate version (which purposely includes a number of the ‘fundamentals’ Slides from the Introductory module, these (Slides 2-10) are clearly marked “Review” slide). Many slides are self-loading and are marked accordingly (“Auto Slide : Please Wait”). Progress through the slides, and the presentation itself, can be accelerated by using either the left-mouse or right-arrow keys on your keyboard. To complement this module, there is a downloadable Project Management Tool-kit.
IMPORTANT NOTE: Programme and Project Management can be as simple or as sophisticated as you or your organisation want it to be. But there are some core elements that you will need to understand and know how to use. It is our aim to show you, using our ‘FeelGood’ scenarios, how to use a number of key programme and project management tools and techniques, apply them to practical work-related situations.
The component parts of Programme & Project Management are largely sensible, logical approaches to planning, implementing and managing work; they have been brought together over the years to form a structured, disciplined approach to managing goal-specific and time-finite activities. Projects may be large (e.g build a sports stadium, or a new power station) or small (e.g. arrange a move to new offices or install a new departmental computer system). Programmes are linked series of projects that contribute to overall larger ‘pieces of work’ (see below).
The Programme & Project Management approach is designed to achieve greater focus on why particular “pieces” of work are carried out - and to introduce a more planned approach to how the work is then scheduled and implemented. Programme and Project Management is driven primarily by results - or rather by goals, the attainment of goals. It is especially useful where specific “pieces of work” are organised to achieve particular goals.
What is the difference between Programmes and Projects?
For many years we spoke only of Project Management as a subject, as a discipline; it was largely about using particular approaches to handle one-off ‘pieces of work’. More recently as project management has grown in popularity and use, we began to use the word Programmes to describe series of projects that link together to become “themed” programmes. For example building a road bridge or a rail tunnel would be a project (large, complex project) but building the bridge/tunnel may well not be a ‘stand-alone’ or ‘one-off’ but part of a larger ‘regeneration’ or ‘transport development’ programme, i.e with its own approach roads etc as part of an overall transport infrastructure programme. Basically a ‘programme’ is a series or group of related ‘projects’ that are managed together as a ‘portfolio’. In our Introductory module we gave examples of programmes and projects - which included the renowned first Apollo Moon Landing : most people will either know or recall that man’s first landing on the moon by Neil Armstrong and Buzz Aldrin was a particular project (Apollo 11) or mission that formed part of a major space and lunar exploration programme, the Apollo programme. “A Programme is a collection of projects and other items of work that are managed together as a portfolio” Department for Education & Skills ‘PPM’ website : http://www.dfes.gov.uk/ppm/
More recently (2000) in the UK, the well-known Millennium Dome and also the adjacent North Greenwich London Underground Station were both major ‘projects’ that formed part of a major regeneration ‘programme’ for the ‘Greenwich Peninsula’ in south-east London. The new North Greenwich station itself formed part of a major London Underground extension ‘programme’ (“The Jubilee Line Extension).
Welcome to the intermediate module on project management
This intermediate module on project management is designed to build upon and develop our Introductory module. It has been specially designed to help you explore the practicalities of the ‘project management approach’ and to show how useful project management can be in the work environment.To complement this module, there is a downloadable Project Management Tool-kit. If you are new to project management we suggest you first visit the introductory module
Important note: Project management can be as simple or as sophisticated as you or your organisation want it to be. But there are some core elements that you will need to understand and know how to use. It is the aim of this intermediate learning module to re-visit some of the fundamentals of project management and to show you how, using our ‘FeelGood 2’ scenario, to use them, how to apply them to practical work-related situations.
In the final slide we have shown the main sources we have used to prepare this module; most of these are books, available from most good booksellers and business libraries; note though that a couple are ‘on-line’ and that one (Xebec) can be delivered, ‘on-line’ via the internet or company intranet or ‘off-line’ via Inter-Active CD-ROM. Video arts also can supply a video or CD-Rom that links to the ‘Guide to Project Management’ booklet.
The component parts of Project Management are largely sensible, logical approaches to planning, implementing and managing work; they have been put together over the years to form a structured, disciplined approach to managing goal-specific and time-finite activities. The project management approach is designed to achieve greater focus on why particular pieces of work are carried out - and to introduce a more planned approach to how the work is scheduled and implemented. In this module we will use a simple, practical real-life scenario (the ‘FeelGood 2’ project) to work through the key steps of project management.
Project management is driven primarily by results – or rather by goals, the attainment of goals. It is especially useful where specific ‘pieces of work’ are organised to achieve particular goals and objectives.
This module is based on our highly practical project management workshops which use an excellent project management guide – Project Management: The Essential Guide to Thinking and Working Smarter. References to key parts of this practical support booklet are provided throughout this module.
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 2: Programme & Project Management is….
MANAGEMENT
RESOURCES
‘planning, gathering and managing the resources needed to achieve particular goals and objectives within defined time and budgetary constraints’
QUALITY
TIME
COST
REVIEW
AUTO SLIDE
Please Wait
use
left-mouse
or
right arrow
to
move-forward
Notes: The History And Key Elements Of Project Management:
Project management as a modern management discipline is now nicely over 50 years old, its beginnings being generally considered to be the Atlas Project in the United States which began in 1953.
But it is only in the last ten years or so that the component parts of project management have become fully structured and formalised, in part driven by the capabilities of modern technologies – the development of dynamic systems such as PRINCE and software packages like Microsoft Project 2000.
There are two principal project management methodologies – the critical path method (CPM) and the cost specification method (C/SPEC). In our modules we follow, as do the majority of project management systems and software packages, the critical path method.
Its worth here at the outset taking an initial look at the key elements that together comprise project management:
Looking first at the points of the triangle (above), financial cost is a key element, as is time. We talk a lot about projects being delivered ‘on time and within budget’. But there is also a quality dimension - the quality to which a project is to be delivered will impact on both the cost and the time taken to complete, e.g. a bridge or a new building needs to be built to certain safety and quality specifications; these of course will impact on the cost of the project; similarly quality parameters of building the foundations and the structure may well impact upon the time required to complete a project.
Other key elements of cost are of course the resources that are needed to deliver a project: the people, the equipment, the materials, possibly also property (e.g. the office space where the project is to be run from, where the project team are to be based).
Beyond this the project’s management will be of critical importance – the project manager and his/her team will need to manage the project to given quality standards, to ensure that the project is delivered on time as well as within budget – and to the specified quality standards.

## Slide 3: a ‘Project’…...
is a unique ‘venture’ or ‘piece of work’
is set up to achieve a particular objective or goal
  has defined outcomes
    qualitative as well as quantitative
is typically carried out for a ‘client’
is time limited - has a beginning and an end
uses defined resources :
  people
  money
  equipment
typically has a single point/person of responsibility
uses teams and team-work
the goals are defined and the project is finite
REVIEW
AUTO SLIDE
Please Wait
use
left-mouse
or
right arrow
to
move-forward
Notes: What is a Project ? The above characteristics of projects are taken from a variety of definitions but to summarise we give the Open University Project Management book’s hybrid definition:
“A project is an organised piece of work towards a pre-defined goal or objective that requires resources and effort, a unique venture having its own budget and time-scale (schedule). A project’s success can be measured in terms of how closely it comes to achieving its goal/objectives (including the qualitative as well as quantitative aspects), within the parameters of its budget and schedule. Once a project is ‘closed-out’ (completed), it ceases.”
Thus you will realise that projects are finite – but, that said, they can last from a few weeks (sometimes just a few hours!) to several (sometimes many) years.
Examples: Specific pieces of work that would benefit from the project management approach:
design and develop an integrated database for the Public Health department of a Strategic Health Authority or PCT
develop a web-based knowledge-platform to support staff learning and development
Organise a major office move to accommodate existing and new staff in an improved, more efficient, more effective working environment
Note: whilst projects are finite (time limited) their products (deliverables) and the benefits thereof frequently live on – i.e. the end users continue to benefit from the knowledge and experience that the project provides – thus users of this knowledge platform will, we hope, retain and use some (perhaps even all) of the knowledge they gain about programme and project management.
Note re “Pilot” Projects : today we often see organisations run ‘pilot’ projects; they run these to find out if and how something works; then from the experience they gain in the ‘pilot’ they will often develop further ‘follow-on’ projects and larger programmes of linked projects i.e. they use the outcomes and experience they gain in the ‘pilot’ project to inform and develop further projects or larger programmes of activity.
Field M, Keller L.Project Management. Milton Keynes: Open University, 1998.

## Slide 4: Key Features of Programme & Project Management
very strong focus on results (outcomes,goals)
positive and effective time management
positive and effective management of resources
  people
  equipment
  property
  MONEY!
strict scheduling + the use of milestones
good budgeting
frequently uses team-work
REVIEW
AUTO SLIDE
Please Wait
“A Programme is a collection of projects
and other items of work that are managed
together as a portfolio”
Notes: Key features of Programme and Project Management:
In this slide we have summarised some of the key features and characteristics that apply to virtually all projects, large or small:
Typically they are, as we have said, goal-driven and finite (time-limited)
They require sound, positive, ‘hands-on’ management –
• management of people, time, money, property and/or equipment
Budgeting is an essential requirement
Scheduling of tasks and activities is a key requirement
Milestones are used to mark key points within the project and are an important part of the review/progress-checking procedures
Finally, teams and team-work are frequently features of good project management, people – often bought together to complete a specific project or programme, work together to pool their skills, abilities and experience to ensure that the project is delivered within budget, on time, and to the required quality standards.
We looked in our Introductory module in some detail at the typical key players in projects and/or programmes; we used the term ‘stakeholder’ to include anyone who has an involvement, or interest, in a particular project or programme.
In the next slide we take a look at some of the people issues that are so important to successful programme and project management; in particular we focus on team-working – which is a typically common feature in the design and delivery of modern-day programmes and projects.

## Slide 5: The Project Life Cycle
CLOSE
-OUT
EXECUTE
ORGANISE
PLAN
DEFINE
FEASABILITY
PHASE
sometimes
called scoping
risk is assessed
feasibility tested
“GO” or “NO GO”
decision made.
If “GO” 
PLANNING
PHASE
tasks
sequencing
milestones
estimating
budgeting
PROJECT
PLAN
ORGANISING
PHASE
resources
tools
reviews
reporting
communications
IMPLEM-
ENTATION
PHASE
activities
monitoring:
costs
progress
controlling
quality
COMPLETION
PHASE
client “hand-over (= acceptance)
complete documentation.
review: sign off
post implementation audit
maintenance
“value assessment”
R
E
V
I
E
W
1.
2.
4.
3.
5.
S
T
A
R
T
I
U
P
{Implementation Phase}
REVIEW
AUTO SLIDE
Please Wait
Notes: The Project Life Cycle:
We use this model because a thorough understanding of how projects normally evolve and develop – an ‘holistic’ view - can be invaluable both to programme/project managers and those in project teams. Here we show the ‘cycle’ in linear fashion, with a clear start (start-up) and end (review). Phase 1: Definition: This phase covers ‘scoping’ (clearly identifying what you want to achieve, by when and within what constraints) and, often, a feasibility study (including a risk assessment and cost benefit analysis) to establish whether the project should go ahead or not. (Hobbs pp 24-27)
Phase 2: Planning: The importance of this phase cannot be overstated; good work done here will help ensure that the project runs well and that the goals and objectives are achieved. The planning phase develops some of the scoping aspects in phase 1; it plots, particularly, the timing and cost requirements. The resourcing of the project, the costs, the tasks and activities and their sequencing are all included in the overall project plan that is the major output from this phase. The project plan is used to steer and manage the project through the remaining phases.
Phase 3: Organising: Here the project manager marshals and organises all the various resources that will be required to carry out the project. This is still largely a process of organising rather than acting - a bit like packing and getting all your documents (tickets, passports, currency etc) ready and together before you set out for your annual holiday. Note: Phases 3 and 4 are often grouped together and called the implementation phase.
PHASE 4: Execution phase: This really is the ‘active’ phase; it is the process of implementation that follows a lot of planning and organising that has already taken place. In this phase the project team work through the various project activities in accordance with the project schedules and budgets contained within the project plan.
PHASE 5: Close-out: There are a number of activities that typically take place in this phase. All the activities are completed so as to enable delivery of the project to the client. The hand-over process involves delivering the project goals and objectives to the client - and, in many cases, also to the end-users. Typically there is a final review that establishes how well the project has run, looks at what has gone well and what has not. Today these are called ‘after-action reviews’ and include a section headed ‘lessons learned’ i.e. capture the key learning points from the project as part of an ongoing project management ‘knowledge management’ system.
NOTE: An alternative Project Life Cycle is presented by Vivien Martin in her 2002 book “Managing Projects in Health and Social Care” ; this is shown in Appendix 1 of this module (see Slide 47).
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 6: Time and Precedences
‘Estimating the time required for tasks can be one of the most difficult parts of planning a project’ (Hobbs Pg 42)
TASK TIME v LAPSED TIME
e.g *Time needed for PR agent to write publicity piece: 16 hrs (= 2 days)
* Time taken to submit publicity piece (10 days)
Precedence diagrams are particularly useful because they show the links and relationships between tasks across the whole project and therefore aid the estimation of total time that a project will take to complete. In particular precedence diagrams show tasks that are critical i.e those that must be completed before other linked work can proceed..
‘It is very important to work out the ‘dependencies’ between tasks:
a precedence diagram will help here.’ ( Hobbs Pg 43)
Precedence diagrams help project managers to spot potential ‘blockages’ and ‘bottle necks’ and to pay attention to them at the planning stage
REVIEW
Sample time-precedence chart next screen
AUTO SLIDE
Please Wait
Notes: Estimating Time In Projects : Unless similar projects have been undertaken previously - and experience from those projects therefore used to inform time estimation etc - calculating time for tasks in programmes and projects can be quite challenging. This is because many projects take place in ‘unfamiliar territory’.
For this reason it is advisable to break down larger tasks into smaller, more manageable elements.
Also, it is very important not to confuse task time with lapsed time: serious time over-runs can ensue if these distinctions are not made, as, in the example shown above, what appears to be a 2 day job (the agent gets paid for 2 days work) actually takes 10 days in practical terms before it gets delivered. There is a useful formula for estimating time given in Hobbs’ Project Management guide (Pg 42).
Dependencies Another important factor to understand and plan for is the aspect of dependency – how and where certain tasks are dependent upon others being completed. For example, until the publicity piece mentioned above is actually received it cannot be distributed to relevant publications and editors. Most publications have strict deadlines for the receipt of material for particular issues. If these deadlines are missed then the publication of project-relevant publicity material may be delayed for a month, or even longer.
Network logic or precedence diagrams are visual aids which help project managers log all tasks and their dependencies; such diagrams, often part of PERT diagrams, help project managers see where time is likely to be lost and therefore where estimated project delivery times may become extended. An example of a precedence diagram developed in module 1 is featured on the next slide (Time Precedence chart). See also page 43 of the Hobbs Project Management Guide.
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 7: TIME-PRECEDENCE CHART FROM MODULE 1
sanction of
budget to
cover costs
of contractor
workshop
locations &
materials
by
25/5
recruitment of
competent contractor
to develop/deliver
Bespoke Workshops
by
31/5
recruitment
of min 35
delegates
of which
min 20 for July
flyers out
by 03/6
35 bookings
by 30/6
book two quality
delivery locations
and book facilitator
for these dates
by
01/6
DELIVERY OF
2 WORKSHOPS
TO
SATISFACTORY
QUALITY &
DELEGATE
FEED-BACK
LEVELS
First on
25th July
Second on
22nd Sept
R
E
P
O
R
T
&
C
L
O
S
E
O
U
T
Workshop
structure
developed
& agreed
by
18/6
Workshop
content &
presntn.
developed
by
5/7
30thSept
2001
further
recruitment
If /as
necessary
July-
Sept
R
E
H
E
A
R
S
A
L
by
17/7
A
P
P
R
O
V
E
D
by
10/7
A
G
R
E
E
G
O
A
L
S
&
B
U
D
G
E
T
S
1ST May
2001
materials
prepared
& printed
1ST July
2001
1ST June
2001
1ST Aug
2001
PHASE 1
definition
PHASE 2
planning
PHASE 3
organising
PHASE 4
executing
PHASE 5
Close-Out
WRITE
PROJECT PLAN
*
*
*
*
*
*
*
*
START
Asterisks = “Milestones”
*
*
Notes: Time-precedence (or Network Logic) Diagrams and the Project Life Cycle Here we show a time-precedence diagram we developed for our “project-within-a-project” scenario in our introductory module; it is also featured in our project management tool-kit. This may look complex, even complicated, at first sight but in reality it is quite simple, as explained below:
There are of course computerised versions of these types of diagram but this one (we feature some in later Slides), as many still are today, was developed on paper and then transferred to a number of visual-aids, including the graphical representation shown above. In some organisations it may well be printed on large scale card and mounted on a wall, or it may be written onto a white-board so that it is highly visible, can be seen, and used, by project staff and stakeholders. In computerised environments these charts will typically today be located on shared network drives where they can be made accessible to staff involved in the project. Later in this module we will be showing you PERT and GANTT charts (slide 14: Project Evaluation Review Technique and slide 15: GANTT chart), themselves varieties of network-logic diagrams.
The chart above shows clear time lines (see foot of the horizontal axis). There are two distinct - but obviously linked tracks or strands to this particular project, which in fact is based on a real-life (successful!) project to put on two introductory project management workshops for managers and key staff of the old Brent and Harrow Health Authority. For reference purposes we have shown the Project Life-Cycle stages at the very foot of the document. The top track, shaded blue, relates to the hiring of a contractor to develop the workshop materials and to deliver two workshops which the client – the Chief Executive of the organisation – wanted to run in late July and mid September (August being a prime holiday month in the UK). The other track - the lower one, shaded grey - combines two strands – the marketing of the programme/recruitment of participants and the hiring of suitable venues for the two workshops. You will note that the hiring of the venues and booking of dates needed to be synchronised with the hiring of the Contractor who would be delivering the workshops. Note that there is what we call ‘float’ time during August and the early parts of September when, if recruitment for Workshop 2 had not been wholly successful (it was!), further marketing of the 2nd workshop could have been undertaken. Had workshop 1 been unsuccessful (it proved to be highly successful) then this time was also available to re-visit the workshop structure and materials and to re-organise the workshop based on the feed-back from workshop 1. As mentioned above, in practice this diagram would have probably have been converted to a GANTT chart, or perhaps a PERT chart as these are typically more user-friendly and easier to read and communicate to people who may well not have had previous involvement with projects.

## Slide 8: The People Factor
communication is very important
  types and methods of communication:
    meetings, memos, e-mail, shared files (project management software etc)
need to keep team people involved
needs to be sense of shared responsibility
and shared values
key objective is to get shared ownership:
  of goals and their achievement
  of activities and their relevance
CLASSIC TEAM-DEVELOPMENT LIFE-CYCLE:
FORMING: STORMING: NORMING: PERFORMING
singing from the
same song-sheet
working together
towards shared goals
REVIEW
AUTO SLIDE
Please Wait
Teams and Team-working
Notes: The value of Teams and Team-working in Programme and Project Management
There is considerable evidence to show that team-work can play a significant part in project management - it is a key part of it, part of the ‘focus on results’ and on ‘managing resources’. There are a number of key features of good team-work that are worth noting - and striving towards:
Communication : between the project manager and his/her team, and between players in the team, is a critical area. How do they communicate? What do they communicate? The key aim is to keep all members of the team fully up-to-date, aware of what is happening and understanding of how their roles and activities fit into ‘the whole’.
Involvement of the team in both the design/development and the delivery of the project can pay big dividends; they start to work for each other, rather than merely with, or in the worst cases against, each other; thus a sense of shared responsibility is a key attribute of high-performing teams; a genuine sharing of values amongst the team can further add to team harmony and higher performance.
Team-work can be so important that it is worth mentioning here the classic model of team development
1. The team is firstly formed, created for a particular purpose i.e. a specific project.
2. Then the team members begin to storm (in the sense of brainstorming) the project, its requirements, how they will work together etc.
3. Typically there then follows a process of norming during which the team starts to work to agreed standards and work-practices that are normalised out of the two previous phases.
4. It is at this stage, the fourth stage, where teams begin to perform – not only to carry out the project activities but, working closely and carefully together to execute them to high standards.
NOTE: It is very useful for project managers and project co-ordinators to know and understand this team-working model; an understanding of the dynamics of team-working can help foster good team-working practices, help to ensure projects are delivered on time, within budget and to the required quality.

## Slide 9: Tips, Tools and Techniques l
deliverables
‘scenarios’
force-field analysis
swot and pest analyses
cost benefit analysis
risk assessment
the five whys
Feasibility, Scoping &
Risk Assessment Tools:
REVIEW
AUTO SLIDE
Please Wait
Notes: Feasibility, Scoping and Risk Assessment Tools
In this slide and those which follow, we will re-visit some of the tips, tools and techniques that apply to programme and project management and which can help make it particularly effective, enhance considerably its chances of success. Here we give merely an overview:
Deliverables are quite simply the goals, objectives and outputs of the project; they need to be clearly and accurately stated and defined at the very outset of a project. Clear definition of the deliverables, and agreement of them with the client/sponsor, is essential if a project is to be well planned, well organised and well executed (implemented). See slide 5:The Project Life Cycle.
Scenarios are a method of assessing how various outcomes might be achieved; several scenarios can be developed - and perhaps discussed with the client - so as to decide which one(s) represent the best blend of quality, time and money in achieving particular deliverables.
SWOT analyses help gather all the strengths, weaknesses, opportunities and threats that might be connected with the project and its delivery. PEST (sometimes called STEP) is a similar tool used for gathering relevant external information (on political, economic, social and technological factors) which could impact upon the project and affect its delivery. See Project ToolKit.
Cost benefit analyses are typically applied early in many programme and projects – usually in pre-start situations as part of an overall scoping exercise to assess the true value of the project, to decide if it should actually be carried out. In recent years large programme and projects have also been subjected to Health Assessments – what are the impacts, dangers, benefits in health terms of carrying out the project e.g building the new Wembley Stadium and its infrastructure, or building a new Power Station close to heavily populated areas. This is the stage at which the programme and/or project managers and the client(s) address the key areas of cost and evaluate these against the potential benefits that successful delivery of the project will bring. They are frequently carried out in conjunction with a technique known as scenario evaluation - different approaches and different solutions are assessed to ascertain which will be the preferred option. These techniques are covered in more detail in the tool-kit. Finally, there is also a process, a very useful one, known as the Five Whys that can be used to test the fundamental reasons for actually carrying out the project. Quite simply the project manager ask a series of ‘why’ questions (e.g. why should we do this?). The answer is then tested with another ‘why?’ until - normally on or about the fifth ‘why?’ - the fundamentals of the project (and therefore why it is being considered) become understood. WE often refer to this useful tool as the ‘nagging child concept’ - anyone who has had, or worked with, young children might quickly recognise might recognise “why”! See also slide 23: “The 5 Whys” in Introduction to project management.

## Slide 10: Tips, Tools and Techniques II
Planning & Implementation Tools
deliverable breakdown structures
milestones
work breakdown structures
work packages
meta-planning
network logic diagrams
time precedence charts
GANTT charts
PERT charts
critical path analysis
project software
  e.g Microsoft Project, Case, Prince 2
REVIEW
Those in blue were covered
in module 1: ‘Introduction to
Project Management’.
Those in red are covered
later in this intermediate module
AUTO SLIDE
Please Wait
Notes: Planning and Implementation tools Deliverables are the goals, objectives and outputs of a project; we can use them to start developing some structure into our project. This we do by using deliverable breakdown structures. (Slide 35: Deliverables)
Milestones are key points in the development of a project that project managers use to check progress, to help them spot any developing problems that might affect the overall outcomes of the project. Work breakdown structures are very commonly used devices that enable key areas and ‘packages’ of work to be defined and then allocated amongst the project team. (Slide 13: Work breakdown structure) Meta-planning is a particularly useful planning and scheduling technique which is covered in detail in our Introductory module slide and also in the Project ToolKit. Fundamentally, this technique starts with the project’s deliverables and then typically works backwards to consider what components of work, what activities, are needed to achieve that deliverable – in programme and project management parlance we call these components ‘packages’ of deliverables or packages of tasks/actions : ‘work packages’, as they are frequently referred to, that are the building blocks to achieving the project’s goals and objectives. (Slide 35: Deliverables)
Critical path analysis is a widely used technique - a fundamental of project management - that enables a project manager not only to determine the shortest period in which a project can be delivered but also helps define the aspects of the project that are most critical, the ones which will determine the ‘pathway’ to ultimate project success. (See slide 16: Critical Path Analysis and slide 17: Practical use of Critical Path Analysis). Network logic diagrams are logistical/mathematical tools used to calculate not just project schedules but also the various dependencies of tasks and actions that together comprise the overall project. Here we are following the Critical Path technique which these days seems more popular than its cousin the ‘Cost Specification Method’ (C/SPEC). In module 1 we looked at relatively simple time-precedence charts but also mentioned GANTT and PERT charts, both of which are derivations that are popularly used to represent and communicate the more complex Network Logic Diagrams: a GANTT chart is basically a bar-chart which uses time as its horizontal axis and on which the duration of various tasks and activities (and groups of tasks and activities) are represented geometrically (see also slide 15: GANTT chart). Project managers use them to plot the key tasks, activities and milestones within the plan against which they will mark/monitor/manage progress as the project develops. The PERT (Programme Review and Evaluation Technique) tool is another more user-friendly type of network logic, or precedence diagram (see also slide 14: Project Evaluation Review Technique). It enables a graphical representation of sequential activities that need to be performed during the project and helps the project manager schedule the various activities, understand their inter-dependencies and, importantly, to plot the project’s critical path. See next slide for software packages.

## Slide 11: Computerised Project Management Systems
Cobra
Incontrol
Microsoft Project
PMIS = Project Management Information Systems
AUTO SLIDE
Please Wait
There are literally hundreds of computerised project management
systems available today, here are just a few of the better-known ones:
Notes: Computerised Project Management Information Systems (PMIS)
Today project managers are increasingly turning to specialist software packages and computer-based applications to help them plan and manage their projects. We have listed just a small handful of the literally hundreds of such systems now available world-wide. See also slide 18: Project management methods and systems, slide 19: Example of project management systems and slide 20: Microsoft project 2000)
Microsoft have developed a fairly sophisticated package, Project 2000, which links readily with other Microsoft packages and applications (e.g Word and Excel) within the Microsoft Office suites.The latest versions also have 24/7 web-based support enabling project team members to access secure project records and documents from wherever in the world they might be. Even without Microsoft Project 2000, a company’s ‘Outlook’ and ‘Outlook Express’ packages can be deployed to support scheduling of the tasks and activities within projects.
There are many project management packages but before project teams rush into using these, we feel it is helpful for people in organisations where the project ethos is not strong, to first understand the fundamentals of project management before moving on to more formal computer-based systems. For, unless the majority of the project team know how to use them, they can become dangerously confusing or merely ‘expensive wallpaper’ that somehow simply ‘dresses’ the project, adding no real value. However, used well and as part of an overall project management system - and with proper structured staff training in their use - such systems can without doubt prove a real boon to project managers and their teams.

## Slide 12: Programme & Project Management : key features: Summary
client
sponsor
aims, goals and objectives
project life-cycle
scoping document: risk assessment: Cost–Benefit-Analysis
project plan:
  resources: activities: financial: schedules: critical path analysis
project management tools and techniques:
  GANTT and PERT charts: network diagrams: time/precedence charts
deliverables
work breakdown structure: work packages:
milestones
communication and reporting
implementation and monitoring
close-out
review
The features in green
are covered in our
introductory module,
Those in red are covered in this intermediate module
REVIEW
AUTO SLIDE
Please Wait
Notes: Review slide
Before we progress our thinking and activities on projects and project management we have listed above all the key features of project management systems. Those in green were covered quite fully in our introductory module, those in red are featured in this module.

## Slide 13: Work Breakdown Structure
work breakdown structure for the recruitment
of a new person to fill a vacant post.
Courtesy of SpottyDog Project Management
AUTO SLIDE
Please Wait
See notes
below
Notes: Work Breakdown Structures
This is a technique that helps us analyse the content of work and also the cost by breaking it down into its component parts. Work breakdown structures are derived from ‘network analysis’ systems many of which utilise the ‘critical path’ method covered in slide 16: Critical paths, and slide 17:Practical use of critical path analysis.
Work breakdown structures are often referred to as the ‘backbone’ of project management and the root of many project control systems.
They are produced by:
identifying the key elements
breaking each element down into component parts
continuing to break down until manageable work packages have been identified. These work packages can then be allocated to the appropriate person or people.
The use of work breakdown structures and work packages helps to develop the project into ‘hierarchies’, the lowest level of which is a well-defined task (i.e. one piece of work or group of tasks) for an individual to perform in a reasonable period of time.
See module1 and also pages 38-41 in Hobbs ‘Project Management Guide’ for a more detailed description of this process - and of the aspects and items that flow from them.
Shown in the slide is a work breakdown structure for the recruitment of a new person to fill a vacant post.
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 14: Project Evaluation Review Technique
Courtesy of SpottyDog Project Management
CRITICAL PATH
Network diagram for the recruitment
of a new person to fill a vacant post.
AUTO SLIDE
Please Wait
See notes
below
PERT
Chart
Notes: Project Evaluation Review Technique (PERT)
PERT* is used as a form of ‘network analysis’ to determine the inter-relationships between the tasks identified in the work breakdown structure (see previous slide) and to define the dependencies of each task. Whilst laying out a PERT chart, it is often possible to see that assumptions for the order of work are not logical or that they could be achieved more cost effectively by re-ordering or rearranging them. This is particularly true when allocating resources; it may become evident that two tasks cannot be completed at the same time by the same person due to lack of working hours. Conversely, by adding an extra person (even part-time) to the project team several tasks can be done in parallel - thus shortening the length of the project.
Shown in the slide is the PERT chart of the work breakdown structure shown in the previous slide after network analysis has been applied.
Critical Path Analysis (CPA)
CPA is used in conjunction with PERT analysis to identify the tasks that are critical in determining the overall duration of the project and that are critical to its overall success. In the example above the critical path is shown by the tasks in red boxes.
*NOTE: PERT systems were developed jointly by the US Navy Special Projects Office, Booz-Allen-Hamilton and Lockheed

## Slide 15: GANTT Chart
for the recruitment of a new person to fill a vacant post
Courtesy of SpottyDog Project Management
GANTT charts are a user-friendly visual version of ‘network diagrams’, designed to be easily understood and applied by non - ‘chart-ographers’ !
See notes below
AUTO SLIDE
Please Wait
Notes: Gantt charts
Gantt charts (although many people believe it’s a weird acronym its actually named after its inventor, Mr Gantt!) or bar charts as they are sometimes called, are used to display and communicate the results of PERT and Critical Path Analysis in a simple bar chart format that can be readily understood by those not involved in the detail of the project.
A Gantt chart is a horizontal bar or line chart which will commonly include the following features:
activities, identified on the left hand side
time scale is drawn on the top (or bottom) of the chart
a horizontal open oblong or a line is drawn against each activity indicating estimated duration
dependencies between activities are shown
at a review point the oblongs are shaded to represent the actual time spent (an alternative is to represent actual and estimated by 2 separate lines)
a vertical cursor (such as a transparent ruler) placed at the review point makes it possible to establish activities which are behind or ahead of schedule
Project management tools incorporating Gantt Charts include PRINCE, MacProject and Microsoft Project 2000.
The PERT chart shown in the previous slide is now displayed above as a Gantt chart.

## Slide 16: Critical Paths
Critical Path Analysis can also help project managers see where there is slack time with their projects - time between critical tasks in which other non-critical tasks can be completed
It also helps identify float times - how long certain non-critical tasks may be delayed without affecting the overall length of the project.
Critical Path techniques are very useful beyond the
fundamentals of project management
CRITICAL TASKS
SLACK TIME
FLOAT TIME
Once the Time-Precedence (or Network) Diagram has been developed, then Critical Path Analysis can be used to work out the shortest time it will take to complete the project
REVIEW
AUTO SLIDE
Please Wait
Notes: Critical Path Analysis
This is a very useful technique that builds upon many of the fundamentals we covered in our introductory module and forms the core of the Critical Path Method (CPM) of project management that was first developed in the 1940s – and which we are following in this module.
CPM/CPA lies at the heart of many proprietary project management systems, including most of the computer-based systems available today.
Essentially the technique allows a project manager to realistically calculate the shortest time that a particular project should take to deliver its goals and objectives. It does this by helping project managers understand those key tasks, activities and deliverables that are critical to many others.
PERT charts are very useful in bringing out these benefits; if you re-visit slide 14: Project evaluation review technique, you will see the critical path (the red heavily shaded boxes across the centre); the total time the project will take will be the aggregate of the times taken to complete each of these critical tasks; each can only be done when that proceeding it has been satisfactorily completed.
Float tasks are tasks where there is some flexibility between the scheduled task start date and the latest task start date that would be acceptable – in other words the project manager can ‘float’ the task further along the project time-lines without it becoming a problem or bottleneck to other tasks.
Slack time is time between critical tasks where other tasks, often additional tasks that arise during the project (e.g. remedial work or extra activities that become necessary) can be accommodated.

## Slide 17: Practical Use of Critical Path Analysis
aids scheduling
  tasks on the critical path tell us the total time required to complete the project
helps decide how to allocate tasks (including to whom?)
project managers must resist the temptation to do all critical path tasks themselves
critical path tasks need to be reviewed more often than other tasks
treat tasks with ‘float’ time as opportunities e.g. to coach/train/develop people
Important note: any task can become a critical task if it seriously misses its original deadline
Critical Path
AUTO SLIDE
Please Wait
Notes: The Practical Application Of Critical Path Analysis
The Critical Path Method (CPM) was originally introduced as an aid to scheduling - paths which lie on the critical path will indicate the total time that will be required to complete the project. Use of this technique helps project managers how to allocate tasks. They will also keep extra vigilant watch on tasks on the critical path because if they slip behind schedule the whole project can be delayed.
It can be advantageous to have some tasks with float time - they can be managed on a flexible basis around the critical tasks. However as we show above any task can become critical if it misses its own deadline.
So watch out for ‘non-critical’ tasks that creep up on you!

## Slide 18: Programme Project Management Methods & Systems
Manual, paper-based
Computer-based packages
e.g. Microsoft Project 2000
Case
Cobra
MinuteMan
better to understand the
fundamentals of project
management and to get
experience of applying
them before turning to
sophisticated
computer-based systems
or methodologies
AUTO SLIDE
Please Wait
SEE LATER SLIDE (#21) RE
“Prince 2” Methodology
Notes: Project Management Methods And Systems
For a decade or two, projects were handled largely on paper but in the late 1960s some organisations began developing software for their mainframe computers to help them improve their efficiency of handling projects. From those early days several software packages developed and became more widely used. Today there are literally hundred of project management systems, many for specialised application in particular sectors and industries.
But the first question should be – is there a need for them?
The answer is probably yes – but not until someone in an organisation has assessed their needs and then researched the market to see what meets those needs – and also looked at aspects such as staff training and budgets for it. Otherwise it may be better not to rush in and commit to any particular project management system or package. Better to train staff in the fundamentals then provide those who need it the opportunity to receive training and familiarisation on a system that can be effectively applied right across the organisation. There are many project managers using their own pet systems which often work very well for them - but frequently do not fit in with the approaches taken in other parts of the organisation.
We show above just a few of the frequently used packages.

## Slide 19: Example of Project Management Systems ‘MinuteMan’ System
AUTO SLIDE Please Wait
See notes below
use
left-mouse
or
right arrow
to
move-forward
Notes: Example of a Project Management System featuring a GANTT chart
The above chart shows some of the features of just one computerised Project Management system – MinuteMan. You can see the various task and activities along the horizontal time lines. Linkages of tasks are shown.
This diagram shows how milestones (white diamonds) may or may not lie on the critical path (see slide 16: Critical paths, and slide 17: Practical use of Critical Path Analysis); critical milestones are on red backgrounds, normal (i.e. non-critical) ones on blue.

## Slide 20: Sample of Microsoft Project 2000
GANTT Chart
AUTO SLIDE
Please Wait
See notes below
use
left-mouse
or
right arrow
to
move-forward
Notes: Microsoft’s Project software
Here is a replicate page of the main project document using Microsoft Project. Note milestones and critical tasks are shown in red. Project Manager’s regularly up-date progress to the system which then indicates the progress against plan. Resources (especially human resources) can be tracked, costed and managed via this system.

## Slide 21: PRINCE & PRINCE 2 Methodologies
used for larger projects in ‘controlled environments’
a Project Management methodology covering the organisation, management and control of projects
first developed in the UK in 1989
see Notes below for features, benefits and main applications
requires formal training & Prince accreditation
most useful in organisations that have adopted PRINCE project management methodology
http://www.ogc.gov.uk/prince/about_p2/about_intro.htm
Is a Registered Trade Mark of
AUTO SLIDE
Please Wait
Notes: The PRINCE Project Methodologies
PRINCE - which stands for Projects in Controlled Environments - is a project management method covering the organisation, management and control of projects. PRINCE was first developed by the Central Computer and Telecommunications Agency (CCTA) now part of the Office of Government Commerce (OGC) in 1989 as a UK Government standard for IT project management. Its use as a programme and project management methodology continues to increase in the UK and beyond – but it remains of most practical use in larger, capital intensive projects in, as stated above ‘controlled environments’. Learning PRINCE2 (the latest version, see below) can be useful for individuals – but is only of real practical relevance if the organisation, or part of the organisation, that you work in has adopted PRINCE as its preferred project management methodology
Since its introduction, PRINCE has become widely used in both the public and private sectors and is now the UK's de facto standard for the management of larger projects. Although PRINCE was originally developed for the needs of IT projects, the method has also been increasingly used on many non-IT projects. The latest version of the method, PRINCE2, is designed to incorporate the requirements of existing users and to enhance the method towards a generic, best practice approach for the management of all types of projects. PRINCE2 provides benefits to the organisation, as well as the managers and directors of the project, through the controllable use of resources and the ability to manage business and project risk more effectively. PRINCE2 enables projects to have:
A controlled and organised start, middle and end;
Regular reviews of progress against plan and against the Business Case;
Flexible decision points;
Automatic management control of any deviations from the plan;
The involvement of management and stakeholders at the right time and place during the project;
Good communication channels between the project, project management, and the rest of the organisation.
The PRINCE2 (Managing Successful Projects) Manual is published by The Stationery Office, priced £55. For information on obtaining a copy of the manual, please view the Publication page or go to http://www.ogc.gov.uk/prince/about_p2/about_intro.htm