## Slide 1: Introducing
The FeelGood Projects
Please read the report below by the manager
who organised ‘Feelgood Day’
Consider how the application of the principles of
project management could have helped in the
organisation and implementation of this event
Practical I
A summary + further information on ‘Feelgood Day’ are on the next slide
AUTO SLIDE Please Wait
Notes: Practical: Report re “FeelGood Day”
Organisers: Community Involvement and Health Promotion team, Brent and Harrow Health Authority(BHHA); and Occupational Therapy Manager, Mental Health Unit, Harrow and Hillingdon Healthcare Trust (HHHT).
Rationale: The organisers decided that Wednesday 10th October, World Mental Health Day, was the ideal time to promote staff mental well-being. A decision was made to implement the suggestions raised by staff participating in the Coping with Change workshops, organised by the Health Authority earlier that year. Time frame/budgets: The organisers raised the idea at a Mental Health Promotion meeting in mid-August and this was favourably received. Action began at the end of September continuing until 2 October (two weeks), once funding had been approved. The Trust Fund at the Health Authority agreed to fund up to £400. This amount would be matched by partner organisation Harrow and Hillingdon Healthcare Trust, to bring the total to £800.
How the day was organised: key steps (see next slide)
Findings: Number of people who attended = 73
Cost-effectiveness: Total cost of venue and food = £1397.95. Cost of contributors (contractors) = £260.00
Total cost = £1657.95. Cost borne by each of BHHA and HHHT = £828.98
Cost per person = 1657.95/73 = £22.71
NOTE: The total amount spent (£1,700) was twice the original budget. The budget was increased when the likely numbers and precise costs were known, a few days before the event. What worked well? Yoga, Tai Chi, opportunity to relax and look after oneself, opportunity to feel valued, networking, lunch, group bonding. What could have been improved? Larger venue, more time for individual sessions. taking bookings in advance for these treatments, adequate ventilation, event attracted very few men, some staff from Wembley unable to come because no car, more advance notice of such events, should have been within budget.
Conclusions: Overall, the event was extremely successful, judging by an analysis of both the quantitative and qualitative data. The event was perceived to send a positive message to staff, who clearly indicated that they would like similar events to be organised on a more regular basis in the future, particularly activities such as Yoga and Tai Chi. While the event did run over budget, the venue and the food absorbed most of the costs, not the contributors themselves. Therefore, if classes could be set up at cheaper venues, then this approach would be a positive way of promoting staff well-being, without being resource-intensive. As a direct consequence of the day, a local massage therapist who facilitated an aromatherapy workshop at the event suggested offering free treatments to staff on a weekly basis. Sessions are already underway for Health Authority and PCG staff at different locations each week to ensure that the treatments are accessible to everyone. The event was an example of good practice in mental health promotion and will be included and costed in local strategies, to keep such activities sustainable.

## Slide 2: FeelGood Day 10th October 2001
-
Summary :
event for NHS Staff as part of World Mental Health Day 2001
main goals:
  publicise World Mental Health Day
  help staff undergoing major organisational change (reduce stress etc)
main problems:
  budget setting
  event logistics
  very few men attended
Outcomes :
73 attendees
cost per person: £22.71
excellent feedback
  good range of activities
  some difficulties in people getting to venue
Yoga
T’ai Chi
Aromatherapy
Stress Relief
“Excellent Day”
“Very enjoyable”
“Very Relaxing”
“Let’s Do It Again”
AUTO SLIDE
Please Wait
See Notes Below
Notes: How the FeelGood Day was Organised:
The idea was discussed with the organisers at Brent and Harrow Health Authority (BHHA) and Harrow and Hillingdon Healthcare Trust (HHHT) and it was agreed to take it forward and work together
Trust Funds money was applied for, and support sought from HR managers
approval gained from Trust Funds of principle and secured funding
networked to find out details (cost, availability) of possible contributors of complementary therapies
decided on appropriate venue, Harrow Hotel - local, accessible, history of working with them, pleasant, familiar
determined cost of venue and booked a suitable room
drafted an agenda for the day
notified Health Authority (HA) employees to keep the date free until detail had been finalised
booked times and activities with contributors
gained assurance from her manager that her team could pay for the excess costs, if the Trust Funds wouldn't
confirmed amongst organisers the agenda and the final e-mail that would be circulated to staff
drafted a flyer, which was posted within the organisations and notified HR manager of developments
posted the final e-mail with agenda to staff at HA
secured media coverage with HR Manager
visited the venue a couple of days beforehand and made adjustments to layout of room and confirmed eating arrangements
set up the room early on the day, including a visitor's book to keep track of who attended and their feedback, a display of health promotion resources from BHHA and examples of good HR practice from 3HT, a screen to cordon off the individual therapies, refreshments, and audio-visual equipment

## Slide 3: FeelGood 2
FeelGood 2 is our project scenario for this module
Key features of the scenario:
• proposal to organise ‘FeelGood 2’ event in March 2002
•’in principle’ budget must be agreed – subject to:
• full project plan including:
• scope
• goals and objectives
• recommended venues and catering
• overall budget
• project ‘milestones’
• detailed event plan
see detailed Brief below
TOOL-KIT
work book
AUTO SLIDE
Please Wait
Notes: The ‘Feelgood 2’ Project
Introduction: Following the success of a FeelGood day, organised as part of World Mental Health Day 2001 for staff of Brent & Harrow Health Authority (BHHA) and Harrow and Hillingdon Healthcare Trust (HHHT) it is proposed that a follow-on event, to be known as FeelGood 2 should be held in March 2002. Turnout at the initial event on October 10th 2001 was very good, as was the feedback from the 73 people who attended. Some of the lessons learned from the first event will need to be considered when putting on a proposed wider programme of activities offering attendees a greater choice of activities and timings. The date proposed for the day-long event is 21st March, 2002 the first day of Spring. There are options on venues and costs.
For this event a more structured Project Management approach is to be adopted. Objectives: The primary objectives for the event are to promote staff mental well-being; given the high record of stress-related ill-health suffered by NHS employees generally the programme is proposed to consist of optional activities that will help staff cope with some of the stresses and strains of major change initiatives. A range of interesting and varied programmes is being considered, again at the Harrow Quality Hotel – which proved a popular and successful location in October. However, in an effort to achieve good value-for-money other cheaper options are also being considered. This time the aim is to get 125-150 people to attend during the day, also to increase significantly the proportion of males attending. The overall aim is to provide a relaxing and enjoyable experiences for all those who attend.
Approach: 1. Given the lessons learned from the first event a more structured project management approach is to be adopted. 2. This time there will be, subject to approval of a detailed project plan, a clear budget and milestones. 3. Quality and satisfaction with the event will be measured by questionnaires that attendees will be asked to complete before leaving. 4. On this occasion there is the opportunity to consider using a trial version of Microsoft Project 2000 as a planning and monitoring aid. 5. Although attendance will be voluntary, the event will be marketed and promoted by BHHA and HHHT and the aim is this time to get at least 125 staff to attend during the day. 6. To help planning and logistics, the intention this time is to positively encourage participants to pre-book.
Organisation of the project: The project is to be organised by BHHA and, as in the original ‘FeelGood’ Day, HHHT.
Rationale: A potential budget of up to £1,000 has been identified from the BHHA Trust Fund; there may be additional funding available if pre-bookings indicate high levels of intended acceptance. It is intended that HHHT be asked to match this amount but this can only be approved once a viable project plan has been submitted and agreed.

## Slide 4: FeelGood 2 Project
SCHEDULE OF CONTRACTORS AVAILABLE AND COSTS
M = believed to be of appeal to men
CONTRACTOR
COST
AVAILABILITY
COMMENTS
Aroma -tiks
£100
All sessions
Ind. 20 min sessions: table + power
Body Beautiful
£100
All sessions
Ind. 20 MIN table/chairs - (M)
Colour Me
£75
Afternoon only
Presentation – 10/15 @ 30 min session
Dress ‘n’ Go
Free
All sessions
Presentation : 10/15 @ 30 min. session (M)
Exercise the Mind
£50
All sessions
Presentation : 5/10 @ 30 min session (M)
Forget-me-Not
£75
Morning only
Presentation : 10/15@ 30 min session (M)
Glad-to-be-Alive
£50
All sessions
Personal 20 min consultations:
Happy as I Am
Free
All sessions
Personal 20 min consultations
Harrow Quality Hotel : £250 per session a.m/p.m (total £500 for full day)
2 adjoining rooms = additional £50 per room per session (max £200)
Food/refreshments: £2 per head (refreshments) £6 per head (lunch)
Business Exchange : £150 per session am/pm : £250 for full day
Adjoining room: same price/terms
Food/refreshments: as Harrow Quality Hotel above
Another no-cost NHS location (Belmont) has also been suggested, but not yet checked out. Catering at this venue would need to be brought-in but is believed to be about 25% cheaper than the above Hotels
AUTO SLIDE
Please Wait
COST ESTIMATES & POSSIBLE CONTRACTORS
Notes: Projected Costings for FeelGood 2 :
You will need to consider the undernoted options regarding
location for the FeelGood 2 day
contractors available to be present on 21st March 2001
Venues:
Harrow Quality Hotel : £250 per half day (Total £500 for full day)
2 adjoining rooms: additional £50 per room per session (Max £200)
Food/Refreshments: £2 per head (refreshments); £6 per head (lunch)
This Hotel was used for the original FeelGood day and feed-back was generally quite good
Business Exchange, Harrow : £150 per half day (Total £250 for full day), adjoining room: same price/terms
Food/refreshments: as for Harrow Quality Hotel
More of a Business Centre in central Harrow but with same standard/similar quality of facilities
Another no-cost NHS location (Belmont) has also been suggested, but not yet checked out. Catering at this venue would need to be bought-in but is believed to be about 25% cheaper than the above hotels
Contractors (providers of ‘stalls’ and services)
These are local people and businesses who see potential marketing value in getting their facilities and products in front of 100+ interested and potential customers in one day.
Eight have been identified who can do the proposed date. See table above

## Slide 5: Practical II
who are the main stakeholders ?
who is the client ?
who are the end-users ?
is the project time limited ?
is there a budget ? If so how much ?
is there a feasibility - a GO/NO-GO point ?
FeelGood 2
NOTE
Slide 10 in
module 1 has
details about
stakeholders
AUTO SLIDE
Please Wait
See notes below
Notes: People and players in projects (these notes appeared in module 1 in association with a similar exercise to the above)
Firstly there is typically a client – the person or organisation who initiates a project. In the movies this might be Universal Studios; in the ‘Heartbete’ example in module 1 it was the Harrow Primary Care Group. Typically clients set the overall goals (the deliverables, the quality parameters and the overall budgets), but these are then normally finally agreed in detailed discussion with the project director/manager or project co-ordinator. Some projects also depend upon sponsors – people or organisations who are brought in to co-fund or co-produce the project. In the film-world this could be a specialist film-financing organisation (who will share in the success or otherwise of the finished film); for ‘Heartbete’ it could be a charity e.g. British Heart Foundation. Sponsors often share the risk of carrying out the project – they share the cost of doing the project and/or they enjoy certain benefits based on, or flowing from, its success.
A big project will typically have a director who will have overall responsibility for delivery – and who may well hire a specific project manager (or even a whole project management team). Smaller projects may simply use a project co-ordinator – someone whose responsibility it is to manage and co-ordinate the resources to deliver the project. As quality and cost are important, larger projects may well have specialist quality assurance and finance managers, who may work either full-time or part-time on the project depending on the size, scale and overall deliverables. Also, dependant upon the size and scale of the project, there will be either part-time and/or full-time people appointed or hired into the project team; these may be a mix of ‘internals’ (people from within the organisation that is carrying out or managing the project) and ‘externals’ (typically specialists and contractors who are brought in to deliver specific areas and pieces of work e.g. publicity, design, presentational material).
Finally, many larger projects, especially those that depend on public or part-public funding and involve relatively high levels of accountability, use a project steering group, a group of key people representing stakeholders in the project who meet with the project director/manager at agreed intervals to discuss progress and problems.

## Slide 6: Project Life-Cycle: Phase1 Project Definition Phase
this is where the proposed project and the need for it, is assessed and defined using:
  feasibility or scoping exercises
    risk assessment
    cost-benefit-analysis
    a number of tools and assessment models
it is during this stage that you determine the project’s overall time-cost-quality parameters – and their relative importance (see triangle, slide 2)
‘it is important in this stage to clearly define the goal and principal objectives of the project’ (Hobbs pp 30-33)
  It can be helpful to write a succinct ‘project mission statement’
outputs from the use of these tools and techniques typically lead to a “Go/No-Go” decision
REVIEW
See notes below
AUTO SLIDE
Please Wait
Notes: The Project Definition phase of the Product Life Cycle
In this first phase of the project life-cycle we are seeking to clearly define what it is that we are to achieve – determine the project’s goals and objectives, the timescale and the budget and also the quality parameters i.e the three main points of the project management triangle shown in slide 2.
To help us do this we carry out the feasibility and scoping exercises, using a number of project management tools and techniques.
Sometimes the feasibility study has already been conducted - and a GO/NO GO decision has already been made - before a project is handed to a project team, in which case the project manager/supervisor and his/her team will concentrate on the definition of the project. Where the feasibility study has not been carried out we need to make a detailed assessment of the project - to consider the risk involved, to conduct a cost-benefit analysis, applying a number of assessment tools, instruments and techniques. We need to carry out all or some of these (depending upon the size and scale of the project and its importance) before we make a considered GO NO-GO decision, which is then normally agreed with the client and the sponsors of the project. This we do by accumulating the feed-back (outcomes) from the various tools and techniques mentioned here (and also covered in the project management toolkit); we also re-visit the main tools and techniques that we can use (next few slides). The summaries of the outcomes from the use and application of these tools and techniques are then used to:
(where a GO/NO GO decision has not already been made) make a final assessment and recommendation as to whether the project should go ahead
formally scope and define the project – to develop the project mission statement, determine the goals and objectives and agree the key project parameters (time/cost/quality)
(see Hobbs’ pp 30-32)
It can be very helpful then to capture the scoping and definition of a project in a summarial Project Definition Document (see Slide 29: Project definition summary, example in toolkit, and Hobbs pg 33)
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 7: Practical III
Tools you may wish to consider using:
The ‘5 Whys’
* Cost-benefit analysis
* Force-field analysis
* Risk assessment
Complete a
Project scoping/definition for the ‘FeelGood 2’ project
Use a
Project Definition Document
to summarise
See sample slide
* Covered in next
few slides
AUTO SLIDE
Please Wait
Notes: Practical: Project Scoping and Definition
Use the various tools and techniques as necessary to scope and define the FeelGood 2 event.
There is a Project Definition Summary located on the next slide.
See also the Project Management ToolKit.

## Slide 8: Project Definition Summary
Project name: FeelGood 2 | Project No.: 01/17
Sub projects: None | Related projects: FeelGood 1
Project manager : A. N. Other | Client:
End users: BaHHA/HHHT staff | Sponsors : Trust Fund/HHHT
Key benefits: | Scope:
Goals: | Objectives:
Timings : Draft plan by 10/12/01 | Deliverables:
Costs: | Milestones:
Quality parameters: | Key resources:
Authority levels | Key assumptions:
AGREEMENT Client (Sponsor) | AGREEMENT Project manager
Developed from Hobbs ‘Project Management : Essential Guide’
AUTO SLIDE
Please Wait
See notes below
Notes: Project Definition Summary
It is highly recommended, once scoping and definition of a project is completed, that a formal Project Definition summary is completed. See example above, developed from the essential guide by Peter Hobbs (Pg 33) This cements the project definition and, as outlined in the example above, provides the facility for the client, any sponsors and the project manager to agree all the main parameters of the project. This then becomes a key document for the project and typically if there are to be any variances during the project these should be agreed between the signatories.
In this way the journey plan - the “route map” for the project - is clearly established at the outset and arrangements put in place as to how the project will be managed/handled. It should also be used as a key document when the project is concluded and the final project report is prepared – were all key goals and objectives met? Was the project completed on time? Within budget? Were the quality parameters achieved? Were the key benefits realised?
Note: In our FeelGood 2 scenario there is not at this stage a budget; you are asked to prepare a draft project plan and if this is accepted (on or about the 3rd January 2002) a budget will be agreed. For this exercise you will need to consider all factors and recommend a suitable budget geared to particular quality parameters.
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 9: Cost Benefit Analysis & ‘Scenarios’
together they are a means of ‘weighing up’ whether a project is worth embarking upon, whether its costs justify the benefits:
  why do it ?
  try the ‘5 whys’ approach (see toolkit)
  not all projects are purely costs driven so…….
it is therefore worth careful evaluation of benefits – not all have a primarily financial benefit……..
……remember quality is also a key consideration
when all factors are taken into account the end result is to make a decision !
GO !
NO-GO!
?
REVIEW
AUTO SLIDE
Please Wait
Notes: Cost Benefit Analysis:
This is a very useful tool that can be used early on in the definition phase of a project; it can be used to help determine the real or perceived value of a project - a measurement of the outcomes and impacts of the project (the benefits) against the costs. Using cost benefit analysis the project manager can establish with the client (also the sponsor where relevant) the overall value of carrying out the project. Cost Benefit Analysis can be especially useful, as we have said, when used alongside scenarios. Scenarios are ‘what if’ situations that are developed to facilitate comparison and assessment, the aim being to help the project manager to make decisions about preferred courses of action. Thus a number of different scenarios can be developed and considered, the relative values of each ascertained, and final decisions then made. See Module 1 for a worked example related to our project-in-a-project scenario.
Slide 25: Cost Benefit Analysis, in module 1 has more on cost benefit analysis.

## Slide 10: Force Field Analysis
Force-field analysis is a tool that helps
us assess the factors that drive and resist
change and/or new initiatives (see toolkit)
REVIEW
here is a partially completed Force-Field for factors
affecting staff morale-boosting events such as Feel Good 1 & 2
Notes: Sample Force-Field analysis
Here is an example of a Force-Field analysis. These are covered more fully in Module 1 and also in the tool-kit.

## Slide 11: Risk Assessment
there are a number of tools and techniques:
here we show a simple but quite effective numerical assessment:
How likely is this particular risk to happen?
How serious will it be if it does?
1
10
Very
unlikely
Extremely
likely
5
Quite
likely
1
10
Trivial
Extremely
serious
5
Quite
serious
Suggestion: look hard at anything scoring 25-30 +
REVIEW
AUTO SLIDE
Please Wait
Multiply the two
scores together
*
3
*
8
EXAMPLE
Risk of Not
Getting Enough
Participants
3 X 8 = 24
Notes: Risk Assessment
Refer to tool-kit (also Hobbs pg 47) for full details of using this technique which is based on a scoring system that drives us to think about the fundamentals of the project and the key factors that will determine its success or failure. There is a worked example in module 1.
There is also further information on the next slide.
The technique is also covered in the downloadable Project Management Tool-Kit.
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 12: Project Life-Cycle: Stage 2: Planning Phase
once a GO decision is made:
clearly determine the aim, goals, and objectives
determine realistic time-scale & budget
agree goals and mission statement with client
agree deliverables, time-scale and budget with client
develop the project plan
The project plan is the key document (or software) which
captures the goals and objectives
and develops/schedules the key
actions, activities and tasks which
will deliver the project :
- on time and within budget !
AIM OF PROJECT
GOALS & OBJECTIVES
BUDGETS
KEY DELIVERABLES
ALLOCATION RESOURCES
PEOPLE
EQUIPMENT
PROPERTY
MONEY
WORK BREAKDOWN
STRUCTURES :
WORK PACKAGES
PERFORMANCE TARGETS
SCHEDULES
MILESTONES
MONITORING POINTS
PROJECT PLAN
PROJECT
PLAN
REVIEW
AUTO SLIDE
Please Wait
Notes: Planning your Project
Before we look in detail at project planning let us first consider how programme and project management can be used in organisations:
We have said that project management is designed to help manage discrete, defined pieces of work that have a finite term and clearly identified, deliverable goals. Project management techniques can be applied to new product development, to events and product launches, to organisational change programmes and to information technology installations. Typically for all but repeat projects where there is good prior experience, it is very useful to firstly conduct a feasibility study – to include (where appropriate) also a risk assessment.
A feasibility study is typically a set of scenarios that the project manager generates using a number of techniques (including a SWOT – Strengths/Weaknesses/Opportunities/Threats – analysis and, where significant external factors are involved, a STEP or PEST analysis (analysis of Social, Technological, Environmental and Political factors). The scenarios will also include financial feasibility, a critical assessment of the amount of money and resources that need to be invested in the project, measured against the outcomes – the benefits – of doing the project. There are degrees of risk attached to all projects and it is often important to conduct an up-front risk assessment so that the client/sponsor and the project manager fully understand the risks, individual and collective, that are involved in carrying out a project. Thus risk assessment is an approach which attempts to spot potential problems and think of possible solutions before resources are committed and work gets underway. This way the costs of various solutions, activities and resources can be factored into the project, their overall impact assessed from the outset.

## Slide 13: PRACTICAL IV
project deliverables
work breakdown structures
work packages
use ‘meta-planning’ to determine:
‘FeelGood 2’
See next three slides for relevant information
AUTO SLIDE
Please Wait
Notes: Working with Work Breakdown Structures & Work Packages
Deliverables and meta-planning are described in the following slide.
Work breakdown structures in slide 37: Work breakdown structures & work packages

## Slide 14: Deliverables
Metaplanning:
a technique that can help
us determine work
breakdown structures
and work packages
a list of all the key items to be accomplished (delivered via the project)
  what? when? by whom?
there are end-deliverables i.e. ‘end products’
  e.g. a workshop, conference, programme or event;
  a fully tested and commissioned de-salination plant
….and there are mid-project deliverables
  e.g. obtain suitable venue : and speakers;
    prepare and print practicals or hand-outs;
  full working drawings and specifications pre planning application
Deliverables are used to determine
Work breakdown structures
and work packages
REVIEW
AUTO SLIDE
Please Wait
See notes below
Notes: Project Deliverables and Work Packages using Meta-Planning Project managers typically look first at the deliverables of a project and then, as we have said, tend to work backwards, from the deliverables, many of which will have been already considered in the definition phase of the project in order to determine deliverable breakdown structures - which are then used to to develop work breakdown structures and then work packages.
Practical: Meta-planning It is here that the concept called MetaPlanning can come in very useful: This is ideally a team activity: take two packs of differently coloured post-it notes and pens; you’ll also need a whiteboard or any convenient flat surface (on which the post-its will be placed). Then, re-state the deliverables, developed from your definition phase of the project, and any obvious constraints that have been identified. On one colour post-its work with the team to write all the deliverables (outputs – things you’ll need to produce) and, on another colour, all the things you’ll need to do (tasks and activities) to achieve the deliverables. Next, stick all the post-its on the chosen surface – initially in any order. Then separate the deliverables from the tasks/activities; use the deliverables as the headers and then group all tasks relevant to each deliverable underneath it. As the team do this, encourage team members to place the tasks/activities in groups and/or sequentially (i.e. the ones on which other tasks depend first). Note: during this stage you and your team may well think of additional tasks – in which case make out additional post-its and place them wherever they best fit. Using this process you should, after discussion and a certain amount of moving the post-its around, have determined not only a deliverable breakdown structure but also work breakdown structures. You may well also be able to start adding the names of people who will undertake specific tasks and activities. This will help you to determine some groups of tasks/activities and their dependencies on each other – thus enabling you to establish some work packages. (See Hobbs pp 38-41)
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 15: Scenario Deliverables
Let us now determine the key deliverables in our FeelGood 2 project scenario and the dates they need to be delivered by
DELIVERABLE | BY (date) | COMMENT
Full project proposal for consideration |  | 
AUTO SLIDE
Please Wait
See notes below
Notes: Project Deliverables
The template above has been designed to help you determine the key deliverables in our FeelGood 2 scenario. We have entered the first deliverable, development of the full project plan which, in this instance, is required before a GO/NO GO decision can be made.
You need to work out what the other key deliverables will be.

## Slide 16: Work Breakdown Structures & Work Packages
it is a ‘top-down’ process (i.e developed from ‘deliverables’)
by which we create a work hierarchy
  in which the lowest level is ‘a well-defined task for an individual to perform in a reasonable period of time’
work packages are derived from the work breakdown structures
  work packages define:
  what is to be done
  who is responsible for doing it
  start and completion dates
  deliverables
  milestones
Work
Package
1.
we use work breakdown structures to divide
‘pieces of work’ into individual tasks:
PROJECT
AUTO SLIDE :
Please Wait
Notes: Work Breakdown Structures
These flow naturally as we have said from the deliverables breakdown structure and can be determined, (as mentioned in slide 34: Deliverables) by using meta-planning techniques (the technique that uses post-it notes and a large wall!). They also help us to determine our work packages.
Each work-package links back to a deliverable and will typically form part of a least one milestone.
The use of work breakdown structures and work packages helps to develop the project into hierarchies, the lowest level of which is a well-defined task (one piece of work or group of tasks) for an individual to perform in a reasonable period of time.
Pages 38-41 of Hobbs’ Project Management guide give a more detailed description of this process - and of the aspects and items that flow from them.
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 17: Practical V
Draft a preliminary project plan for the FeelGood 2 project
Draft a time-precedence diagram
Consider what are likely
to be key milestones
‘FeelGood 2’
See project management tool-kit
DOWNLOADABLE
See notes below
AUTO SLIDE:
Please Wait
Notes: Practical: Drafting a Project Plan: Milestones: Time-precedence Diagrams
Once we have worked out our Deliverable Breakdown Structure (DBS), our Work Breakdown Structure (WBS) and our work packages, we can finally determine our milestones. In fact, often project managers try to ‘guesstimate’ their likely milestones quite early on in the planning process and then keep re-visiting and re-validating them as techniques like DBS and WBS are applied.
“Milestones are Interim objectives, points of arrival in terms of time for purposes of progress management.” Project Management Glossary
“A Milestone is “a significant scheduled event that acts as a progress marker in the life of a project. A milestone is either passed or it is not, the achievement, or non-achievement, of which is monitored and reported.” Tasmanian Government Web-Site – Project Management Glossary at http://www.go.tas.gov.au/projman/pmirp_definitions-2.htm#M
For an example of a time-precedence diagram visit slide 7: Time-precedence chart. You may also want to re-visit GANTT (slide 15: GANTT chart) and PERT (slide 14: Project Evaluation Review Technique) charts and Critical Path Analysis (slide 16: Critical paths, and slide 17: Practical use of critical path analysis).
There is a template for a project plan in our project management tool-kit which is downloadable
elsewhere on this platform.

## Slide 18: The Project Plan: Records & Monitoring
draft the project plan
discuss it and its implications with the team:
  preferably get the team involved with drafting the plan
agree records, monitoring & communication systems
finalise and formalise the plan:
  ensure it has ‘visibility’
identify the ‘key performance measures’ (KPMs)
incorporate milestones
maintain records, use regular monitoring
…..and reviews
REVIEW
AUTO SLIDE :
Please Wait
Notes: The Importance Of The Project Plan
We have emphasised already that a core element of project management is the project plan itself. Used properly it can drive and steer the project through its various stages towards successful delivery – on time, within budget and to agreed quality standards. Here we look in more detail at how the project plan is developed and used; we also consider some of the main features of a project plan. Typically, following the scoping of the project and any feasibility study and risk assessment (slide 32: Risk Assessment), the project manager will begin to draft the plan – typically working backwards from the deliverables as we have shown earlier in this module in order to develop the key components of the plan that will be required to ensure it achieves overall success. Frequently project managers bring in their project team to contribute to the plan’s development and this is a good way of establishing ‘buy-in’ from the team members, encouraging shared responsibility, shared values and shared commitment to making the project a success. In slide 35: Deliverables, we detailed a very useful approach (called ‘MetaPlanning’) to project planning that many teams find particularly valuable.
It is important that a project ‘platform’ for communication, monitoring and review of progress and problems is determined at an early stage. It is important that as the plan is finalised the project manager and his/her team agree on a number of key performance measures (KPMs) (sometimes referred to as key performance indicators (KPIs) that they will use in the processes of monitoring and review as the project progresses……and from the detailed planning it will be important to identify a number of key project milestones - summarised in the next slide - things or ‘bundles of things’ that need to be achieved before the project can move on to subsequent phases.

## Slide 19: Milestones
Milestones should be:
  SPECIFIC
  MEASURABLE
  ACHIEVABLE
  REALISTIC
  TIME-BOUND
MILESTONES
(or ‘checkpoints’):
milestones are key dates, key events or key deliverables in a project
make sure
milestones
are not
millstones!
1
2
3
4
work packages
key points or events in a project
REVIEW
AUTO SLIDE :
Please Wait
Notes: More on Milestones
OK, we’ve mentioned milestones many times by now. That’s because they are one of the fundamentals of project management – and also because they are important!
They are a particularly useful device that project managers can use as an aid to the measurement of performance and achievement against plan.
In essence, milestones are checkpoints along the critical path of a project which enable the project manager to consider achievement and attainment against plan as the project develops. Milestones may well be key, critical events or actions which until achieved prevent movement through to subsequent parts and phases of the project. Or they might be ‘packages’ of events and/or activities that need to be accomplished, again before progression to later phases and activities can be achieved. Many, often all, milestones will lie on the critical path.
Realistic determination of milestones is essential – make them too stretching and the likelihood is that they are missed and that the project falls behind schedule. Advice to project managers is: ensure that your selected milestones are realistically achievable – don’t let them become ‘millstones’ (i.e. impossible-to-achieve milestones that when missed weigh the project down - causing it to fall behind schedule, and also potentially causing it to over-run on cost).
There is an acronym - known as SMART - that can help us ensure that our milestones don’t become ‘millstones’. SMART stands for Specific, Measurable, Achievable, Realistic and Time-bound. It can be useful to test any milestones you select against this set of parameters.

## Slide 20: Example Answers
Click right mouse or right-arrow to proceed to reveal
these only if you have completed the exercise or
are in need of further assistance
The following three slides form part of the answers to our 5th and final practical
GO!
Notes: There are no notes with this slide

## Slide 21: Scenario Deliverables
Here we have determined the key deliverables in our FeelGood 2 project scenario and the dates they need to be delivered by
DELIVERABLE | BY (date) | COMMENT
Full Project Plan/Proposal | 12th December | Date it is required
GO: NO decision | 3rd January ‘02 | Date agreed
125-150 NHS staff booked (of which min 20% are males) | 1st March ‘02 | Date by which we need to make bookings
One high-quality event | 21st March ‘02 | Agreed event date, “first day of Spring”
One Close-out report | 10th April ‘02 | Gives enough time to complete this
AUTO SLIDE :
Please Wait
Notes: Project Deliverables for FeelGood 2
The template above has been designed to help you determine the key deliverables in our FeelGood 2 scenario.

## Slide 22: Example of a Project Schedule and Milestones
AUTO SLIDE :
Please Wait
  DELIVERABLE : Receive and welcome 150 staff to quality FeelGood2 event 21/3/02
  ---------------------------------------------------------------------------------------------
  if numbers under target: re-market the event – 16/2 and 1/3
  ---------------------------------------------------------------------------------------------
  Milestone: 150 CONFIRMED BOOKINGS RECEIVED
  --------------------------------------------------------------------------------------------
  record detailed bookings; recognise capacities - ongoing
  acknowledge bookings – send detailed booking sheet by 8/2
  draft and agree acknowledgement form by 1/2
  monitor responses in bookings register (paper or IT) - ongoing
  set up Bookings register by 18/1
  Milestone: dispatch letter/and/or e-mail by 18/1
  draft letter and/or e-mail by 10/1
  decide if all to be approached – if not who, what groups by 10/1
  get database of all target staff – by 7/1
  ---------------------------------------------------------------------------------------------
NOTE: Dates in red will lie along the critical path
  “GO” DECISION + BUDGET APPROVED : 3rd January 2002
End deliverable =
get 150 Staff to attend FeelGood 2 event
Notes: Project Schedule and Milestones for FeelGood 2
In this slide we have shown the sequence of events that need to happen if the FeelGood 2 event planned for 21st March 2002 is to go ahead. Reading upwards from the project approval at the very bottom of the slide (we have assumed a ‘yes’ decision) the project team will need to handle an awareness and internal marketing campaign that will hopefully bring in bookings for the required 125 to 150 staff on the event day. Clearly the despatch of a warm and friendly letter of invitation will be an important Milestone - as will the date on which the project managers actually achieve the upper limit of 150 confirmed bookings. You can see the individual actions and steps that need to be taken to achieve this.

## Slide 23: Examples of Milestones
Milestones in our scenario will be :
  by 10th Dec ‘01 we need to have prepared & submitted our detailed proposal
  if ‘GO’ decision (3rd Jan) then we need a budget and to set milestones
  3. by 16th Jan we need to have contracted with a suitable venue for 21/3/02
  by 16th Jan we need to have satisfactorily contracted with min 8 contractors who are to deliver services on the day
  by 18th Jan we need to have approached staff by memo/flyer/e-mail
  by 1st March we need to have 150 NHS staff committed to attending on 21/3
  if by 7th March we have less than 150 staff signed up – further late marketing
  8. on 21st March we need to put on a really good, well attended event
  9. by 31st March we need to have collected/collated all feed-back
  10. by 10th April we need to have prepared and submitted our final report
  11. by 30th April we need to have closed-out the project, paid all contractors
‘If you don’t know where you are going
any road will take you there’
ANCIENT CHINESE PROVERB
here we consider what milestones will be most relevant to our FeelGood 2 project
AUTO SLIDE :
Please Wait
Notes: Setting the Project Milestones for FeelGood 2
In our scenario there are a number of key actions/activities that would represent significant project milestones.
Firstly we need to submit the project plan and recommend a course of action and seek a budget – so submission on or before the required date is clearly an important milestone
Next comes the 3rd January when we get to know if the proposal has been approved – and that a suitable budget has been agreed
Then – it is very important that the recruitment processes are successful in signing-up the minimum number of people for the event (target of 150 reached if possible) – otherwise further recruiting efforts are needed. So it is very important that the letters or e-mails go out in good time to catch people before their diaries are full with other things
Next the levels of responses to the invitations need to be carefully monitored – are they coming in at a rate that suggest the target of min 125 will be reached?
Another milestone will be when we reach the target of 150 people confirming their bookings – we are suggesting 1st March would be a suitable date by which this needs to have happened – enough time to organise remedial action if insufficient bookings are being made.
NEXT, delivery of the event itself – there are high expectations for this in terms of both variety and quality of ‘visitor experiences’ so we need to ensure we organise all the details and schedules to ensure this happens.
Another milestone will be the completion and collation of the feed-back that can then be analysed to assess how well the ‘end-users’ found the event. Did it make them ‘feel good’? And what worked well for them?
Then there is a key requirement for the project manager’s report to be prepared and sent to the client.
Finally all the bills need to be paid and loose ends tied up so that the project can be closed-out and the books and records closed on what we hope will have been a highly successful and well managed project.
.

## Slide 24: Programme & Project Management REVIEW
focus on outcomes:
  goals and objectives
  deliverables
  on time and within budget
project life cycle:
  define, plan, organise, execute, close-out
project definition: time, cost, quality, risk
  why do it? cost benefit analysis, feasibility study, GO v NO GO
project plan
  resources, schedules, costs
teams & team-working
time-precedence factors:
  network diagrams, GANTT/PERT charts
  deliverable breakdown structures
  work breakdown structures:
  work packages
milestones
critical path analysis
monitoring & reviews
close-out: hand-over
review
On Time
Within
Budget
AUTO SLIDE :
Please Wait
Notes: Review of Programme and Project Management
Here in our (almost!) final slide is a list of areas and items covered in this module.
We suggest that you re-visit those that are most relevant to you and your work, or those which, first time around, you found, perhaps, more difficult to understand.
If you have been on one of our workshops then don’t forget to keep referring to Hobbs’ Project Management guide, and also make good use of our downloadable project management tool-kit, both of which should prove useful as you continue to develop your project management knowledge and skills.
Thank you for using the PHeNet HealthKnowledge platform and for looking at this module – we hope you have found it useful!
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing, 1999.

## Slide 25: Research Sources
PROGRAMME & PROJECT MANAGEMENT : INTERMEDIATE MODULE
Key sources used for research for this presentation were:
Field M, Keller L.Project Management. Milton Keynes: Open University, 1998.
Hobbs, P. Project Management: The Essential Guide to Thinking and Working Smarter. London: Marshall Publishing,1999
Martin, Vivien : “Managing Projects in Health and Social Care”.
PRINCE web-site : http://www.ogc.gov.uk/prince/about_p2/about_intro.htm
Rodney Turner, J. The Handbook of Project-based Management. London: McGraw Hill, 1999.
Taylor J. The Project Management Workshop. Amacom, 2001.
KEY WORDS: project, project management, project-based management, project life cycle, budgets, budgeting, scheduling, deliverable breakdown structures, work breakdown structure, work packages, resource allocation, project management software, managing risk, project planning, assigning tasks, milestones, estimating time, teams and team-working, team motivation, monitoring and control, critical path analysis, reporting, stakeholders, project close-out, client, sponsor, time-precedence charts, GANTT charts, PERT charts, PRINCE 2, network diagrams
Notes: Research Sources For Project Management
In this module we have focused on the approach taken in the book Project Management: The Essential Guide to Thinking and Working Smarter by Peter Hobbs, which we recommend as a well-presented guide to the fundamentals of project management and to understanding some of its key features. It contains some excellent practical exercises that can be related to your own work area, your own projects and is also supported by a video which can be hired or purchased from Video Arts.
The book covers certain areas in considerably more depth than this brief introductory module and can be used to develop knowledge and application of the subject alongside the use of this module.
Important note: The Intellectual Property of the construction, design and presentation of this module, other than references to other works and materials which have been acknowledged within the texts, belongs to Martyn Laycock of the Knowledge College 2001-2005.
.

## Slide 26: The Classic Six-stage Project Management Model
Vivien Martin Pages 22-26
1.
D
E
F
I
N
E
6.
R
E
V
I
E
W
&
EXIT
2. P L A N
4.
C O N T R O L
3. T E A M B U I L D I N G
L E A D I N G & MOTIVATION
5. C O M M U N I C A T I O N S
Developed from Elbeik & Thomas, “Project Skills”, 1998
APPENDIX 1
Notes: APPENDIX 1 Classic Six-Stage Project Management Model
Here we offer a somewhat different approach to the so-called Project Life Cycle – this one developed from original work by Elbeik and Thomas in 1998, Vivien Martin, in her book Managing Projects in Health and Social Care, 2002.
Here we see the traditional phases : “Define”, “Plan” and “Review” but Martin argues that rather than a linear process, effective Programme and Project Management is an integrated process – with key strands “Communication” and “Team Building & Motivation” relevant right the way through a programme or project.
Certainly we agree with the emphasis on Communication and Team development : both in our view being critically important to effective programme and project management – the need for ongoing communication between the various types and groups of Stakeholders right the way through the project, from start to finish : equally the vital need for the development of effective team-working, again right throughout the project.
Also note Stage 4 “Control” is used by Martin to emphasise the importance of overall management and control throughout the whole programme/project process.
We believe this Model is a good, relevant up-to-date approach to managing programmes and projects in modern-day NHS environments.