## Slide 1: Introduction to Programme and Project Management Module
a module specially designed for HealthKnowledge
WRITTEN & DEVELOPED BY
MARTYN LAYCOCK MBA MCIM ACIB
e-learning
version
Additional information
Is provided in the Notes
sections
below each slide
NOTE
Many Slides in this
Presentation
load automatically.
Each such
Slide is marked
“Auto Slide
Please Wait”
Notes: WELCOME TO THIS INTRODUCTORY MODULE ON PROGRAMME & PROJECT MANAGEMENT
It has been designed to show you how useful the Programme & Project Management approach can be in the work environment. To some people it will represent a new approach; others will already be using it – many consciously, some almost unconsciously.
The component parts of Programme & Project Management are largely sensible, logical approaches to planning, implementing and managing work; they have been put together over the years to form a structured, disciplined approach to managing goal-specific and time-finite activities. The Programme & Project Management approach is designed to achieve greater focus on why particular “pieces” of work are carried out - and to introduce a more planned approach to how the work is scheduled and implemented. Programme and Project Management is driven primarily by results - or rather by goals, the attainment of goals. It is especially useful where specific “pieces of work” are organised to achieve particular goals.
WHAT IS THE DIFFERENCE BETWEEN PROGRAMMES AND PROJECTS?
For many years we spoke only of Project Management as a subject, as a discipline; it was largely about using particular approaches to handle one-off ‘pieces of work’. More recently as Project Management has grown in popularity and use, we began to use the word Programmes to describe series of projects that in some way link together to become “themed” programmes. For example building a bridge would be a project but building the bridge may well not be a ‘one-off’ but merely part of a larger ‘regeneration’ or ‘transport development’ programme. Today we often see organisations run ‘pilot’ projects, run these to find out if and how something works; then from that experience they will develop larger Programmes of linked projects based on the outcomes and experience they have gained in the ‘pilot project..
We offer this Module alongside an excellent “Guide to Project Management”, produced by Video Arts and written by Peter Hobbs and which is provided by the Authority to all staff members who complete our introductory Project Management workshop. It is also available in the Library. If you have this booklet we suggest that you keep it by you as you work through this Module. References are provided to key parts of this booklet throughout this Module.
IMPORTANT NOTE : Programme and Project Management can be as simple or as sophisticated as you or your organisation want it to be. But there are some core elements that you will need to understand, know how to use. It is the aim of this Learning Module to introduce you to the fundamentals of Programme and Project Management, show you how to they can be used, applied. More advanced techniques and applications are introduced in a separate Intermediate Module. There is also a Project Management Template that you can download from elsewhere on this Knowledge Platform; also a Project Management Tool-Kit which is also downloadable.

## Slide 2: An Introduction to Programme & Project Management
we will introduce you to these terms
within this Introductory module
SCOPE
COST
TIME
MILESTONES
BUDGETS
GOALS and
OBJECTIVES
PROJECT LIFE-CYCLES
SOFTWARE
QUALITY
CRITICAL PATH
£££
PLANNING/ MAPPING
Auto Slide : Please Wait
SCHEDULING
WORK
STREAMS
Notes: AN INTRODUCTION TO PROJECT MANAGEMENT
Here are some of the terms, tools and techniques that are used in and around Programme & Project Management. We will explain and explore them and many others in this Module. But let us make it clear, this is not an all-encompassing Manual covering all aspects of Programme & Project Management. It is intended as a simple straightforward introduction to the subject. Nor is it a technical module, heavy in jargon. Whilst there is a particular ‘vocabulary’ that is applied to the subject we have tried wherever possible to use simple everyday language to explain the key elements of Programme & Project Management (PPM). We have then suggested that the User turns to some of the recommended literature and materials in order to develop knowledge of the whole subject of PPM and its application in the work environment. NOTE : Still today many people refer to Project Management, rather than use the full title of Programme and Project Management and thus you will find that throughout this Module we refer either simply Project Management or, occasionally, ‘PPM’
There are many Programme and Project Management courses that you can undertake once you have a grasp of the basics, once you understand how ‘PPM’ might be applied in your organisation, your work area.
Within the material provided in this Module there also lies the opportunity for Departmental and Functional heads to consider whether there might be a Programme & Project Management “platform” that they could introduce that would lead to overall improvements in efficiency and effectiveness in the management of work generally within the department, function or across the whole organisation
Our Agenda (Slide 3) sets out the key areas that we will look at in this Module. In the Final Slide in Part III we have shown the main Sources we have used to prepare this Module; most of these are books, available from most good booksellers and business libraries but we have also listed CD-Roms and other material that we use in our courses and workshops.
IMPORTANT NOTE : Don’t be put-off by the seemingly heavily-structured approach advocated by many Project Management “systems”. All of them have their value in particular circumstances; an application of some of the fundamentals of PPM will help most people improve their handling of, and involvement in, programmes and projects – help build a platform for a more thorough approach to programmes and projects and their management in the future.

## Slide 3: Programme & Project Management AGENDA
what is Programme & Project Management (PPM) ?
why use it ?
what are the benefits ?
key features of programme and project management
how to use it : some tips, tools and techniques
practical work-related activities
developing the “PPM” approach
taking PPM forward in the organisation
an initial Programme & Project Management Tool-kit
Auto Slide : Please Wait
Notes: AGENDA for PROJECT MANAGEMENT INTRODUCTORY MODULE
This is our Agenda designed to Introduce and explain Programme & Project Management (PPM) :
We will cover the key features of PPM and look carefully at the benefits of using it in the work environment,
We will present you with a number of tools and techniques that are key components of PPM and offer some tips as to how to use them to manage programmes and projects effectively.
We will use a specially developed Project (a real-life ‘scenario’) to guide us through the key practical applications of PPM, show how this important group of management skills and disciplines can be applied across the organisation to help achieve greater focus on results, attain improved effectiveness and overall efficiency in the handling of ‘pieces’ or ‘programmes’ of work..
If you have attended one of our Programme & Project Management workshops you will also have a Project Management Tool-Kit plus perhaps a copy of the Video Arts book “Project Management – An Essential Guide”, authored by peter Hobbs which amplifies and expands a number of the subjects covered herein.
The Tool-Kit can be downloaded from this Knowledge Platform and the book is available in our Library.

## Slide 4: What are Programmes and Projects?
Hadrian’s
Wall
First Apollo
Moon landing
Harrow PCT Annual Public Health Report
Ceiling of
Sistine Chapel
The Development
of VIAGRA
The Films :
“Lord of
The Rings”
WHAT ARE THE
KEY FEATURES
OF
PROGRAMMES
& PROJECTS?
“Heartbete”
Promotion
REMINDER :
there are Notes below
See next Slide
Auto Slide :
Please Wait
The items in BLUE boxes are examples of “Projects”, those in PURPLE are projects that formed part of larger “Programmes”
The
Millennium
‘Dome’
North Greenwich
Underground Station
Australia’s 5-year $1bn
support programme to
Indonesia (re Tsunami)
Notes: EXAMPLES OF PROGRAMMES & PROJECTS :
We show here some examples of Projects and also illustrate key differences between ‘projects’ and ‘programmes’. Some examples (in the Blue boxes) are world-renowned projects from very different eras - but note also, much closer to ‘home’, Harrow PCT’s ‘Annual Report on Public Health’ and also their “HeartBete Campaign”, a health promotion project that focussed on Diabetes and Coronary Heart Disease. Both of these are projects (the first obviously an ‘annual’ one) within the Public Health areas of the National Health Service. NOTE : The film trilogy “Lord of the Rings” is included because films are excellent examples of projects and the use of Project Management : typically they use a myriad of resources (actors, technicians, scenery-makers, various ‘properties’ – ‘props’) that are covered by an overall Budget and are generally tightly scheduled to be completed within a particular period of time. This particular trilogy of films also helps us to explain the key difference between projects and programmes:
The Differences between Projects and Programmes :
Basically a ‘programme’ is a series or group of related ‘projects’ that are managed together as a ‘portfolio’. In our Slide we have included the renowned first Apollo Moon Landing : most people will either know or recall that man’s first landing on the moon by Neil Armstrong and Buzz Aldrin was a particular project or mission that formed part of a major space and lunar exploration programme, the Apollo programme.
The well-known Millennium Dome and also the adjacent North Greenwich London Underground Station were both major ‘projects’ that formed part of a large regeneration ‘programme’ for the Greenwich Peninsula in south-east London. The new North Greenwich station itself formed part of a major London Underground extension ‘programme’ (“The Jubilee Line Extension).
In the film-world we have an excellent recent example of separate projects that formed parts of a larger programme; the trilogy of recent films in the series “Lord of the Rings” were parts of a whole ‘programme’ of films that together presented the captivating stories in JRR Tolkien’s famous book “The Lord of the Rings”.
We also show above a very recent example, this one related to the very sad impacts of the Boxing Day, 2004, Tsunami that caused such devastation and claimed over 150,000 lives in countries around the Indian Ocean and in East Africa. As just one example, Australia is, as part of massive world aid programmes, providing a 5-year $1bn disaster recovery programme to its neighbour Indonesia, which will take the form of many component projects that will be developed and delivered within an overall programme over the next five years.
“a Programme is a collection of projects and other items of work that are managed together as a portfolio”
Department for Education & Skills ‘PPM’ website : http://www.dfes.gov.uk/ppm/
‘Programmes’ can be very large and last over many years. ‘Projects’, whilst they may simply be components of larger programmes, can themselves be large or small, short or long, last just a few weeks or months or, in some cases take several years. See next Slide for more detail on Projects, Slide 6 for more on Programmes.

## Slide 5: a ‘Project’ is…...
a unique “venture” or “piece of work”
set up to achieve a particular objective or goal
  has defined outcomes;
    qualitative as well as quantitative
typically carried out for a “client”
has a beginning and an end (i.e. is “time limited”)
uses defined resources :
  People
  Money
  Equipment
typically use “milestones”
typically has a single point/person of responsibility
uses teams and team-work
the Goals are defined and the project is finite
Auto Slide
Please Wait
Notes: WHAT IS A PROJECT ?
These characteristics of “projects” are taken from a variety of definitions but to summarise here is the Open University Project Management book’s hybrid definition :
A PROJECT is an organised piece of work towards a pre-defined goal or objective that requires resources and effort, a unique venture having its own budget and time-scale (schedule). A Project’s success can be measured in terms of how closely it comes to achieving its goal/objectives (including the qualitative as well as quantitative aspects), within the parameters of its budget and schedule. Once a project is “closed-out” (completed), it ceases.
Thus it can be seen that Projects are finite (time-limited) - but, that said, they can last, as we have said, from a few weeks (sometimes just a few hours!) to several (sometimes many!) years - but the benefits of successfully completed projects typically live on, sometimes for short periods of time, sometimes for many, many years.
One of several key features of Project Management is the use of ‘milestones’ : these will be explained in more detail later but essentially they represent key points in Projects when key activities - or groups of activities - get completed. Another key feature is the use of teams and team-working, people and people’s time often being key resources utilised in completing the project.
EXAMPLES : We have shown some examples of Projects on the previous slide; here are some examples of specific “pieces of work” that would benefit from the Project Management approach :
* Harrow’ PCT’s “HeartBete” campaign, designed to raise public awareness about diabetes and coronary heart disease – a health promotion campaign that used local publicity and a series of 8 “road shows” in the area
* Development of a multi-media CD-Rom and linked Web-Site to support people who will be involved in a major Change Management programme
NOTE: whilst projects are finite (time limited) their “products” (deliverables) and the benefits thereof frequently “live on” - the end users continue to enjoy the benefits (e.g those who visit the Sistine Chapel, those who go to see – or watch on Video – the Lord of the Rings film) or (as is the case with the Apollo Moon Landing) they continue to benefit from the knowledge and experience that the project provides.

## Slide 6: a ‘Programme’ is…...
a unique series of linked “ventures” or “pieces of work”
  e.g a major long-term strategic organisational change programme
set up to achieve particular overall goals and objectives
  has defined outcomes; qualitative as well as quantitative
typically carried out for a “client”
has a beginning and an end (i.e. is “time limited”)
typically longer and more ‘flexible’ than Projects
uses defined resources : : People : Money : Equipment
typically use “milestones”
typically has a single point/group of people who carry responsibility
uses teams and team-work
Auto Slide
Please Wait
A Programme is a collection of projects and
other items of work that are managed together as a portfolio
DFES PPM website : http://www.dfes.gov.uk/ppm/
Notes: WHAT IS A PROGRAMME?
Above we have described some of the key characteristics of Programmes; many you will note are the same as, or similar to, those of Projects. However, the essential difference between the two is that programmes are linked series of projects that, as the DFES definition shown above tells us, are managed together as a portfolio. Thus programmes are typically bigger, last longer and are more complex than projects.
The DFES web-site by the way is well worth a visit; it contains useful insights into how projects and programmes are managed in organisations.

## Slide 7: Programme & Project Management is….
MANAGEMENT
RESOURCES
the three points of
the triangle show the three key factors relevant to
Programme & Project Management
“planning, gathering and managing the resources needed to achieve particular Goals and Objectives within defined time and budgetary constraints”
but effective PPM also
equires the effective
deployment of……..
QUALITY
TIME
COST
Auto Slide :
Please Wait
Notes: THE MAIN ELEMENTS OF PROGRAMMES & PROJECTS:
Here we take an initial look at the key elements that together comprise Programme & Project Management. First we give a definition which we believe is self-explanatory : particular goals and objectives are set at the outset and these then determine how long the programme or project will need to run for, and how much it will cost. We use a triangle to illustrate the three fundamentals of programmes and projects : financial cost, time and quality. Most people understand the financial and time dimensions – we always talk about bringing projects, particularly, in “on time” and “within budget” - but perhaps don’t quite so readily recognise the importance of Quality in the equation :
The quality standards to which a programme or project is to be delivered will impact on both the cost and the time taken to complete it e.g: a bridge or a new building needs to be built to certain safety and quality specifications; these will of course impact on the cost of the project – the materials required, the robustness of the foundations and the structure – which in turn will impact upon both the cost and the time required to complete such a project. If the bridge or building forms part of a larger development programme – e.g. a major regeneration programme then the same parameters will apply to the whole programme as well as the projects within it
Key elements of cost are of course the resources that are needed to deliver a project : the people (the main people costs being wages of course, but also insurance, travel costs and the like), the equipment, the materials, perhaps also property (e.g. the office space where the project is to be run from, where the Programme or Project Team are to be based etc).
Beyond this the programme or project’s management will be of critical importance – the Project or Programme Manager and his/her team will need to manage the programme or project to achieve particular quality standards, particular specifications, in order to ensure that the programme/project is delivered on time as well as within budget.
Take as an example the already mentioned “HeartBete” campaign to raise awareness in Harrow about diabetes and coronary heart disease. This was a relatively short, high-impact health promotion project that featured press and publicity and a series of 8 “road-shows” where members of the public could come and have their BMI (Body Mass Index) assessed and also receive helpful information about diet and exercise etc. That project ran for a particular period of time– but required quite a lot of pre-planning as to the activities, the locations and who would carry out the road shows, do the “assessments etc. The HeartBete Project Manager needed to plan the whole initiative, obtain and organise the resources – including inputs from other people, arrange suitable locations, write and distribute press and publicity materials etc. Each road-show then needed to be marketed and promoted so as to ensure as many people as possible knew about the events and locations and were encouraged to come along. It is likely that some target numbers would have been agreed at the outset, the numbers of people, particularly in high risk categories who would come along, have their BMIs measured, take away information about diabetes and CHD. As is typical in projects, when all elements and aspects of the campaign were completed an assessment was made as to the impact it had made overall.

## Slide 8: Key Features of Programme & Project Management
very strong focus on Results (“outcomes” “Goals”)
positive and effective time management
  good scheduling
positive and effective management of resources
  People
  Equipment
  Property
  MONEY !
strict scheduling + the use of “milestones”
good budgeting
frequently uses team-work
Good
Team-Work
is a key to
Good
Project
Management
Auto Slide
Please Wait
SUMMARY
SLIDE
Notes: SUMMARY : KEY FEATURES OF PROGRAMME & PROJECT MANAGEMENT:
Before moving on to more complex aspects of Project Management, we give in this Slide, an overall summary of the key features and characteristics that apply to virtually all projects, large or small :
  * Typically they are, as we have said, “goal-driven” and “finite” (time-limited)
  * They require sound, positive “hands-on” management –
    - management of people, of time, of property and/or equipment, of money
  * Budgeting is an essential requirement
  * Scheduling of tasks and activities is a key requirement
  * Milestones are used to mark key points within the project and are an important part of the review/progress-checking procedures
  * Finally, teams and team-work are frequently features of good project management :
    - people work together to “pool” their skills, abilities, experience to ensure that the project is delivered within budget, on time - and to the required quality standards.
On the next couple of slides we take a look at some of the people - and “players” - typically involved in Projects. First let’s do some more practical work……… (next slide)

## Slide 9: Using Programme and Project Management in Organisations
Many programmes and projects take place in business environments but increasingly they are being used in:
  Charities
  Sport (events etc. e.g. The Olympics)
  Universities (research or out-reach work)
  Engineering (e.g bridges/power stations)
  Local authorities (best value etc)
  Healthcare (change and NSF activities)
  Even in the home e.g new rockery or conservatory, a holiday etc
The benefits of an Organisational approach:
  better focus on Outcomes
  one approach/system applies right across the department, division or whole company
  people can move from project to project or be a player in two or more and use same system
  a Programme & Project Management culture is developed
  attractive cost savings can be made over a period of time
there are efficiency and productivity gains available to organisations
that can successfully harness the Programme & Project Management concept
Auto Slide : Please Wait
Notes: GETTING THE BEST OUT OF PROGRAMME & PROJECT MANAGEMENT
Before we explore in more detail some of the tools and techniques that are used in Programme and Project Management, let us first consider how best it can be used in organisations. We have said that PPM is designed to help manage discrete, defined “pieces of work” – or, in the case of programmes, series of pieces of work - that have a finite term and have clearly identified, deliverable “goals”. If an organisation has quite a lot of such ”pieces of work” then it is quite likely that they can realise the benefits of Programme & Project Management by implementing an organisation-wide approach to it. In fact, today, organisations with relatively few “projects” are finding that PPM can help them to handle ‘pieces of work’ more efficiently, more effectively.
Where a PPM approach is adopted across an organisation then it can prove very valuable to have everyone using the same, or very similar, approach, systems and processes; doing this means individuals can be involved in, for instance, more than one project, or can move from project to project, without having to learn a variety of different systems, methods and procedures.
Many organisations that have adopted Programme & Project Management have been pleased with the outcomes, saying that it not only improves the “focus on results” but also tends to bring improved productivity and cost-savings over a period of time. It is not only the organisations but also the individuals in them that can realise the benefits of PPM; often the whole organisation goes through a positive “learning curve” based upon the use of PPM (see Hobbs Pages 86-89) This said, though, the outcomes will very much depend on the quality of the Programme & Project Management, including the training that staff are given, the way projects are actually managed, the effectiveness with which programme & project management tools and techniques are deployed.
PPM techniques can be applied to many aspects of activity within organisations: e.g. New Product Development, Events and Product Launches, longer-term strategic Organisational Change programmes and new Information Technology projects and programmes (to name but a few).

## Slide 10: Practical 1
Who are the potential
STAKEHOLDERS
in a
PROGRAMME or PROJECT?
Please refer to the Notes pages
for additional information on all slides
This is our first of several Practicals in this Module
Notes: STAKEHOLDERS
“Stakeholders” in Projects or Programmes are people and/or organisations who have an Interest (a “stake” or “role to play”) in them. Stakeholder types can be many and numerous.
We ask you to think about a recent Programme or Project that you have been involved in - and try to think of all the various people and organisations who had a sizeable “stake” in it (include key people internally such as the Project Manager and/or Project Director, Finance and Marketing people, Administrators etc together with any ‘externals’ who were also involved.
List down the Stakeholders before you move to the next Slide; grouping them as ‘internal’ (to your organisation) and external (e.g contractors, suppliers, consultants etc)
Typically you will find there are between 6 and 10 types of Stakeholders in programmes and projects – these we explain in the next Slide………..

## Slide 11: Players & Roles in and around Programmes & Projects
CLIENT (initiates it and often pays for, or “underwrites” it)
SPONSOR (person or organisation who supports, co-finances it)
END USERS (the people who use/enjoy the Outcomes, get benefit)
PROGRAMME/PROJECT DIRECTOR
PROGRAMME/PROJECT MANAGER
PROGRAMME/PROJECT CO-ORDINATOR
QUALITY ASSURANCE MANAGER
FINANCE MANAGER
PROJECT TEAM :
  Internals
  Externals
  Contractors, Specialists
PROJECT ‘STEERING/WORKING/ADVISORY’ GROUPS
It very much depends on the type and complexity of a Project as to what level and degree of management is used
- and what, if any, functional (e.g finance or quality) resource is utilised
AUTO SLIDE :
Please Wait
Notes: PEOPLE & PLAYERS in PROJECT MANAGEMENT
If you haven’t already looked at the previous Slide its worth doing so, and completing the practical exercise before continuing with this Slide.
Let’s now look at the types of Stakeholders that typically are found in ’projects’. Firstly there is almost always an identifiable “Client” – the person or organisation who initiates a Project. In the movies this might be Universal Studios; in the “Heartbete” example it was the Harrow Primary Care Trust . Typically Clients set the overall goals (the deliverables, the quality parameters and the overall budgets), but these are then normally finally agreed in detailed discussion with the Project Director/Manager or Project Co-ordinator (see below). Some projects also depend upon Sponsors – people or organisations who are brought in to co-fund or co-produce the Project. In the film-world this could be a specialist film-financing organisation (who will share in the success of otherwise of the finished film): for Heartbete it could be a charity e.g British Heart Foundation. Sponsors often share the Risk of carrying out the project – they share the cost of “doing” the project and/or they enjoy certain benefits based on, or flowing from, its success.
It is very useful when considering Projects to think about the “End-Users” – the people who receive the benefits of the Project e.g : the cinema goers who pay their entrance money to see (hopefully enjoy) the film, or the people who attended any of the HeartBete events and received information and advice on how to avoid diabetes or coronary heart disease.
A BIG project will typically have a Director who will have overall responsibility for delivery – and who may well hire a specific Project Manager (or even a whole Project Management Team). Smaller projects may simply use a Project Co-ordinator – someone whose responsibility it is to manage and co-ordinate the resources to deliver the project. As Quality and Cost are important larger projects may well have specialist Quality Assurance and Finance managers, who may work either full-time or part-time on the project depending on the size, scale and overall deliverables. Also, dependant upon the size and scale of the project, there will be either part-time and/or full-time people appointed or hired into the Project Team; these may be a “mix” of “internals” (people from within the organisation that is carrying out or managing the project) and “externals” (typically specialists and contractors who are brought in to deliver specific areas and pieces of work e.g publicity, design, presentational material).
Finally, many larger Projects, especially those that depend on public or part-public funding and involve relatively high levels of accountability, use a Project Steering Group, a group of key people representing “stakeholders” in the project who meet with the Project Director/Manager at agreed intervals to discuss progress and problems.

## Slide 12: Programmes, Projects & Priorities
today many people are involved in Programmes and Projects
- as managers, team members, “players” -
alongside their everyday tasks and responsibilities
Reactive Proactive
URGENCY
High
Low
I
M
P
O
R
T
A
N
C
E
MODEL : Peter Hobbs
“Project Management”
Projects are High
Importance, Planned,
Pro-Active activities
let’s see where Programmes & Projects “fit” alongside other types of work….
High
Low
Auto Slide :
Please Wait
Notes: PLANNING AND PRIORITISING TASKS AND ACTIVITIES :
Here we take a look at perhaps one of the most useful Tools that help us to understand the relevance and importance of projects; it can be an especially useful tool in organisations that are just turning, or about to turn, to Project Management as a way of handling, organisationally, particular “pieces of work” using Programme & Project Management principles.
This 4-box matrix can be especially useful in analysing the effective use of time and the prioritisation of activities : It can be used by individuals and also by project teams undertaking Project Management.
The matrix looks at the relative Importance versus the Urgency of Tasks and Activities to help us examine those that are Re-Active as opposed to Pro-Active. On the horizontal axis (see the foot of the matrix) we have the URGENCY of the activity; the left-hand column = High Urgency; right-hand column = Low Urgency. On the vertical axis we record the Importance of the activity; Upper boxes include High importance activities, lower boxes Low importance activities. Placing Tasks and Activities in the relevant “boxes” helps us determine (see the top of the matrix) whether these are RE-ACTIVE (left-hand column) activities (where we are responding to something that has already happened) or PRO-ACTIVE (right hand column) activities (where the focus is on things and matters ahead)……….
PROJECTS are typically pro-active (fundamentally about planning, scheduling) and are usually of HIGH importance (that’s primarily why they become Projects!) - so they belong in the Top-Right Hand box. (See next Slide to see how we can use this simple analysis tool)

## Slide 13: Programmes, Projects & Priorities II
the key is to differentiate between tasks and activities that are Re-Active and those that are Pro-Active
Reactive Proactive
High Low
URGENCY
High
Low
I
M
P
O
R
T
A
N
C
E
Development
Tasks
Projects
Distractions
Maintenance
Tasks
MODEL : Peter Hobbs
“Project Management”
Programmes & Projects are
High Importance, Planned,
Pro-Active activities
CRISES
Fleeting
Opportunities
REMINDER :
there are Notes
appended below
Auto Slide :
Please Wait
Notes: RE-ACTIVE AND PRO-ACTIVE ACTIVITIES
Here we show the different types of Tasks and Activities and where they “fit” within the 4-box Matrix. The key of course is to differentiate between the Re-Active and the Pro-Active tasks and to think then about how different types of tasks and activities can be prioritised and accommodated to improve overall efficiency and, particularly, effectiveness.
NOTES :
* Development activities and PROGRAMMES & PROJECTS are, as we have said, typically placed in the top-right box : they are of High importance, planned (and therefore Pro-Active) and relatively Low urgency
* Crises are matters of High importance, High urgency where we are in Re-active, not Pro-active mode
* “Fleeting Opportunities” are worth considering; these arise from time-to-time and need to be accommodated; they are certainly Re-active, typically Urgent and of relatively High importance
* Beware of “Distractions” - re-active things of relatively low-importance (e.g routine telephone calls) that are allowed to get in the way of more important, longer-term matters.
* “Maintenance Tasks” are of Low urgency and Low importance – but they DO need to be scheduled in - otherwise eventually they eventually become High Urgency, Re-Active tasks because they begin to “block” other, normally more important, activities
Understand and use this little Model and, whether you are heavily involved in projects or not, you should, by using it, find it a little easier to plan your work, manage your time in the future.
In the next Slide we invite you to do a piece of practical work that will help you to achieve this Goal!

## Slide 14: Planning & Priorities
H0W TO COMPLETE YOUR SELF-ASSESSMENT
Firstly, record your activities and the time they take in the course of a typical working day or week
Then plot them on the four-box matrix, allocating each activity to one of the quadrants, according to its urgency and importance
Then calculate what percentage of your time was spent in each quadrant
Add the percentages in H1 and L1 to calculate your personal “Re-activity Quotient”
Then consider how you might re-organise your work to achieve greater efficiency
H1
H2
L1
L2
Reactive Proactive
High Low
URGENCY
High
Low
I
M
P
O
R
T
A
N
C
E
MODEL : Peter Hobbs
“Project Management”
PRACTICAL 2
SELF-ASSESSMENT EXERCISE
See the “Notes”
section below
Auto Slide :
Please Wait
Notes: A PRACTICAL SELF-ASSESSMENT EXERCISE
Let us now re-visit the four-box matrix and use it to analyse our own activities. Many people, whether or not they are to be involved in projects, find this tool very useful. It helps them to “stand back” and to analyse how they spend their working time; it can help to prioritise tasks and activities; it encourages an altogether more planned and disciplined approach to work.
In particular this “exercise” can have potentially enormous benefits for those who are, or are about to be, involved in Projects - where planning, scheduling and prioritisation are key features. Naturally, different jobs will involve different levels of re-activity/pro-activity : a telephonist or a Help-Desk operator will obviously be more involved with re-active tasks and activities than, say, a researcher or a product development manager. However whatever the primary job/tasks it can still be valuable for people to carry out this exercise.
THE “PLANNING & PRIORITIES” EXERCISE
Peter Hobbs in “Project Management” (refer pages 11/12) says that “getting a correct balance across the four quadrants is central to good time management”. Work your way through the instructions in the right-hand panel and examine the time you spend in each quadrant; then look particularly at the “relativities” – the proportions of time spent on Re-active (left-hand boxes, H1, L1) v Pro-Active (right-hand boxes, H2, L2) activities. Use Peter Hobbs book, Page 12, to calculate your own “Reactivity Quotient” – calculated by adding the percentages of time spent in the “high-urgency” (H1 and L1) quadrants. This sounds complicated at first but its worth following it through because the outcomes can be very enlightening. EXAMPLE : If your “reactivity quotient” is 75% then a task requiring just two hours of time to complete could in fact take eight hours to complete! That’s because your re-active tasks will get in the way. You need to know this if you are to understand how work can be more efficiently and effectively organised in the future. Discuss the outcomes and the logic of this Exercise with colleagues to realise its significance and possible impact on the way you organise your work.
How can you improve the planning and organisation of your work to improve things ?
Think about this question and if necessary discuss with your line and or project manager(s) how you may be able to improve things ?
USEFUL TIP : schedule regular “blocks” of time for pro-active and project work where you do not allow yourself to be interrupted by re-active tasks; allocate specific tasks and activities to these blocks of “pro-active” time and you should find you’ll start to realise some of the key benefits of “project management”:

## Slide 15: Practical 3.
Think of a programme or project that you are (or have been) involved with :consider it against the typical features of a Project by answering the following questions:
CLIENT? :
GOALs? : Quantitative :
Qualitative :
TIME-FRAME? :
WHAT MILESTONES WERE THERE?
WHAT IS/WAS THE PRIMARY DRIVER :
time ? cost ? quality ?
WHAT RESOURCES were used ? :
money : people :
equipment : time :
Refer to Notes
section below
to read full
details of this
Practical
Auto Slide :
Please Wait
Notes: ACTIVITY TIME !
Think carefully about a “Project” that you are or have recently been, involved in; you might have been the Project Manager or simply a member of the project team. (It may not have been called a “Project” but it should have had clear objectives and a clear time-frame.)
  Who was the CLIENT ? Was there a “SPONSOR”?
  What were the GOALS (the deliverables) ? ;
    - were there “numbers” involved (e.g get 100 paying delegates to attend an Event) ?
    - were there also Qualitative Goals – e.g to very high standards of venue, speakers etc ?
  What was the Time-Frame ? START : FINISH :
  Were there “MILESTONES” involved (achievement of particular things by particular times on the way to full and final Delivery of the “project”)? If so state examples :
  Can you identify the “PRIMARY DRIVER” of the project? Was it to deliver by a particular TIME,or was COST the over-riding factor? Or did QUALITY dominate over the other factors ?
FINALLY : what RESOURCES were involved in delivering the “project” :
MONEY : PEOPLE : EQUIPMENT : TIME :
TIPs :
If you find difficulty in identifying a “project” for this practical exercise, talk to colleagues and see if you can work usefully with one of them, share their experience on a Project. Try to discuss your findings in this exercise with other colleagues, try to convince them about the answers you have generated. Listen to any comments, suggestions they make. This is a very useful way to learn.

## Slide 16: Programme & Project Management : key features : SUMMARY
Client
Sponsor
Aims, Goals and Objectives
Project Life-Cycle
Scoping Document : Risk Assessment : Cost–Benefit-Analysis
Project Plan :
  Resources : Activities : Financial : Schedules : Critical Path Analysis
Deliverables
Work Breakdown Structure : Work Packages :
Milestones
Communication and Reporting
Implementation and Monitoring
Close-out
Review
The items in BLUE we have already considered, those in RED and in GREEN we will consider in the
Slides that follow
Now for our practical
“Scenario” that links
the remainder of our
Module. …
Auto Slide :
Please Wait
Notes: REVIEW OF KEY FEATURES OF PROGRAMME & PROJECT MANAGEMENT
To Progress our thinking on Programmes & Projects we have listed in the Slide the key features of Project Management systems:
Those in blue we have covered.
Those in red and in green we will cover in the remaining Slides in this Module……… those in green in some in detail, the others (red) in outline, ready to cover them in more detail in our Intermediate Module.

## Slide 17: Introducing………. Project-within-a-Project
please refer to the “Scenario” detailed in the “Notes” section below; print it off for ease of access and make any relevant notes as you read it
we will then use the Scenario as we move through the rest of this Module
if you have had recent programme or project experience you might like to make notes about your experiences within that programme or project as we move along
TOOLS TO USE :
PROJECT-WITHIN-A-PROJECT “SCENARIO”
WORK-BOOK
work book
DOWNLOADABLE
Auto Slide :
Please Wait
Notes: SCENARIO: DATE : 1ST MAY 2001 :
“The Project Management Project” : The Chief Executive (CE) has tasked a manager with developing and delivering a programme of Workshops, designed to introduce managers and key staff to the principles of Project Management; as a means of handling particular “pieces of work” which have defined time-scales and own budgets. The CE believes that there are quite a lot of potential Projects that could benefit from the “project management approach” including some change-management programmes starting later in the year. She also feels that this may provide a “platform” for the organisation to develop its own in-house Project Management ‘system’ – a framework that helps people set up and manage projects on an efficient and effective basis that is used across the organisation. Whilst the CE is supportive of formal Project Management training ( e.g. Prince) she feels that staff should be introduced to the Project Management concept through 1/2 day introductory workshops. These will be supported by take-away PowerPoint presentation, a write-in Work-Book and - an innovation - a Project Management “Tool-Kit”.
Through discussion it has been agreed that there will be a pilot workshop (which will be run twice) designed to attract a minimum of 18 and a maximum of 25 key staff at each workshop. Due to a lack of Internal resources an external consultant will be commissioned. Delivery and assessment of these two Workshops will effectively be a “Pilot” project and be used to assess whether further workshops and project management training will be run in the future. For operational reasons these pilot workshops will be held in late July and late September.
There will be a cash budget of < £3,500 for the Pilot phase to cover external consultant, materials development and printing and a suitable venue for each of the two ½ day Workshops . Staff time and indirect costs are estimated as follows :
  CE : 1 day over the whole project (£300 per day) £300
  Manager : 6 days over the whole project (@ £175 per day) £1,050
  Secretary/Admin : 5 days over the whole project (@£90 per day) £450
A small Working Group will be set up (comprising CE, Project Manager External Consultant and the Administrator) and meet monthly to review progress/problems
Feed-back from workshop delegates, from the Contractor and other stakeholders will be collated, summarised and reported back to CE by 30th September. Based on the key performance indicators and feed-back the Working Group will decide whether to recommend further Project Management workshops and training at a meeting scheduled for 1st October. At this stage this project will close.
If further workshops are recommended they will take the form of a new Project or longer-term Programme..

## Slide 18: The Project-within-a-Project
Using the Scenario provided to answer the following Questions :
  Who are the Stakeholders ?
  Who is the Client ?
  Who are the End-users ?
  Is it “time limited” ?
  Is there a Budget ?
We’ll use this Scenario as we work through the rest of this Module ………
QUESTION-TIME !
See Notes section below for full details
Auto Slide :
Please Wait
work book
Notes: The Project-Management project
Having read our “Scenario” (previous Slide) we now invite you to note your answers to these questions:
Who are the Stakeholders ?
Who is the Client ?
Who are the End-users ?
Is it “time limited” ? If so, to when ?
Is there a Budget ? If so, what is the Budget ?
We are going to use this Scenario now as we move though the rest of this Module.
If you have a project which you are currently involved in then we invite you to think about that project and apply the same questions, and to note your answers.
Don’t forget : there is a down-loadable Project Management Template available elsewhere on this platform.
Now we’ll look at another very useful Project Management tool : what we call the Project Life Cycle………

## Slide 19: Project Life Cycle
PLANNING
PHASE
tasks
sequencing
milestones
estimating
Budgeting
PROJECT
PLAN
S
T
A
R
T
I
U
P
PLAN
2.
EXECUTE
4.
ORGANISE
3.
R
E
V
I
E
W
CLOSE
-OUT
5.
{Implementation Phase}
The PROJECT PLAN is
highly important; it is used
to drive, steer and manage the
project through Phases 3, 4 and 5
FEASABILITY
PHASE
-sometimes
called “scoping-”
-risk is assessed
-feasibility tested
“GO” or “NO GO”
decision made.
If “GO” 
DEFINE
1.
“GO”
“NO-GO”
Auto Slide :
Please Wait
Notes: A LOOK AT THE PROJECT LIFE CYCLE :
We use this Model because a thorough understanding of how Projects normally evolve and develop can be invaluable both to Project Managers and those in Project Teams. Here we show the “cycle” in linear fashion, with a clear start (Start-Up) and end (Review). Please note that the phases are not in practice wholly separate; typically they overlap somewhat. In the boxes below each Phase we have given a name to that phase and shown the kinds of activity likely to be going on during each.
PHASE 1: DEFINITION: This Phase covers “scoping” (clearly identifying what you want to achieve, by when and within what constraints) and, often, a Feasibility Study (including a Risk Assessment and Cost Benefit Analysis) to establish whether the project should go ahead or not. NOTE: Some Projects - often called “Top-Down” projects - are “pre-screened” by the Client/Sponsor (meaning the Feasibility Study has already been carried out and a decision to proceed with the project already made). In such cases the project is passed to the Project Manager or co-ordinator on a “ready to roll” basis. Even in these cases, though the Project Manager or Supervisor will still need to ”scope” or “define” the project, this being a key part of overall project management. (Hobbs: Pgs 24-27)
PHASE 2: PLANNING: The importance of this Phase simply cannot be overstated : good work done here will help ensure that the project runs well and that the Goals and Objectives are achieved. To some extent the Planning phase repeats some of the “scoping” aspects in Phase 1 but in this stage the Plan adds detail; it plots, particularly, the timing and cost requirements. The resourcing of the project, the costs, the tasks and activities and their sequencing are all included in the overall PROJECT PLAN that is the major “output” from this Phase. The key thing then is to ensure that the Project Plan is used to steer and manage the Project through the remaining Phases :
NOTE : The next two Phases are often grouped together and called the Implementation Phase but we prefer to show each Phase separately because the activities within each Phase, although linked, are quite different……… (next Slide)

## Slide 20: Project Life Cycle II
CLOSE
-OUT
EXECUTE
ORGANISE
PLAN
DEFINE
FEASABILITY
PHASE
-sometimes
called “scoping-”
-risk is assessed
-feasibility tested
“GO” or “NO GO”
decision made.
If “GO” 
PLANNING
PHASE
tasks
sequencing
milestones
estimating
budgeting
PROJECT
PLAN
ORGANISING
PHASE
-resources
-tools
-reviews
-reporting
-communications
EXECUTION
PHASE
activities
monitoring :
costs
progress
controlling
quality
COMPLETION
PHASE
client “hand-over (= acceptance)
complete the documentation.
review : sign off
post implementation audit
maintenance
“value assessment”
R
E
V
I
E
W
1.
2.
4.
3.
5.
S
T
A
R
T
I
U
P
{Implementation Phase}
Auto Slide :
Please Wait
Notes: THE PROJECT LIFE CYCLE : PHASES 3, 4 AND 5
PHASE 3 : ORGANISING In this Phase the Project Manager marshals and organises all the various resources that will be required to carry out the project in accordance with the Project Plan. This is still largely a process of “organising” rather than “acting” - a bit like “packing” and getting all your documents (tickets, passports, currency etc) ready and together before you set out for a foreign holiday.
PHASE 4 : EXECUTION PHASE : This really IS the “active“ phase; it is the process of implementation that follows a lot of planning and organising that has already taken place. In this Phase the Project Team work through the various project activities in accordance with the project Schedules and Budgets contained within the Project Plan.
NOTE : The Project Life-Cycle depicted in Hobbs’ Guide to Project Management is slightly different from that shown here; Hobbs combines Phases 3 & 4, calls them “Implementation” and then adds a final phase - that of Review (which equates to our “Close-Out”).
PHASE 5 : CLOSE-OUT : There are a number of activities that typically take place in this Phase : all the activities are completed so as to enable delivery of the project to the Client. The “hand-over” process involves delivering the Project Goals and Objectives to the Client - and, in many cases, also to the “end-users”. Then typically there is a Final Review that establishes how well the project has run, looks at what has gone well and what has gone not so well. This Review might typically include a “Post Implementation Audit” and an overall “Value Assessment” - these will be covered in detail in an Intermediate Module. The key thing is that the Project Manager and Team learn from the experience - they identify key areas for application and incorporation into future projects. It is important that this learning – the “project experience” is formally recorded; in this way organisations can accumulate Programme and Project Management knowledge, use it to build strong PPM principles into the way they run things in the future. ……..

## Slide 21: PHASE 1: Project Definition Phase
This is where the proposed project, the need for it, is assessed using :
  feasibility or scoping exercises
    risk assessment
    cost-benefit-analysis
- a number of tools and assessment models
It is during this stage that you determine the relative importance of Time : Cost : Quality (see Slide 6)
Outputs from the use of these tools and techniques typically lead to a “Go : No-Go” decision
Auto Slide :
Please Wait
Notes: THE PROJECT DEFINITION PHASE
In this Phase we are seeking to clearly define what it is that we are to achieve – the Objective, the Timescale and the Budget - the three main points of the project management triangle shown in Slide 6. To help us do this we carry out the feasibility and scoping exercises.
Unless the feasibility study has already been conducted before the project was handed to us, we need to look at the risk involved, to conduct a cost-benefit analysis, apply a number of assessment tools and instruments. We need to carry out all or some of these (depending upon the size and scale of the Project and its importance) before typically we make a considered “GO : NO-GO” decision. This we do by accumulating the feed-back (outcomes) from the various tools and techniques mentioned here (and explained on the next few Slides), summarising these and making a final assessment as to whether the project should go ahead. Hence “GO” or “NO GO”………

## Slide 22: Tips, Tools and Techniques 1
DELIVERABLES
“SCENARIOS”*
FORCE-FIELD ANALYSIS*
SWOT and PEST analyses
COST BENEFIT ANALYSIS*
THE FIVE WHYS*
PRECEDENCE DIAGRAMS*
MILESTONES*
CRITICAL PATH ANALYSES*
Feasibility, Scoping & Risk Assessment Tools:
* We will look at each of these in
detail in the next few Slides
Planning, Scheduling & Monitoring Tools :
Auto Slide :
Please Wait
Notes: SOME USEFUL TIPS, TOOLS AND TECHNIQUES
In this Slide and those which follow, we will begin to look at some of the Tips, Tools and Techniques that apply to Project Management and which can help make it particularly effective, enhance considerably its chances of success. Here we give merely an overview.
DELIVERABLES are quite simply the Goals, Objectives and Outputs of the Project; they need to be clearly and accurately stated and defined at the very outset of a Project. Clear definition of the deliverables, and agreement of them with the Client/Sponsor, is essential if a Project is to be well planned, well organised and well “executed” (implemented).
SCENARIOS are a method of assessing how various Outcomes might be achieved: several Scenarios can be developed - and perhaps discussed with the Client - so as to decide which one(s) represent the best blend of Quality, Time and Money in achieving particular deliverables.
SWOT analyses help gather all the Strengths, Weaknesses, Opportunities and Threats that might be connected with the project and its delivery.
PEST (sometimes called STEP) is a similar tool used for gathering relevant external information (on Political, Economic, Social and Technological factors) which could impact upon the Project, affect its delivery.
COST BENEFIT ANALYSES are an important early step in many Projects - this is where the Project Manager and the Client address the key areas of cost and evaluate these against the potential benefits that successful delivery of the Project will bring. They are frequently carried out in conjunction with Scenarios.There is also a process known as the FIVE WHYS that can be used to test the fundamental reasons for actually carrying out the project.
PRECEDENCE DIAGRAMS (also known as “Network Logic Diagrams”) are very useful in determining the dependencies of various Tasks and Activities and can help determine Project
MILESTONES – key points or events during the project that provide major monitoring and “check”- points. From Precedence Diagrams critical scheduling and timing considerations can be made against Risk assessments to help the Project manager team calculate exactly how long it is going to take to complete a project.
NOTE : As well as most of the above being covered in detail in the Slides which follow, all of them are also covered in our Project Management Tool-Kit, supplied as part of our Introduction to Project Management workshops - and downloadable from our Knowledge Platform.

## Slide 23: Should we do this Programme/Project ?
There are tools and techniques which together help us “weigh up” whether a project is worth embarking upon and whether its costs justify the benefits :
  we should ask ourselves “why do it ?”
  and “should we do it?”
One technique we can use is the so-called “5 whys” approach (Slide 23)
Another is “Cost Benefit Analysis” (Slide 25)
  but not all projects are purely costs driven
  it is therefore worth careful evaluation of Benefits:
  not all projects have a primarily financial benefit
  remember Quality is also a key consideration
when all factors are taken into account the end result is to make a decision !
GO !
NO-GO!
?
Auto Slide :
Please Wait
To Do the project (“GO”) or Not To Do “No-GO”
Notes: COST BENEFIT ANALYSIS:
This is a very useful Tool that can be used early on in the Definition phase of a Project; it can be used to help determine the real or perceived Value of a project - a measurement of the outcomes and impacts of the project (the Benefits) against the Costs. Using Cost benefit Analysis the Project Manager can establish with the Client (also the Sponsor where relevant) the overall Value of carrying out the project. Cost Benefit Analysis can be especially useful, as we have said when used alongside SCENARIOS.
Scenarios are “what if” situations that are developed to facilitate comparison and assessment, the aim being to help the Project Manager to make decisions about preferred courses of action. Thus a number of different Scenarios can be developed, considered, the relative Values of each ascertained, and final decisions then made. See Next Slide :

## Slide 24: The “5 Whys”
Q. WHY put on two Project Management Courses ?
A. Because we need to train at least 50 of our Managers and key staff
Q. WHY do we need to train 50 Managers and key Staff ?
A. Because we want them to start doing Project Management
Q. WHY do we want them to do Project Management ?
A. Because it’s an efficient/effective way to do critical work
Q. WHY is it efficient & effective ?
A. Research shows we could deliver on time on within Budget; at present we often don’t.
Q.WHY do we want to deliver on-time and within Budget ?
A. Because that way we please our customers* - save time - save money - keep costs down
a useful Rationale to apply to get to the heart of why we are planning to undertake a particular project
See how we
use the 5 WHYS
to drive back to the Reason we need to do this Project
(based on the Scenario)
(SEE BELOW))
Auto Slide :
Please Wait
Notes: THE FIVE WHYS
This is a very useful technique that helps drive back to discover why you are really considering doing the project, finding out if it really fits with what, strategically and operationally the organisation requires.
We show in the Slide how this technique can be applied against our Scenario.
The outcome of using this technique in our Scenario seems to endorse the organisation’s need to become more efficient, more effective, more client - focussed (remember that clients can be “internal” as well as “outside” the organisation – the principles are the same!).
The “Five Whys” approach can be very usefully deployed in association with Cost Benefit Analysis, which is explained in the next Slide……..

## Slide 25: Cost Benefit Analysis
COSTS :
£5,300
to train 50 key staff
(= £106 per person)
BENEFITS
* it introduces project management into an organisation
*< 50 key staff get trained
* let us assume at least 25 adopt project management
* and carry out an average of 3 projects p.a (25 x 3 = 75)
* estimated saving per project = 8% of normal cost; normal cost = £8,000 per project (i.e saves £640 per project)
75 x (£8,000 x 8%) = £ 48,000 saving
TOTAL POTENTIALSAVING :
(£48,000 less £5,300) : £42,700 p.a.
a very important and useful tool that helps us consider the FINANCIAL impacts and benefits of carrying out particular projects
Cost Benefit Analysis for our ‘Scenario’ :
(you will need to refer to the “Scenario” - in Work Book or see Slide 17)
Auto Slide :
Please Wait
Notes: COST BENEFIT ANALYSIS
This is pretty much an ESSENTIAL of project management.
The Five Whys tests the reasoning, the drivers for actually doing the project. Cost Benefit Analysis (CBA) delves into the financial aspects of doing the project – a “value assessment” i.e it adds a vital financial dimension to the overall decision-making process. The CBA is developed by listing the benefits that the project will deliver and by ascribing values to those benefits.
Not all Projects, as we have said, will have a purely financial benefit; many benefits are qualitative and it is often hard to accurately calculate the financial benefits - but we must try. In our Scenario there are some key assumptions that need to be made before we can move to making some relevant calculations.
For instance how effective in our Scenario will the Workshops be, how many attendees will go back and actually start to adopt project management principles. Will it be 50% of the total attendees? What if its only 25%.? Then again if we could encourage say 75% of attendees to adopt it, what might our calculations, our savings, be then?
Upon investigation we have found that the average cost of a Project in the organisation is about £8,000, including labour. Some are much larger but many are relatively small. Also we have found from investigation within the NHS that there is a “yardstick”, (“benchmark”) figure that says once PM is adopted, savings of around 8% o the previous costs of doing “project-type” work are feasible. Hence we can make our calculations - these are estimates and we ought to run several Cost-Benefit “scenarios” using different values until we are satisfied that our calculations are realistic - and achievable !

## Slide 26: Force Field Analysis
Force-Field Analysis is a tool that helps
us assess the factors that drive and resist change
for our ‘Scenario’ – in Work Book (or see Slide 17)
REMINDER :
there are Notes
appended below
Notes: PREPARING AND USING A FORCE-FIELD ANALYSIS
The Force-Field analysis tool is very useful for capturing and presenting the factors which “drive” our project, set against those that could be “resisting” forces (or “constraints”). It helps us look at and assess the overall position - and to think about, how, if we decide to go ahead with the project, some of the resistors might be overcome. In the example above we have shown the principal Driving and Resisting forces relevant to our “Scenario”.
Drivers: In our Scenario the Director of Public Health (the “client”) is driving this; she believes there are real benefits to be had. Also within her organisation there are a growing number of people who believe a Project Management approach will bring greater efficiency. Some Team Leaders have heard about it and are keen to try and test the Project Management approach – as are some staff who have used it successfully elsewhere. Underpinning all of this is the premise that properly introduced into the organisation there are clear signs that Project Management will bring greater cost-effectiveness, better value-for-money.
Resistors : some people are saying they haven’t got time to do everything they are supposed to be doing - that they simply don’t have time to learn Project Management. There is also some “internal politics” around this subject, some resistance to the idea. A number of people fear its introduction, others have heard stories that efforts to introduce it elsewhere have not been wholly successful. There are others who strongly believe the Authority should invest right away in a proprietary project management system (e.g Prince or Microsoft’s Project 2000) which although considerably more expensive are felt to be more thorough, more advanced.
It can be a real help to the Project Manager and Project Team to consider these Drivers and Resistors in totality and to think about the potential conflicts and problems that might arise. A Force-Field Analysis can summarise at “a glance” the inter-face and identification of key issues relevant to a particular project. They are often well worth the effort in “piecing together”.

## Slide 27: Risk Assessment
there are a number of tools and techniques:
here we show a simple but quite effective numerical assessment :
SUGGESTION : LOOK HARD AT ANYTHING SCORING 25-30 +
REMINDER :
there are Notes
appended below
EXAMPLE :Risk of not getting minimum total of 35 people to the two Workshops
HOW LIKELY IS (this particular Risk) TO HAPPEN ?
1
10
Very
Unlikely
Extremely
Likely
5
Quite
Likely
6
HOW SERIOUS WILL IT BE IF IT DOES ?
1
10
Trivial
Extremely
Serious
5
Quite
Serious
6
RISK : 6 X 6 = 36
Auto Slide :
Please Wait
Notes: ASSESSING THE RISKS
There are two factors to take into account when assessing risks in undertaking a Project :
  1. How likely it is to happen? and 2. How serious will it be if it does?
In each case you should aim to rate the risk on a scale of one to ten. For instance, if you were assessing the risk of a labour dispute, you might decide it was fairly unlikely (3), but that the results would be very serious (9). You then multiply the two figures together (= 27) which will give you a figure between one and hundred. The higher the figure, the more seriously you need to treat the risk.
Planning for risk
Just about every task in your project will contain some element of risk. What the Project Manager has to do is decide at what level the risk should be regarded as serious.
A typical recommendation is that we use 25 on the risk assessment scale (medium likelihood multiplied by medium seriousness) as the “danger” point. Any task with a risk above that needs to be looked at in advance, and progress towards its completion monitored more carefully than usual. You may also need to have a backup plan for the most serious risks I.e how to deal with them should they occur. Very high levels of Risk - say 70+ - need to be very seriously considered, discussed with the Client because unless they can be reduced in some way they may be indicating that the project should not be undertaken at all
Recording risks
Once you have identified tasks where the risk is higher than average, you may find it helpful to record them in a “Risk Register”. Using such a document you can regularly review the positions, make notes on any actions taken and thus keep very careful control of the key risks. This approach encourages you to anticipate what might otherwise come as a complete surprise - possibly a nasty shock! It encourages you not only to recognise Risk – but also to manage it .
(Refer to Hobbs Pg 47 for full details of using the Risk Assessment technique.)

## Slide 28: Stage 2 : Planning Phase
Once a “GO” decision is made :
Clearly determine the AIM, GOALS & OBJECTIVES
Determine realistic Time-Scale & Budget
Agree GOALS and MISSION STATEMENT with CLIENT
Agree Deliverables, Time-Scale and Budget with CLIENT
Develop the PROJECT PLAN:
The Project Plan is the Key Document (OR Software) which
captures the Goals and Objectives
and develops/schedules the key
Actions, Activities and Tasks which
will deliver the Project :
- on time and within budget !
AIM OF PROJECT
GOALS & OBJECTIVES
BUDGETS
KEY DELIVERABLES
ALLOCATION RESOURCES
PEOPLE
EQUIPMENT
PROPERTY
MONEY
WORK BREAKDOWN
STRUCTURES :
WORK PACKAGES
PERFORMANCE TARGETS
SCHEDULES
MILESTONES
MONITORING POINTS
Project plan
PROJECT
PLAN
Auto Slide :
Please Wait
Notes: THE PLANNING PHASE
This is an absolutely critical stage - Phase 2 in the Project Life Cycle - not a stage to be skipped - or treated lightly! It is a vital part of the whole Project Management process. Time spent at this stage drafting realistic, yet flexible Plans will almost certainly pay dividends later.
You need to either write a good, practical Plan - or use one of many software packages to develop one on your Computer. It can then be used to steer and guide you through the demanding Implementational phases (Phases 3 & 4) that follow.
The PROJECT PLAN is the document that captures the Goals, Objectives and Outputs that need to be achieved by your project; it also helps you schedule the activities the Project Team will need to carry out to ensure that the Goals and Objectives are achieved – achieved, moreover, on Time and within Budget!
NOTE : In some organisations Project Managers are encouraged to write into the front-end of their plans brief “Mission Statements” that encapsulate just what the project is about, what it is being set up to achieve. A Mission Statement for our Scenario project might read “ To introduce the concept, practice and potential benefits of Project Management into the organisation by piloting introductory project management workshops for managers and key staff and by evaluating the impacts of these workshops within the organisation before making decisions on how next to proceed.”
The Plan then will use Deliverables and Time-Scales as primary foci and will identify Actions and Activities, which show just who will do what - and when ! It will also show how everything should fit together as part of an integrated, workable Plan that will deliver.
In the next few Slides we will cover some of the key Tools and Techniques that will be used to develop you Project Plan.

## Slide 29: Time and Precedences
“Estimating the time required for Tasks can be one of the most difficult parts of Planning a Project” (Hobbs Pg 42)
Precedence Diagrams are particularly useful because they show the links and relationships between Tasks across the whole Programme or Project and therefore aid the estimation of total time that a Project or Programme will take to complete. In particular Precedence Diagrams show tasks that are critical i.e those that must be completed before other linked work can proceed. They help Programme and Project Managers to spot potential “blockages” and “bottle necks” and to pay attention to them at the planning stage.
It is very important to work out the ‘dependencies’ between Tasks :
A ‘precedence diagram’ will help here. ( See Next Slide and Hobbs Pg 43)
LET’S MOVE NOW TO A SAMPLE PRECEDENCE DIAGRAM
Auto Slide :
Please Wait
Notes: Estimating Time in Projects :
Unless similar projects have been undertaken previously and experience from those projects then used to inform time estimation, calculating time for tasks in projects can be quite challenging. This is because many projects take place in “unfamiliar territory”.
For this reason it is advisable to break down larger Tasks into smaller, more manageable elements.
Also it is very important not to confuse “task time” with “lapsed time”: serious time over-runs can ensue if these distinctions are not made as , in the example shown above, what appears to be a “2 Day” job (the Agent gets paid for 2 days work) actually takes 10 days in practical terms before it gets delivered. There is a useful Formula for Estimating Time given in Hobbs’ Project Management guide (Pg 42).
DEPENDENCIES Another important factor to understand and plan for is the aspect of dependency - how and where certain tasks are dependent upon others being completed. For example, until the Publicity Piece mentioned above is actually received it cannot be distributed to relevant publications and editors. Most publications have strict deadlines for the receipt of material for particular issues. If these “deadlines” are missed then the publication of project-relevant publicity material may be delayed for a month, or even longer.
PRECEDENCE DIAGRAMS (sometimes referred to as “Network Diagrams) are visual aids which help Project Managers log all tasks and their dependencies; such diagrams help Project Managers see where time might be lost and therefore where estimated project delivery times may become extended. A Precedence Diagram covering our own Project is developed in Slide 30 and a further example featured on Page 43 of the Project Management Guide (Hobbs).

## Slide 30: Time & Precedences : Sample Diagram
sanction of
budget to
cover costs
of contractor
workshop
locations &
materials
by
25/5
by
31/5
recruitment
of Min 35
Delegates
of which
Min 20 for July
flyers out
by 03/6
35 Bookings
by 30/6
book two quality
delivery locations
and book Facilitator
for these dates
by
01/6
Delivery of
2 workshops
to
satisfactory
quality &
delegate
feed-back
levels
First on
25th July
Second on
22nd Sept
R
E
P
O
R
T
&
C
L
O
S
E
O
U
T
Workshop
structure
developed
& agreed
by
18/6
by
5/7
30th
Sept
further
Recruitment
if/as
necessary
July-
Sept
R
E
H
E
A
R
S
A
L
by
17/7
A
P
P
R
O
V
E
D
by
10/7
A
G
R
E
E
G
O
A
L
S
&
B
U
D
G
E
T
S
1ST May
2001
materials
prepared
& printed
1ST July
2001
1ST June
2001
1ST Aug
2001
PHASE 1
definition
PHASE 2
planning
PHASE 3
organising
PHASE 4
“executing”
PHASE 5
Close-Out
recruitment of
competent contractor
to develop/deliver
Bespoke Workshops
Workshop
content &
presntn.
developed
WRITE
PROJECT PLAN
*
*
*
*
*
*
*
*
*
*
1/
10
START
* Asterisks = “Milestones”
Auto Slide : Please Wait
Notes: Time/Precedence/Critical Path Chart
Here is a comprehensive Precedence Diagram governing the “Project Management Project”. It opens (dates in green) on 1st May and closes on 1st October. We show the various Phases of the Project Life Cycle across the foot of the chart.
Phase 1 (definition) sees the assessment of the project (Cost Benefit Analysis, Risk Assessment etc) and a “GO” decision made in mid-May. The Project Manager then “scopes” the project and sets about writing the Project Plan (Phase 2).
The Project Plan is completed by 25th May whereupon the Project moves into Phase 3 (Organising) and Phase 4 (Executing)
IMPORTANT NOTE : Before we describe Phase 3 (‘organising’) and Phase 4 (‘executing) - together we call these phases the “Implementation” phase - we ask you to note the two “strands” of the project that run along the upper (the blue boxes) and middle (the grey boxes) sections of our Diagram. These ‘strands’ of the project run concurrently, the tasks in each strand are not dependent upon the other.
Work in Phase 3 identifies (top line, blue boxes) suitable Contractors and (middle line, grey boxes) suitable Locations. Upon receiving Tenders for the work the Project Manager decides, for simplicity and better overall cost, to use an experienced Consultant who can both develop and deliver the Workshops. Meantime the Administrator contacts suitable venues and checks prices/availability. Availabilities of the chosen Consultant and the chosedn Location are correlated and agreed. By 1st June the Project has entered Phase 4 (“execution”) – which please note runs right through to 22nd September – the date on which the second of the two Workshops is delivered. Beyond this date the project enters into 5 Phase 5 (Close-Out); this begins on 23rd September and runs until the project ends on 1st October (allowing, therefore, just 8 days for evaluations to be collated, reports written and formal ‘close-out’ to take place).
But they are not entirely separate from each other - there needs to be correlation of dates and availability of both the Consultant and the quality locations for the Workshops – which, it is decided, will run on 25th July and 22nd September.
Critical points/actions are indexed with a red asterisk *. If any of these tasks are delayed (i.e over-run scheduled delivery dates) then the tasks that follow could well also have to be delayed - which may mean the whole project over-runs. On some items there may be some limited space to accommodate over-runs.
Q. Which two events look most important ? (i.e if they are not completed could cause the most serious problems).
A. The recruitment of delegates is a relatively high-risk item and problems will ensure if the target numbers (minimum35) are not achieved. However if a minimum of 18 can be recruited for the first workshop then, as we have said there is about 8 weeks before Workshop 2, in which further recruitment can take place. If the Consultants presentation (due on 15th July) is late (or unsatisfactory) then there is a real danger that delays will require postponement of the first workshop.

## Slide 31: Critical Paths
Critical Path Analysis can also help Project Managers see where there is “slack time” within their projects – time between Critical Tasks in which other non-critical tasks can be completed
It also helps identify “float times” - how long certain non-critical tasks may be delayed without affecting the overall length of the project.
Critical Path techniques are very useful beyond the fundamentals of
Project Management and are covered in more detail in an
Intermediate Module. You can get more information from the
Project Management Guide by Peter Hobbs pages 44-46
CRITICAL TASKS
SLACK TIME
FLOAT TIME
Once the Precedence Diagram has been developed, then
CRITICAL PATH ANALYSIS can be used to work out the
shortest time it will take to complete the project
(See Hobbs Pages 44 – 46)
Auto Slide :
Please Wait
Notes: Finally we come to Critical Path Analysis – a very useful technique that builds upon many of the fundamentals we have covered in this Module. Critical Path in fact lies at the cross-Roads of our Introductory into Intermediate Project Management Modules and here we will simply cover the essentials…….
  essentially the technique allows a Project Manager to realistically calculate the shortest time that a particular Project should take to deliver its Goals and Objectives. It does this by helping Project Managers understand those key tasks, activities and deliverables that are critical to many others.
The Precedence Diagram (see Slide 29) aids Critical Path Analysis, helps the understanding of relationships between tasks that go to make up a Project, helps to identify “slack” and “float” times that can be used to advantage within the overall concept of Project Management. Precedence Diagrams represent the activities of projects by “boxes” (or “nodes”) that contain essential information calculated about the project. Interdependencies between activities are represented by Arrows to show the flow of the project through its various stages. To ease visual representation and understanding information in precedence Diagrams, once determined, is typically converted to a GANTT chart, on which Software applications such as Microsoft’s “Project 2000” are based. GANTT charts are covered in Pages 51-55 of Hobbs’ Project Management Guide.
Our INTERMEDIATE Module will start with Timing, Precedence and a greater exploration of Critical Path before we examine some of the more advanced aspects of Project Management, especially some of the programmes and systems that can be used to help manage projects - on time, within budget and to high quality standards. It will look in detail at Project Close-Out and Hand-Over aspects which are covered briefly in Slide 41, and which can also be explored in Hobbs Chapter 6, Pages 84-91.

## Slide 32: The Project Plan : Records & Monitoring
draft the Project Plan
discuss it and its implications with the Team:
  preferably get the team involved with drafting the Plan
agree records, monitoring & communication systems
finalise and formalise the Plan :
  ensure it has “visibility”
identify the “key performance measures” (KPMs)
incorporate Milestones
maintain records, use regular Monitoring…..and Reviews
Auto Slide :
Please Wait
Notes: THE IMPORTANCE OF THE PROJECT PLAN
Used properly the PROJECT PLAN can be used to drive and steer the project through its various stages towards successful delivery - on time, within budget and to agreed Quality standards. Here we look in more detail at how the Project Plan is developed and used; we consider some of the main features of the Project Plan.
Typically, following the “scoping” of the project and any feasibility study and risk assessment, the Project Manager will begin to draft the Plan – typically working backwards from the “Deliverables” in order to develop the key components of the Plan that will be required to ensure it achieves overall success. Frequently Project Managers bring in their Project Team to contribute to the Plan’s development; this is a good way of establishing “buy-in” from the team members, encouraging shared responsibility, shared values and a shared commitment to making the project a Success. In Slide 33 we detail a useful approach (called “MetaPlanning”) to Project planning that many teams find particularly valuable.
It is important that a project “platform” for communication, monitoring and review of progress and problems is determined at an early stage and that the Plan once drafted becomes highly visible; this latter aspect is especially important; it is important not only to the Project Manager but also the team members - and often also the Client – in that they can see how the project is progressing “against Plan”. This means, of course, that the Project Manager must ensure that progress against Plan is clearly and regularly recorded and therefore “visible”.We cannot emphasise this “visibility” requirement too much! It is important that as the Plan is finalised the Project Manager and his/her team agree on a number of “key performance measures” (KPMs) (sometimes referred to as “key performance indicators” – KPIs ) that they will use in the processes of monitoring and review as the project progresses From the detailed planning it will be important to identify a number of key project MILESTONES - things or “bundles” of things that need to be achieved before the project can move on to subsequent phases. For more on Milestones see Slide 37/38.

## Slide 33: Tips,Tools and Techniques II Planning & Implementational Tools
“Deliverable Breakdown Structures”
Milestones
Work Breakdown Structures
Work Packages
Metaplanning
Critical Path Analysis
Project software :
  e.g Microsoft “Project” : CASE etc
GANTT Charts
REMEMBER :
there are Notes
appended below
AUTO SLIDE :
Please Wait
Notes: TIPS, TOOLS & TECHNIQUES FOR PROJECT MANAGEMENT II
We have considered “Deliverables” earlier in this Module – they are the Goals, Objectives and Outputs of the project. But we can also use them to start developing some structure into our project - this we do by using “DELIVERABLE BREAKDOWN STRUCTURES”.
MILESTONES we have also considered already - key points in the development of projects that Project Managers use to check progress, spot any developing problems that might affect the overall outcomes of the project. WORK BREAKDOWN STRUCTURES are commonly used devices that enable key areas and ‘packages’ of work to be defined. META-PLANNING can help here (see next Slide for details). Remember we recommended that in the planning stage, starting with the Deliverables, a Project Manager typically works backwards to consider what ‘packages’ of deliverables and therefore packages of tasks/actions (“WORK PACKAGES”) are key to achieving the project Goals and Objectives.
CRITICAL PATH ANALYSIS is, as we have said, a well used technique that enables a Project Manager to determine the shortest period in which a project can be delivered - and also helps define the key, critical aspects that will determine the ‘pathway’ to ultimate project success. Today Project Managers are increasingly turning to specialist SOFTWARE PACKAGES and applications to help them plan and manage their projects. Microsoft TM have developed a fairly sophisticated such package “Project 2000” which links readily with other Microsoft packages (e.g Word and Excel). Microsoft's “Outlook” package can also be deployed for scheduling of tasks and activities. There are many other such packages but to use them it is helpful to first understand the fundamentals of Project Management before moving on to more formal training, attempting to use what are quite sophisticated software packages.
Last but not least are GANTT charts…a GANTT is basically a bar-chart using time as its horizontal axis and in which the durations of tasks are represented geometrically. Project Managers use them to plot the key tasks, activities and milestones within the Plan and then to mark/monitor progress against these. A GANTT chart enables a graphical representation of sequential activities that need to be performed during the Project, helps the Project Manager schedule the various activities, understand their “inter-dependencies”. (See Tool-Kit for example)

## Slide 34: Deliverables
METAPLANNING :
a technique that helps
determine WORK
BREAKDOWN STRUCTURES
and WORK PACKAGES
A list of all the Key Items to be accomplished (delivered via the project)
  WHAT ? WHEN ? BY WHOM ?
There are END - deliverables i.e. “end products”
  e.g. : Workshop, Conference or Programme
  : fully tested and commissioned De-Salination Plant
….and there are MID-PROJECT deliverables
  e.g. : obtain suitable venue : and speakers
    : prepare and print Practicals or Hand-Outs
  : full working drawings and specifications pre Planning Applic’t’n
DELIVERABLES are used to determine
WORK BREAKDOWN STRUCTURES
and “WORK PACKAGES”
See notes appended below on how to use MetaPlanning
Auto Slide :
Please Wait
Notes: PROJECT DELIVERABLES :
Project Managers typically look first at the Deliverables of a Project and then, as we have said, tend to “work backwards”, from the deliverables, many of which will have been already considered in the “Definition” Phase of the project, to determine “Deliverable Breakdown Structures”, which are then used to to develop “WORK BREAKDOWN STRUCTURES”.
PRACTICAL
It is here that the concept called MetaPlanning can come in very useful:
This is ideally a team activity : take two packs of differently coloured “Post-It” notes, enough felt-tip pens for one per person; you’ll also need a whiteboard or any convenient flat surface (on which the Post-Its will be placed). Then : Re-state the Deliverables, developed from your Definition phase of the project, and any obvious constraints that have been identified. On one colour Post-Its work with the team to write all the Deliverables (outputs – things you’ll need to produce) and, on another colour, all the things you’ll need to do (= tasks and activities) to achieve the Deliverables.
Next : stick all the Post-Its on the chosen surface – initially in any sort of order. Then separate the Deliverables from the Tasks/Activities; use the Deliverables as the “headers” and then group all tasks relevant to each Deliverable underneath it. As the team do this encourage team members to place the tasks/activities in groups and/or “sequentially” (i.e the ones on which other tasks “depend” first). NOTE : during this stage you and your team may well think of additional tasks – in which case make out additional Post-Its and place them wherever they best ”fit”. Using this process you should, after discussion and a certain amount of moving the Post-Its around, have determined not only a Deliverable Breakdown Structure but also Work Breakdown Structures. You may well also be able to start adding the names of people who will undertake specific tasks and activities. This will help you to determine some groups of tasks/activities and their “dependencies” on each other – thus enabling you to establish some “Work Packages”. (See Hobbs pages 38-41)

## Slide 35: Scenario Deliverables
One WORKSHOP STRUCTURE - by 18th June
One POWERPOINT PRESENTATION
  to drive the Workshop delivery - by 10th July
2 WORKSHOPS for total of 35-50 managers/key staff
  highly-practical and held in good quality locations/venues - - on 25th July and 22nd September
min 35 “LEARNING EXPERIENCES” in project management - by 22nd September
min 35<50 delegate FEED-BACK/EVALUATION forms - by 22nd September
REPORT & RECOMMENDATIONS - by 30th September
PROJECT CLOSE-OUT - by 1st October
here we show the key Deliverables in our Project-in-a-Project Scenario and the dates they need to be delivered by
(refer Slide 29 : Time & Precedences)
Auto Slide :
Please Wait
Notes: PROJECT DELIVERABLES
Here are all the main deliverables relevant to our Scenario; we have shown them in order of when they need to be completed with the dates captured from the Time & Precedence Chart (Slide 30).
The last two Report & Recommendations and Project Close-Out are END deliverables, the others are Mid-programme/project deliverables.
NOTE : sometimes the Delivery of “deliverables” can be “milestones” nut, as we shall see, other key actions and achievements can represent Milestones.

## Slide 36: Work Breakdown Structures & Work Packages
it is a “top-down” process (i.e developed from “deliverables”)
by which we create a “work hierarchy”
  in which the lowest level is “a well-defined task for an individual to perform in a reasonable period of time”
WORK PACKAGES are derived from the WORK BREAKDOWN SRUCTURES
  Work Packages define:
  what is to be done
  who is responsible for doing it
  start and completion dates
  deliverables
  milestones
Work
Package
1.
we use Work Breakdown Structures to divide “pieces of work” into individual TASKS :
PROJECT
AUTO SLIDE :
Please Wait
Notes: WORK BREAKDOWN STRUCTURES
These flow naturally from the Deliverables Breakdown Structure and can be determined as mentioned by using “Metaplanning” techniques (using Post-Its).
Each “work-package” links back to a Deliverable and will form part of a least one Milestone. The use of Work Breakdown Structures and Work Packages helps to develop the project into ‘hierarchies’, the lowest level of which is a “well-defined task” (= one piece of work or group of tasks) for an individual to perform in a “reasonable period of time”.
See pages 38-41 in the Project Management Guide for a more detailed description of this process - and of the aspects and items that flow from them.

## Slide 37: Example of a Work Package
  structure agreed, signed-off and Structure delivered
  final agreed structure to be delivered by 18th June amendment of structure to Working group requirements
  draft structure to be delivered by 12th June instruct contractor to commence development obtain watertight contract
  agree satisfactory budget & development schedule (MILESTONE)
  locate competent external contractor
  is there competence/capacity in house OR do we need to use an external contractor ?
Q. WHO does this ?
A. Contractor with Project Manager
NOTE
these
are in
reverse
order
because
you
work
backwards
when
developing
Work
Packages
See
MetaPlanning
Slide 33
Deliverable = “Develop Course Structure”
REMINDER :
there are Notes
appended below
this is a logical way to determine Work Packages but see later NOTE :
Auto Slide :
Please Wait
Notes: EXAMPLE OF WORK-PACKAGE
Here we show a Work-package broken down from the key Scenario Deliverable of “Develop A Course Structure”. Following our metaplanning recommendation you would start with the deliverable and work backwards through the various steps that the project team will need to go through to get to this “destination”.
If you are using the Slide in auto-present mode than you will find that the steps arrive in the reverse order – just to remind us that there is a certain logic that applies when developing Work Packages.
For an excellent Example well away from our Scenario refer to Hobbs pg 43.

## Slide 38: Milestones
Milestones should be
  SPECIFIC
  MEASURABLE
  ACHIEVABLE
  REALISTIC
  TIME-BOUND
MILESTONES
(or “Checkpoints”) :
* milestones are key dates, key events or key deliverables in a project
make sure
milestones
are not
“millstones”!
1
2
3
4
“work packages”
key points or events in a project
REMINDER :
there are Notes
appended below
“on time”
“within
budget”
Auto Slide :
Please Wait
Notes: MILESTONES
OK, we’ve mentioned MILESTONES many times by now. That’s because they are IMPORTANT!
They are a particularly useful device that Project Managers can use as an aid to the measurement of performance and achievement against Plan.
In essence Milestones are “Checkpoints” along the “Critical Path” of a Project which enable the Project Manager to consider achievement and attainment against Plan as the Project develops. Milestones may well be key, critical events or actions which until achieved prevent movement through to subsequent parts and phases of the project. Or they might be “packages” of events and/or activities that need to be accomplished, again before progress to following Phases and Activities can be achieved.
Realistic determination of Milestones is essential – make them too stretching and the likelihood is that they are missed and that the project falls behind Schedule. Thus advice to project managers is : ensure that your selected Milestones are realistically achievable – don’t let them become ‘millstones’ (i.e impossible-to-achieve milestones that when missed weigh the project down, cause it to fall behind schedule and also potentially cause it to over-run on Cost).
There is an acronym - known as SMART - that can help us ensure that our Milestones don’t become “Millstones”. SMART stands for Specific, Measurable, Achievable, Realistic and Time-limited. It can be useful to test any Milestones you select against this,

## Slide 39: Examples of Milestones
  By 1st June we need to have a contract with Contractor for Workshop design and delivery by the required dates PLUS we need to book two suitable quality venues on dates on which Contractor can deliver the two workshops
  2. By 30th June we need to have recruited minimum 35 people for the workshops and have booked suitable venues for each Workshop
  3. By 10th July we need to have received and approved all materials and arrangements for delivery of the workshops (ahead of a Rehearsal set for 17th July)
  4. We need by 25th July to have satisfactorily delivered the first Pilot workshop
  5. We need to have satisfactorily delivered Workshop 2 on 22nd September
  6. The meeting scheduled for 1st October needs to make a decision on how best to proceed with further development of project management within the organisation
here we consider what Milestones will be most relevant to our Project-in-a-Project Scenario
Auto Slide :
Please Wait
Notes: SETTING THE PROJECT MILESTONES
In our Scenario there are a number of key actions/activities that would represent appropriate project “milestones”.
FIRSTLY, the Contract with an appropriate Contractor (Consultant) and correlation of delivery dates for the 2 workshops - with rooms booked and confirmed
THEN – very important that the recruitment processes are successful in signing-up the minimum 35 people for the two workshops (max target of fifty reached if possible) – otherwise further recruiting efforts to be mobilised.
NEXT the Completion by the Consultant of the presentation that will drive the two workshops - alongside the materials that will be used in those workshops.
NEXT, delivery of the two workshops – in fact each Workshop may well be a Milestone in itself – completion of the first generates feed-back that can be used to inform possible changes in the second, if felt necessary.
FINALLY, there is a clear requirement to collate all feed-back and for that and the Project manager’s Report & recommendations to inform the Meeting scheduled for 1st October at which decisions regarding how project management should be taken forward within the organisation will probably be made.

## Slide 40: Practical 4.
Relate a recent or current
project in which you have been
involved with these key elements.
DELIVERABLES
1.
WORK PACKAGES
3.
WORK BREAKDOWN STRUCTURES
2.
MILESTONES
4.
make notes under each heading
REMINDER :
there are Notes
appended below
Auto Slide :
Please Wait
Notes: PRACTICAL EXERCISE
Think back to the Project you considered in Practical 3 (Slide 14), then direct your thoughts a project you are currently involved in and :
Detail the main Deliverables
Develop the Work Breakdown Structures
Develop some typical Work Packages
Think what Milestones are appropriate and where they should be located
If you are not currently involved in a Project you may need to work with colleagues on this Exercise, to work through with them the above key areas/aspects of “Programme/Project life”.

## Slide 41: Phases 3 & 4 Organisation & Execution of Project
The following are key features of this stage:
hands-on management of the project
this is where the bulk of resources - and money! – are used
regular monitoring and reviews of progress against KPMs/KPIs
problem-solving as and when necessary
adjustment and flexing of the Plan
regular team meetings – and of Steering Group where such exists
positive communication between all Stakeholders
here all the tasks and activities are carried out
in accordance with the Project Plan
(the Implementation Phases)
Next Slide stresses the
importance of People in all this
REMINDER :
there are Notes
appended below
Auto Slide :
Please Wait
Notes: PHASES 3 & 4 IN THE PROJECT LIFE CYCLE (= “Implementation”)
These two Phases together are the “implementational” phase of a project - where the detail of the plan and the schedules are put into action. Thus the strength - or otherwise! - of the planning process will now shape the implementation, determine how successful that implementation will be. In Phase 3 (Organising) the Project Manager and his/her team will begin marshalling the resources needed to implement the various parts of the project whereas in Phase 4 (Execution) they go “hands-on” making the various tasks and activities happen - by the right people, at the right time - and to the required quality standards. It is in this Phase that the Project Manager’s skills and abilities are tested (sometimes in big and/or complex projects tested towards the “limits”). Project managers must constantly monitor progress, deal with any problems that arise. Actions taken, tasks achieved will be “marked off” on the Project Plan – either on a white-board in the office or, more likely these days, on a software application on a computer – or more likely on networked computers where members of the project team will be able to look to find out what is happening. Critical tasks will be given particularly close attention to ensure that they go smoothly and therefore don’t delay other following parts of the project.
Communication is a critical area at this stage - the “ground rules” and style/type of communication should have been set and advised by/to the project team so that everybody, including all stakeholders, is kept informed on how the project is going. There will need to be project-team meetings from time to time and in the light of experience adjustments may need to be made to the Plan. (There is further information about Communication in the “Managing Change” Modules)
IMPORTANT NOTE : This - highly active - Phase is where typically the Project Manager/Supervisor’s management skills are most challenged - where they will frequently need to be “fleet of foot”, dealing with problems, chasing progress on deliverables etc, ensuring that Milestones are met and that the goals and objectives of the project are delivered on time- and within budget.

## Slide 42: The People Factor Teams and Team-working
communication is very important
  types and methods of communication :
    Meetings, Memos, E-Mail, Shared Files (Project Management Software etc)
need to keep the team people involved
needs to be sense of “shared responsibility”
and shared values
key objective is to get “shared ownership” :
  of Goals and their Achievement
  of Activities and their Relevance
Forming : Storming :
Norming : Performing……..
singing from
the same
song-sheet
working together
towards
shared goals
(see notes below)
Auto Slide :
Please Wait
Notes: THE VALUE OF TEAMS AND TEAM-WORKING IN PROJECT MANAGEMENT
There is considerable evidence to show that team-work can play a significant part in Project Management - it is a key part of it, part of the focus on Results and on managing Resources. There are a number of key features of good team-work that are worth noting - and striving towards:
COMMUNICATION between the Project Manager and his/her team is a critical area : how do they communicate?: what do they communicate?; the key aim is to keep all members of the team fully up-to-date, know what is happening, understand how their roles and activities fit into “the whole”
INVOLVEMENT of the team in both the development and delivery of the Project can pay big dividends necessary; they start to work for each other, rather than merely with, or in the worst cases against each other; thus a sense of SHARED RESPONSIBILITY is a key attribute of high-performing Teams; a genuine sharing of VALUES amongst the team can further add to team harmony, higher performance.
TEAM-WORK can be so important that it is worth mentioning here the “classic model” of team development :
The team is firstly formed, created for a particular purpose i.e. a specific project. Then the team members begin to “storm” (in the sense of “brainstorming”) the project, its requirements, how they will work together etc. Typically there then follows a process of “norming” during which the team starts to work to agreed standards and work-practices that are “normalised” out of the two previous phases. It is at this stage, the fourth stage, where Teams begin to perform – not only to carry out the project activities but, working closely and carefully together to execute them to high standards. It is very useful for Project Managers and Project Co-ordinators to know and understand this Team-Working model; an understanding of the “dynamics” of team-working can help foster good team-working practices, help to ensure Projects are delivered on time, within budget and to the required Quality.

## Slide 43: PHASE 5 Project Close-Out
the Project Manager and team handle a number of “closure” tasks :
  end all tasks per Project Plan to required quality standards
  formally “hand-over” the deliverables to the Client and Sponsor
  close all financial aspects : payments out, payments in; summary
  review all aspects of the project : timing, performance, cost, quality
  conduct a formal Review (normally a meeting or series of meetings)
  complete a Close-Out report covering all the above
  hopefully celebrate success !
it is important that the Project Manager, Team and Organisation learn from the experience of running the project……
and that this learning informs future handling of projects !
the final Phase in which the project deliverables are handed-over to the Client and all project tasks and activities completed so that the project is effectively closed-down (hopefully on Time and within Budget!) :
(also known as “Hand-Over & Review”)
Auto Slide :
Please Wait
Notes: PROJECT CLOSE-OUT PHASE
This is an important final Phase of a project - one we strongly recommend is not skipped or skimped (but sadly, for a number of reasons, often is). It is a very important phase within the project management cycle and, done properly can help inform future projects, add to the overall value, the body of knowledge, within an organisation that flows from a project management approach.
The Close-Out phase is where the most senior person responsible for the project (Director, Manager, Supervisor) effectively “wrap up” all the details, tie up any “loose-ends”, pay-off contractors and externals, arrange the return of internal resource back to their normal organisational “home” and sort out all the remaining financial aspects to complete the budgetary process. Typically the senior person will then conduct a review of the project and compile a Report and Recommendations which is normally presented to the Client and/or Sponsor (where appropriate). This is where the senior person will formally hand-over the project to the Client/Sponsor. Often this is in the form of a Report summarising how the goals and objectives have been met, what overall budgetary factors apply, together with any recommendations for taking matters forward (e.g maintenance etc). Where there are tangible deliverables e.g. a book, a CD-Rom, a Database, an IT installation then a formal ‘hand-over’ of these takes place together with any relevant documentation – manuals, service agreements etc. In these circumstances the Client typically needs to formally “accept” the project deliverables before the project can be formally “closed-out”.
Assuming the project has been successful we strongly recommend that the senior person, maybe even the Client, arranges some kind of celebration for the project team and, where appropriate, key stakeholders, at an appropriate time and venue. Beyond this it is important that within the Close-Out the project manager/supervisor looks at and summarises the key learning points flowing from the project. This is important so as to inform not only those who have worked on the project but also to contribute to the body of knowledge about projects and project management within the organisation

## Slide 44: Review Time
Focus on OUTCOMES (deliverables)
PROJECT LIFE CYCLE :
  Define, Plan, Organise, Execute, Close-Out
Project Assessment : TIME : COST : QUALITY : RISK
  Why do it? : Cost Benefit Analysis : Feasibility Study : “GO” v “NO GO”
PROJECT PLAN
  Resources, Schedules, Costs
TEAMS & TEAM-WORKING
DELIVERABLE BREAKDOWN STRUCTURES
  work breakdown structures :
  work packages
MILESTONES
MONITORING & REVIEWS
CLOSE-OUT : Hand-Over
REVIEW plus…………one last thing ………….
these are the
main areas we have covered in this Module
there are Notes
appended below
Notes: Review of Project Management Introduction
Here in our (almost!) final Slide is a List of areas and items covered in this Module.
We suggest that you re-Visit those that are most relevant to you and your work, or those which, first time around, you found, perhaps, more difficult to understand.
Don’t forget to keep referring to the Project Management Guide, and using our Project Management Tool-Kit, both of which should prove useful as you continue to develop your project management knowledge
Oh, and we’ve mentioned it already but DON’T FORGET …….. (next slide :)

## Slide 45: celebrate SUCCESS !
DON’T FORGET ! :
Notes: PLEASE
Don’t Forget !
CELEBRATE SUCCESS !
Its all part of the Programme & Project Management approach !

## Slide 46: Research Sources
AN INTRODUCTION TO PROGRAMME & PROJECT MANAGEMENT
Key sources used for research for this presentation were:
“Project Management” Mike Field and Laurie Keller, Open University/Thomson Learning 1998 : “The Project Management Workshop”, James Taylor, Amacom 2001: “Project Management : The Essential Guide to Thinking and Working Smarter” Peter Hobbs, Video Arts/Marshall Publishing
KEY WORDS: Project, Project Management, Project Life Cycle, Budgets, Budgetting, Scheduling, Deliverable Breakdown Structures, Work Breakdown Structure, Work Packages, Resource Allocation, Project Management Software, Managing Risk, Project Planning, Assigning Tasks, Milestones, Estimating Time, Teams and Team-Working, Team Motivation, Monitoring and Control, Critical Path Analysis, Reporting, Stakeholders, Project Close-Out, Client, Sponsor
FURTHER SUGGESTED READING/MATERIAL: “Project Management”, Internet, “Harvard Manage Mentor”; “Planning, Scheduling, Budgetting”, Xebec McGraw Hill, Internet/Intranet/Multi-Media CD-Rom
Web Link : DFES ‘PPM’Site : http://www.dfes.gov.uk/ppm/
FINAL SLIDE
Notes: RESEARCH SOURCES FOR PROJECT MANAGEMENT
In this Module we have focused on the approach taken in the Video Arts “Project Management – the Essential Guide to Thinking and Working Smarter” workbook, written by Peter Hobbs, which we recommend as a well-presented guide to the fundamentals of Project Management and to understanding some of its key features. It also contains some excellent practical exercises that can be related to your own work area, your own projects and is also supported by a Video which can be hired or purchased from Video Arts.
The book covers certain areas in considerably more depth than this brief Introductory module and can be used to develop knowledge and application of the subject alongside the use of this Module.
IMPORTANT NOTE : The intellectual property of the construction, design and presentation of this Module, other than references to other works and materials which have been acknowledged within the texts, belongs to Martyn Laycock of the Knowledge College 2001
The copyright in this document is owned jointly by Martyn Laycock and Brent & Harrow Health Authority 2001. All Rights Reserved.